## Sheet1
Monthly Report | [7 empty] | MGSA
MPSA
Contracts (Executed Only) | [7 empty] | Schedule
SMP/SMA | Type of Contract* | Contract Value | [5 empty] | Supplement
Elaine Cantlon | Schedule | 3500000 | 1 |  |  |  |  | CAODC
Colleen Gibson | CAODC | 22000000 | 11 |  |  |  |  | COA
Colleen Gibson | MGSA | 19000000 | 3 |  |  |  |  | SFCA
Colleen Gibson | Schedule | 96000000 | 6 |  |  |  |  | PO
Ken Miller | MGSA | 5000000 | 1 |  |  |  |  | CA
Kevin Ross | Supplement | 1200000 | 1
Kevin Ross | Schedule | 100000 | 1 |  |  |  | CA
Lesley Dovichak | PO | 6000 | 1
Lesley Dovichak | MGSA | 1500000 | 3 |  |  |  | CAODC
Pan Su | SFCA | 2080000 | 8
Pan Su | Supplement | 100000 | 2
Stuart Kinnear | CA | 0 | 2
Candice MacLean | SFCA | 450000 | 3
RFP's (Issued)
RFP #/Name | Scope of Work | SMP/SMA | Value | Start Date | End Date | Status
RFP #347 Conventional Camps Voice, Data & Media Services | Voice, Data and Media Services at Conventional camps | Lesely Dovichak | 3000000 | 2014-01-07 | 2014-01-31 | RFP bid open |  |  | Savings
RFQ #342 Conventional Camp Fiber Optic Instal | Fiber optic install quote to Woodenhouse and Central Brintnell Camps | Lesely Dovichak | 3000000 | 2014-01-07 | 2014-01-31 | RFP bid open
Milling RFP | Septimus Project Pricng | Renato/Candice |  | Feb. 6/2014 |  | Pending Packages | Avoidance
Rental Equipment RFP | Septimus Project Pricng | Renato/Candice |  | Feb. 6/2014 |  | Pending Packages | Savings
Truck/Tank Moving RFP | Septimus Project Pricng | Renato/Candice |  | Feb. 6/2014 |  | Pending Packages
Safety RFP | Completions Safety Services | Renato/Candice |  | Dec .19/13 |  | Pending Packages
Production Testing RFQ | Septimus Project Pricng | Renato/Candice |  | Feb. 5/2014 |  | Pending Packages
Coil Tubing RFQ | Septimus Project Pricng | Renato/Candice |  | Feb. 5/2014 |  | Pending Packages
Safety RFQ | Septimus Project Pricng | Renato/Candice |  | Feb. 5/2014 |  | Pending Packages
Snubbing RFQ | Septimus Project Pricng | Renato/Candice |  | Feb. 5/2014 |  | Pending Packages
Fluid Hauling RFQ | Septimus Project Pricng | Renato/Candice |  | Feb. 5/2014 |  | Pending Packages
Financial (Cost Control)
Contractor | Scope of Work | Scope of Work Value | Type | Cost Control Value | Information | Business Area
Front 9 | Trash Pumps | 10000 | Avoidance | 1800 | Negotiated lower rate | Drilling
Iron Creek | Rig Matts | 7000 | Avoidance | 1800 | Negotiated lower rate | Drilling
Groundforce | Drilling Rig | 2000000 | Avoidance | 29250 | Negotiated lower rate | Drilling
Millennium EMS Solutions | Enviro Consulting | 1200000 | avoidance | 120000 |  | Environmental
Trace Associates | Enviro Consulting | 500000 | avoidance | 40000 |  | Environmental
Tenaris/Summit | Casing (7" TS Blue) | 714490 | Avoidance | 714490 | Inventory reutilization from one area to another | Drilling & Thermal
Tenaris/Summit | Casing (7" TS XP) | 300120 | Avoidance | 64950 | Eliminated need to purchase form Market by using internal goods | Thermal
RD Scan. Inc | On-Site Tubing Inspection | 6200000 | Avoidance | 241800 | Negotiated zero increase | Eastern Heavy Oil Operations
Key Initiatives (Going Forward)
Sanjel Audit Kickoff - Jan 31
RFP / RFQ Review
Procurement Plan for Logging and Coring (with Elaine Catlon)
Procurement Plan for securing Drilling and Coring Rigs for the 2014-2015 Strat Program
Procurement Plan for Delivery to Site Locations (review of current processes mail, courier, trucking, warehousing)
Securing Warehousing requirements/Operations for CDC (with Cassie)
Direct negotiation to secure purchase of 21 sand separator units (~$4M) while customizing a master rental agreement. Savings of 15% on rentals will be realized (estimating $350/year) Expecting to close before March 1 2014.
Discussion and prioritization of 2014 initiatives with Field Ops managers, to be finalized in February.
Procurement plan for E&I Labour is under development. Working with additional SM Stakeholders in consortium approach to develop a larger "category" strategy
Ongoing Barrick Contract Review
Regent T&C's elevated to Executive level.
Summit T&C's near completion
Forward progess with Tenaris T&C's
•RPF Electricall Wholsale Supply requirements to support Horizon, Conventional & Thermal
•Electrical & Instrumenation E&I Strategic Procurement Plan (working w/Operations & Major Projects)
•Primrose Pad BlueSky swivel joint rework project (establish new MGSA and Schedulas with Bonnyville Welding to commision rework)
•Write contract supplement to suport on-Site Acklands store at Horizon
•MRC annual Business Review
•Support Horizon with Fire Extiguisher maintenance initiative
•Support MRC VMI implementation initiative at Horizon