## Conventional Monthly Report
Update Contract Registry
Contracts Executed | [5 empty] | RFP or RFQ's Issued | [8 empty] | Financial/Cost Control
Month | SMA/SMP | Contract Type | Number Executed | Total Contract Value | Contractor / Notes | Month | SMA/SMP | RFP # | RFP Name | Scope of Work | Estimated Value | Issue Date | Closing Date | Notes | Month | SMA/SMP | Contractor | Scope of Work | Scope of Work Value | Type | Corrected type | Control Value | Information | Business Unit | Notes
|  |  | 179 | 484809144 |  |  |  | 17 |  |  | 51235000 | [7 empty] | 350443928.98 |  |  | 31990770.27 |  |  |  | Early Pay Program
January | Elaine Cantlon | Schedule | 1 | 3500000 |  | January | Lesley Dovichak | 347 | VDM | Voice, Data, and Media Services at Conventional Camps | 3000000 | 2014-01-07 | 2014-01-31 | Negotiation | January | Colleen Gibson | Front 9 | Trash Pumps | 10000 | Savings |  | 1800 | Negotiated Lower Rate | Drilling |  | April | 320280 | Q1 | DO NOT REPORT ON THE GRAPH FOR Y2D COST SAVINGS. THERE IS A SEPARATE GRAPH FOR EARLY PAY.
January | Colleen Gibson | CAODC | 11 | 22000000 |  | January | Lesley Dovichak | 342 | Fiber Optic Install | Fiber optic install quote to woodenhouse and central brintnell camps | 3000000 | 2014-01-07 | 2014-01-31 |  | January | Colleen Gibson | Iron Creek | Rig Matts | 7000 | Savings |  | 1800 | Negotiated Lower Rate | Drilling
January | Colleen Gibson | MGSA | 3 | 19000000 |  | February | Renato LanFranchie/Candice MacLean | 358 | Milling RFP | Septimus Project Pricing | 450000 | 2014-02-06 | 2014-03-05 |  | January | Stuart Kinnear | RD Scan Inc. | On-Site Tubing Inspection | 6200000 | Avoidance |  | 241800 | Negotiated No Increase | Eastern Heavy Oil Operations
January | Colleen Gibson | Schedule | 6 | 96000000 |  | February | Renato LanFranchie/Candice MacLean | 361 | Rental Equipment RFP | Septimus Project Pricing | 700000 | 2014-02-06 | 2014-03-05 |  | January | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 600000 | Asset Utilization |  | 250000 | Customer Property Utilized in Nov & Dec 2013 | Completions
January | Ken Miller | MGSA | 1 | 5000000 |  | February | Renato LanFranchie/Candice MacLean | 363 | Truck/Tank Moving RFP | Septimus Project Pricing | 700000 | 2014-02-06 | 2014-03-05 |  | January | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 600000 | Asset Sales |  | 55000 | Customer Property Sales in Nov & Dec 2013 | Completions
January | Kevin Ross | Schedule | 1 | 100000 |  | February | Renato LanFranchie/Candice MacLean | 356 | Production Testing RFQ | Septimus Project Pricing | 1500000 | 2014-02-05 | 2014-02-28 |  | January | Renato Lanfranchi | Vertex Professional Services | Surface Casing Vent flow and gas migration services | 54800 | Rebate |  | 5758.2 | Monthly rebate Cheque | Completions
January | Lesley Dovichak | PO | 1 | 6000 |  | February | Renato LanFranchie/Candice MacLean | 357 | Coil Tubing RFP | Septimus Project Pricing | 2500000 | 2014-02-05 | 2014-02-28 |  | January | Renato Lanfranchi | Various | Snubbing Services | 3750000 | Savings |  | 120000 | RFP for 2014 | Completions
January | Lesley Dovichak | MGSA | 3 | 1500000 |  | February | Renato LanFranchie/Candice MacLean | 359 | Safety RFQ | Septimus Project Pricing | 320000 | 2014-02-05 | 2014-02-28 |  | January | Renato Lanfranchi | Various | Production Testing | 23230000 | Savings |  | 1520000 | RFP for 2014 | Completions
January | Pan Su | SFCA | 8 | 2080000 |  | February | Renato LanFranchie/Candice MacLean | 362 | Snubbing RFQ | Septimus Project Pricing | 350000 | 2014-02-05 | 2014-02-28 |  | January | Renato Lanfranchi | Various | E-Line Services | 21800000 | Savings |  | 573000 | RFP for 2014 | Completions
January | Pan Su | Supplement | 2 | 100000 |  | February | Renato LanFranchie/Candice MacLean | 360 | Fluid Hauling RFQ | Septimus Project Pricing | 1500000 | 2014-02-05 | 2014-02-28 |  | February | Colleen Gibson | Groundforce | Drilling Rig | 2000000 | Avoidance |  | 29250 | Negotiated Lower Rate | Drilling
January | Candice MacLean | SFCA | 1 | 150000 |  | February | Renato LanFranchie/Candice MacLean | 335 | Safety RFP | Completions Safety Services | 10600000 | 2014-02-19 | 2014-02-24 |  | February | Kevin Ross | Millennium EMS Solutions | Environmental Consulting | 1200000 | Avoidance | Cost Savings | 120000 | Preferred rates, early pay, lowered disbursement fee, took out 5% holdover fee | Environmental
January | Allan Romero | COA | 5 | 700000 |  | April | Colleen Gibson | 394 | Bonnyville General Contractor | General Contractor for Bonnyville Renovations | 300000 | 2014-04-30 | 2014-06-06 |  | February | Kevin Ross | Trace Associates | Environmental Consulting | 500000 | Avoidance | Cost Savings | 40000 | Preferred rates, early pay, lowered disbursement fee, took out 5% holdover fee. Cell phone, sat internet, electrical conductivity meter, soil prove, pin finder, quantab, and ground water monitoring supplies charges | Environmental
February | Kevin Ross | Supplement | 1 | 1200000 |  | April | Candice MacLean | 405 | Reserve Fund Study | Reserve Fund Study for FMM condos | 15000 | 2014-04-17 | 2014-04-28 |  | February | Cam Woo | Tenaris/summit | Casing | 714490 | Asset Utilization |  | 714490 | Inventory reutilization from another area | Drilling
February | Stuart Kinnear | CA | 2 | 0 |  | May | Elaine Cantlon | 426 | Well File Scanning Services | Scanning of Well Files | 2300000 | 2014-05-14 | 2014-05-29 |  | March | Colleen Gibson | Ensign Drilling | Drilling Rig | 2000000 | Savings |  | 1125 | Strat Program Flare Tank Rental Negotiations | Drilling
February | Candice MacLean | SFCA | 2 | 300000 |  | June | Cam Woo/Dale Palmer | 429 |  | Supply of Polymer to Brintnell | 21500000 | 2014-06-06 | 2014-06-30 | 2 years | March | Colleen Gibson | BlueRock Energy Services | Drilling Rig | 5000000 | Savings |  | 155660.71 | Review and Credit for Non Productive Rig Time originally billed to CNRL | Drilling
February | Pan Su | SFCA | 4 | 1040000 |  | June | Candice MacLean | 443 | Lindbergh Environmental Assessment | Lindbergh In Situ Oil Sands Project - Environmental Assessment | 1500000 | 2014-06-20 |  | For Kevin Ross | March | Candice MacLean / Renato Lanfranchi | Precision | Snubbing Services | 346560 | Savings |  | 116640 | RFQ 362 - Septimus | Completions
February | Pan Su | Supplement | 2 | 100000 |  | June | Candice MacLean | 441 | Geotextile Material | Geotextile Material for Lease/Road Construction | 1000000 | 2014-06-13 | 2014-06-26 |  | March | Candice MacLean / Renato Lanfranchi | Mustang | Trucking & Tank Moving | 700000 | Savings |  | 77000 | RFP 363 - Septimus | Completions
February | Allan Romero | COA | 11 | 1540000 | [10 empty] | March | Renato Lanfranchi | Vertex Professional Services | Surface Casing Vent flow and gas migration services | 84925 | Rebate |  | 4458.56 | Monthly rebate Cheque | Completions
February | Lesley Dovichak | MGSA | 1 | 10000000 | Bigstone (Catering & Housekeeping WDH Ops & Camp 2) | [9 empty] | March | Candice MacLean / Renato Lanfranchi | Various | Safety Services | 10600000 | Savings |  | 890000 | RFP 335 for 2014 | Completions
March | Stuart Kinnear | CAODC | 1 | 20000000 | Signed Tervita's CAODC and Utilization Based Pricing Deal. | [9 empty] | March | Candice MacLean / Renato Lanfranchi | Precision | Coil Tubing | 2422200 | Savings |  | 512116.67 | RFQ 357 -Septimus | Completions
March | Colleen Gibson | CAODC | 1 | 2000000 | PD 133 | [9 empty] | March | Candice MacLean / Renato Lanfranchi | TTS | Milling | 410585 | Savings |  | 195459.5 | RFP 358 - Septimus | Completions
March | Colleen Gibson | CAODC | 1 | 2000000 | Superior 5 | [9 empty] | March | Candice MacLean / Renato Lanfranchi | Firemaster | Safety Services | 317665 | Savings |  | 91165 | RFQ 359 - Septimus | Completions
March | Colleen Gibson | CAODC | 1 | 2000000 | PD 118 | [9 empty] | March | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 610723 | Asset Utilization |  | 445017 | Customer Property Utilized in Jan & Feb 2014 | Completions
March | Colleen Gibson | Supplement | 1 | 5000000 | Welltec | [9 empty] | March | Justin Ball | Enerchem | Premium & Secondary Diluents | 10500000 | Savings |  | 4120000 | RFP 300 | Conventional Operations | 6-month contract banked $1.62M + est.$2.5M)
March | Ken Miller | MGSA | 1 | 2000000 | SDI - Sand Seperators | [9 empty] | March | Kevin Ross | LandSolutions | Surface Land Acquisition | 900000 | Savings | Cost Savings | 250000 | RFP | Surface Land
March | Dale Palmer | PO | 1 | 150000 | Alkaline | [9 empty] | March | Kevin Ross | RBW | Haz Bins | 776542 | Avoidance | Cost Savings | 38827 | Rate Negotiation | Ops, Enviro, Drilling
March | Dale Palmer | PO | 1 | 250000 | Nano Polymer | [9 empty] | March | Kevin Ross | Tervita | TRDs | 16200000 | Avoidance | Cost Savings | 238140 | Rate Negotiation | Ops, Enviro, Drilling
March | Candice MacLean | SFCA | 3 | 750000 | [10 empty] | March | Kevin Ross | Tervita | Landfills | 21800000 | Avoidance | Cost Savings | 21800 | Rate Negotiation | Ops, Enviro, Drilling
March | Candice MacLean | MGSA | 1 | 4000000 | [10 empty] | March | Dale/Jenny | Univar | Chemicals | 20466041.24 | Rebate |  | 77327.31 | Contracted Q 1 rebate | Conventional Operations | $54,167.55 still outstanding
March | Elaine Cantlon | MGSA | 1 | 52000000 | Spilak | [9 empty] | April | Colleen Gibson | Van Houtte | Coffee Contract | 1300000 | Savings |  | 6119.8 | Billed incorrectly | Corporate Services
March | Allan Romero | COA | 2 | 280000 | [10 empty] | March | Candice MacLean / Renato Lanfranchi | FMC | Production Testing | 1505911.25 | Savings |  | 72414.65 | RFQ 356 - Septimus. After award FMC offered an 7% discount on specific equipment | Completions
March | Allan Romero | MGSA | 1 | 7000000 | ATCO; Camp Maintenance | [9 empty] | March | Ken Miller | Specialized Desanders Inc | Surface Equipment - Desanders | 5000000 | Avoidance |  | 1500000 | Converted Rental to purchase | Field Operations | Combination Savings + Avoidance.
March | Kevin Ross | MGSA | 1 | 1300000 | Enviroconsulting | [9 empty] | March | Ken Miller | Rocksteady Oilfield Services Inc | Transportation: Fluid Haul | 2000000 | Avoidance |  | 330000 | 17% reduction in fixed pricing | Field Operations | 1 year savings.
March | Lesley Dovichak | MGSA | 1 | 4000000 | PDCNC - Primrose | [9 empty] | March | Allan Romero | 24/7 Compression Ltd | Mechancial Parts | 2541876.53 | Rebate |  | 52812.41 | Volume Rebate 2% Net Sales | Field Operations | 1 year savings.
March | Renato Lanfranchi | MGSA | 1 | 400000 | Team Snubbing - Snubbing Services | [9 empty] | March | Jenny Tejeda | Superior Propane | Labour rates (Jan - Mar) |  | Savings |  | 471036 | Reduction in service rates | Field Operations | Ytd will revisit each quarter
March | Renato Lanfranchi | MGSA | 1 | 750000 | Powerstroke - Snubbing Services | [9 empty] | March | Jenny Tejeda | Superior Propane | Equipment rates (Jan - Mar) |  | Savings |  | 338000 | Negotiatioed priceReduction in rental equipment rates | Field Operations | Ytd will revisit each quarter
March | Renato Lanfranchi | Schedule | 1 | 500000 | Piston Well - Snubbing Services | [9 empty] | March | Justin Ball/D Palmer | PetroCanada/Weatheford | Rebate for PetroCanada Lubes | 23000000 | Savings |  | 103575 | Pass on CNRL rates for lubes purchased from Weatherford | Conventional Operations
March | Renato Lanfranchi | MGSA | 1 | 500000 | Snub Force - Snubbing Services | [9 empty] | March | D Palmer | Champion/Nalco | transport billing methodology | 23000000 | Avoidance |  | 300000 | Standardized transport billing methodology | Conventional Operations | estimated avoidance for 2014
March | Renato Lanfranchi | MGSA | 1 | 800000 | Dawson - Production Testing | [9 empty] | March | D Palmer | Champion/Nalco | Barrick Energy using CNRL rates | 23000000 | Rebate |  | 361414 | Barrick to use CNRL price list | Conventional Operations
March | Renato Lanfranchi | MGSA | 1 | 3000000 | Haltech - Production Testing | [9 empty] | April | Kevin Ross | Newalta | Landfill | 900000 | Avoidance | Cost Savings | 180000 | Rate Negotiation | Ops, Enviro, Drilling
March | Renato Lanfranchi | Supplement | 1 | 700000 | Northern Snubbing - Snubbing Services | [9 empty] | April | Kevin Ross | RBW | Haz Bins | 1500000 | Savings | Cost Savings | 75000 | Changed bins | Ops, Enviro, Drilling
March | Renato Lanfranchi | MGSA | 1 | 450000 | TTS - Septimus Milling Services | [9 empty] | April | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 431571 | Asset Utilization |  | 162989 | Customer Property Utilized in March 2014 | Completions
March | Renato Lanfranchi | PO | 1 | 11000 | Digital Ally - Corporate Security | [9 empty] | April | Renato Lanfranchi | Vertex Professional Services | Surface Casing Vent flow and gas migration services | 93325 | Rebate |  | 6257.55 | Monthly rebate Cheque | Completions | March rebate
March | Renato Lanfranchi | Schedule | 1 | 350000 | Firemaster - Septimus Safety Services | [9 empty] | April | Colleen Gibson | Earth Fluids | Drilling Fluids | 5000000 | Savings |  | 152435.31 | Discounts given in Q1 based on the number of rigs EF is supplying product to | Drilling
March | Renato Lanfranchi | Supplement | 1 | 2500000 | Firemaster - 2014 Safety Services | [9 empty] | April | Lesley Dovichak | 1227415 Alberta Ktd. Operating as CAMPtek | Voice, Data and Media Services | 1300000 | Savings |  | 5900000 | RFP #347 for conventional camp VDM services | Camps | Savings over 3 year term of agreement vs current provider.
March | Elaine Cantlon | PO | 1 | 138000 | Willowstick Tech - Testing | [9 empty] | April | Colleen Gibson | Contemporary Office Interiors | Office Chairs | 2000000 | Savings |  | 850 | Avoided Manufacturers Increase due to notification period less than 30 days | Corporate Services
March | Pan Su | SFCA | 3 | 780000 | [10 empty] | April | Colleen Gibson | Purolator | Courier | 300000 | Savings |  | 276268.12 | Savings through discounts | Corporate Services
March | Pan Su | Supplement | 2 | 100000 | [10 empty] | April | Allan Romero | Frontier First Aid Services Ltd. | Helmet First Aid Services | 1000000 | Avoidance |  | 82416 | Rate Negotiation | Field Operations | Savings over 2 year term of agreement vs current state
March | Candice MacLean | Supplement | 1 | 50,00.00 | [10 empty] | May | Candice MacLean | Canadian Base Operators (CBO) | Ground Handling Services | 1400000 | Avoidance |  | 100000 | Invoice negotiations/incorrect billing | Thermal Field Ops
March | Candice MacLean | SFCA | 5 | 1300000 | [10 empty] | May | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 323850 | Asset Utilization |  | 78647 | Customer Property Utilized in April 2014 | Completions
March | Ken Miller | MGSA | 1 | 5000000 | Specialized Desanders (SDI) | [9 empty] | May | Renato Lanfranchi | Vertex Professional Services | Surface Casing Vent flow and gas migration services | 31990 | Rebate |  | 2351.27 | Monthly rebate Cheque | Completions | April rebate
March | Colleen Gibson | CAODC | 1 | 4000000 | Nabors 27 extended | [9 empty] | April | Javier Acosta | Weatherford | Surface Equipment | 12064671 | Avoidance |  | 550206 | Currency index Matrix rejection proposed by Supplier | Heavy Oil Field Operations
April | Colleen Gibson | CAODC | 1 | 4000000 | Quintera 6 | [9 empty] | April | Javier Acosta | Europump | Surface Equipment | 10700000 | Avoidance |  | 495580 | Currency index Matrix rejection proposed by Supplier | Heavy Oil Field Operations
March | Colleen Gibson | MGSA | 1 | 300000 | Purolator | [9 empty] | April | Justin Ball | Newalta | Slop Oil Treatment | 2600000 | Savings |  | 200000 | Negotiated lower rental rate from NewAlta | Conventional
April | Stuart Kinnear | CAODC | 1 | 2000000 | Galleon Well Servicing | [9 empty] | May | Justin Ball | Tervita | Mobile Waste Treatment Facility | 3600000 | Savings |  | 722000 | Negotiated lower purchase price from Tervita for the purchase of their mobile waste treatment facility | Conventional
April | Kevin Ross | MGSA | 1 | 50000000 | Tervita - Waste/Environmental | [9 empty] | May | Justin Ball | Tervita | Mobile Waste Treatment Facility | 466200 | Savings |  | 82200 | Negotiated lower daily operating rate for the operation of the mobile treatment facility | Conventional
April | Colleen Gibson | Supplement | 1 | 44000000 | Halliburton - cementing | [9 empty] | May | Justin Ball | Tervita | Mobile Waste Treatment Facility |  | Avoidance |  | 2369580 | Negotiated shorter term service agreement from Tervita from 2 years to 3 months for the contracted operation of the mobile treatment facility | Conventional
April | Cassie Doucette | MGSA | 1 | 2000000 | T-Bar 1 - Transportation and Warehousing | [9 empty] | May | Stuart Kinnear | Tuboscope | Sucker Rod Inspection and Repair | 51742 | Asset Utilization |  | 124400 | Difference between re-utilizing rods vs. buying new. | Conventional
April | Colleen Gibson | MGSA | 1 | 1500000 | Razor Vac | [9 empty] | May | Stuart Kinnear | Tervita Production Services | Well Servicing | 25000000 | Savings |  | 23895 | Service Rig Utilization Based Pricing Discount | Conventional
April | Colleen Gibson | MGSA | 1 | 1500000 | Drillers Directional | [9 empty] | May | Allan Romero | Gas Drive | Mechanical Parts and Labour | 7181260.96 | Savings |  | 57500.16 | 3% Discount on parts and labour when combined for compressor overhauls in 2013 | Conventional
April | Pan Su & Cassie Doucette | SFCA | 10 | 2600000 | [10 empty] | May | Colleen Gibson | Loomis | Courier | 300000 | Savings |  | 22 | Corrected Billing | Corporate Services
April | Pan Su & Cassie Doucette | Supplement | 4 | 200000 | [10 empty] | May | Colleen Gibson | VanHoutte | Coffee Supplier | 1200000 | Savings |  | 30943.56 | Negotiated Rates for Calgary and field offices | Corporate Services
April | Dean Boyarski | Supplement | 1 | 18000 | AGI - SCBA testing at Horizon | [9 empty] | May | Colleen Gibson | Lyreco | Stationery and Paper Supplier | 1700000 | Savings |  | 330117.15 | Negotiated Rates | Corporate Services
April | Dean Boyarski | Supplement | 5 | 6850000 | EECOL Electric | [9 empty] | May | Kevin Ross | Tervita | Landfills | 21800000 | Savings | Cost Savings | 5000 | Invoicing Issues | Ops, Enviro, Drilling
April | Allan Romero | COA | 3 | 420000 | [10 empty] | May | Kevin Ross | Trace Associates | Enviro Consulting | 500000 | Savings | Cost Savings | 70000 | Rate Negotiations + Volume Discount | Enviro
April | Allan Romero | MGSA | 1 | 500000 | Frontier First Aid Services | [9 empty] | May | Kevin Ross | TerraLogix | Enviro Consulting | 900000 | Avoidance | Cost Savings | 18000 | Rate Negotiation | Enviro
April | Allan Romero | Schedule | 1 | 30000000 | E-Can; Production Services | [9 empty] | May | Colleen Gibson | Precision Drilling | Rig Supplier |  | Savings |  | 1225000 | Avoidance of costs for not accepting proposal increase of a $350.00/day rate increase from for 14 drilling rigs | Drilling
April | Ken Miller | MGSA | 1 | 2000000 | Rocksteady Oilfield | [9 empty] | May | Kevin Ross | Tervita | Landfill | 200000 | Savings | Avoidance | 200000 | Canceled new engineering plans, not required | Horizon
April | Candice MacLean | SFCA | 5 | 1300000 | [10 empty] | June | Kevin Ross | Can-Am | Surveying | 11250000 | Avoidance | Cost Savings | 1285000 | Rate negotiations | Surface Land
May | Dean Boyarski | MGSA | 1 | 2000000 | Bonnyville Welding | [9 empty] | June | Allan Romero | Gas Drive | Mechanical Parts and Labour | 1500000 | Savings |  | 29580 | Negotiated Rates | Conventional
May | Candice MacLean | Schedule | 1 | 500000 | AMEC - Engineering & Grading Work | [9 empty] | June | Dale/Jenny | Superior | Propane-Equipment rental |  | Avoidance |  | 338000 | August 2013:Negotiatioed price decrease for Equipment Used to be $275 new price $120 for vapourizers | Conventional/Horizon
May | Stuart Kinnear | MGSA | 1 | 20000000 | KMC Oilfield Maintenance | [9 empty] | June | Dale/Jenny | Superior | Propane-Service |  | Avoidance |  | 471036 | October 2013: $40 charge for "misc. per W/O removed | Conventional/Horizon
January | Javier Acosta | MGSA | 1 |  | West Oilfield Services | [9 empty] | June | Dale/Jenny | Superior | Propane-Equipment rental 99" regulators |  | Avoidance |  | 68400 | Negotiatioed new price for Equipment Used from $200 to new price $50 for 99-513P Regulator .We are using in Heavy Oil . Also we are getting more regulators | Conventional
January | Javier Acosta | schedule | 1 | 2500000 | West Oilfield Services | [9 empty] | June | Elaine Cantlon | Maxxam Analytics | Oil and Gas Chemistry | 2311752.69 | Rebate |  | 85958.18 | Negotiated rebate based on 5% of spend over a comulative threshold of 500K within a 12 month period. | Field Operations | Ytd will revisit each quarter
May | Laura Gerber | SFCA | 1 | 286000 | BC Welding Co. Ltd. | [9 empty] | June | Dale/Jenny | Univar | Chemicals | 20466041.24 | Savings |  | 220500 | cost saving on a techical services for Q1 | Conventional
May | Laura Gerber | SFCA | 1 | 286000 | Jimmy Scar Pipefitting and Oilfield Maintenance Ltd. | [9 empty] | June | Dale/Jenny | Univar | Chemicals | 20466041.24 | Savings |  | 589806.7 | CNRL price savings | Conventional
June | Laura Gerber | SFCA | 1 | 286000 | Melda Investments Ltd. | [9 empty] | June | Allan/Ken | Gas Drive | Mechanical Parts | N/A | Avoidance |  | 31832 | Held back $0.20/km proposed increase on truck mileage | Conventional | Discussion held in Q1, reported when Contract executed.
June | Candice MacLean | SFCA | 6 | 1560000 | Calgary Office Consultants | [9 empty] | June | Renato Lanfranchi | Vertex Professional Services | Surface Casing Vent flow and gas migration services | 57608.13 | Rebate |  | 4368.46 | Monthly rebate Cheque | Completions | May rebate
June | Candice MacLean | Supplement | 1 | 8000000 | Early Pay Supp. - Clayton | [9 empty] | June | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 172033 | Asset Utilization |  | 65714 | Customer Property Utilized in May 2014 | Completions
June | Candice MacLean/Renato L | Supplement | 7 | 10000000 | Safety Services - Various | [9 empty] | July | Kevin Ross | Vertex Professional Services | Land Admin | 3100000 | Avoidance | Cost Savings | 403000 | Rate Negotiations | Surface Land
June | Candice MacLean/ Renato L | MGSA | 1 | 600000 | Safety Services - CIP | [9 empty] | July | Renato Lanfranchi | GE Oil & Gas | Wellhead Supply and Service | 671049 | Asset Utilization |  | 112630 | Customer Property Utilized in June 2014 | Completions
June | Laura Gerber | COA | 6 | 840000 | 6 Operators on the list from Devon
July | Laura Gerber | SFCA | 1 | 280800 | Encore Environmental Ltd
July | Kevin Ross | Schedule | 1 | 157344 | Visser Consulting Ltd.
Note on O20: Hamilton Nkwonta: RFP Close date extended to July 7th.

## Reference (hidden)
MGSA | Avoidance | January
MPSA | Savings | February
Schedule | Rebate | March
Supplement | Asset Sales | April
CAODC | Asset Utilization | May
COA |  | June
SFCA |  | July
PO |  | August
CA |  | September
October
November
December

## OPS only - Weekly Tasks
Instructions: Add the tasks that you are working on, and update them in-line with the previous note with different colour text (Black color will be the work done on the previous weeks). Write in red for highlighting the important subjects. Add RFx/Contracts estimated value when possible/applicable. Hid the line the month after being closed and reported. Laurence to highlight the cells in "pink-red" for her own use (follow-up/update).
In progress
Closed
Start Date | Vendor / BU / Area | Task Details | Status | SMA/SMP | Reported by LD
2014-04-01 | Tervita | CAODC Executed | Closed | Stuart Kinnear
2014-04-01 | Corporate Services | Developing MGSA for Van Houtte (coffee services) | In progress | Colleen Gibson
2014-04-01 | Corporate Services | Developing Schedule Amendment for Lyreco (stationery services) | Closed | Colleen Gibson
2014-04-01 | Drilling | Developing MGSA for Razor Vac (vac services) | Closed | Colleen Gibson
2014-04-01 | Drilling | Developing MGSA for Drillers Directional (directional drilling services) | Closed | Colleen Gibson
2014-04-01 | CDC | Beginning to source and procure items for CDC (with Cassie). Awaiting Management Approval on budget before actually procuring items. Budget approved for 250K in which $195,171.59 has been allocated to purchase 131 items. ($6,983.34 for warehouse supplies and $188,734.25 for equipment to service). Several PO will be issued to procure the approved items. | In progress | Colleen Gibson | tbr when more information
2014-04-01 | Reporting | Managing Monthly and weekly reporting spreadsheets. | Closed | Stuart Kinnear
2014-04-01 | Drilling | Working with Rig companies to restructure the pay for stat holidays | Closed | Colleen Gibson
2014-04-01 | Early Pay Program | Working with Amie Harvey to review and update procedure for Early Pay | Closed | Colleen Gibson
2014-04-01 | Drilling | Developing pilot program for quick pay for a drilling rig company | In progress | Colleen Gibson
2014-04-01 | ComplyWorks | Working with Support Services on ComplyWorks Internal Approval Request testing, this includes development of user guides for the internal approval requestor, Managers and VPs | Closed | Colleen Gibson
2014-04-01 | PDCNC | PDCNC - Primrose, Catering and Housekeeping Services. Executed March 31st, 2014. $4MM, 16 month term. | Closed | Lesley Dovichak
2014-04-01 | VDM RFP | Hosted VDM RFP Clarification Meeting with CampTek. Evaluation Updated with Alternative Pricing. Reviewed VDM RFP Evaluation with BU. Preparing Award Recommendation. Next action: negotiate the liquidated damages with Camp Tek. Review with BU the breakeven for Rental vs cancellation at N.Brintnell. Update April 9th: Award Recommendation signed by SM, pending BU review and signing before issuing award and regret letters. Award recommendation: Award CampTek 3 year term with monthly rental program at North Brintnell. SM signed and approved the Award Recommendation. Update April 15th: Reviewed with the BU. BU is checking about leaving Data-4 services at North Brintnell Camp. TBD. Update April 17th: Award Recommendation Update; Award CampTek Woodenhouse, Central Brintnell and Primrose. Hold pricing options (rental and 3 year term) for North Brintnell for 180 days. Remain with Data-4 services until SOW expiry Dec 31st, 2014 or until further notice. Decision pending on economic outcome of the Brintnell Field Operations. If camp remains open past 6 months, award one of the 2 CampTek Service Options. Update April 22: Award Notices issued to CampTek, Regret letters issued to remaining proponents. Held kick-off meeting to begin planning the transition and mobilization of the new VDM services | Closed | Lesley Dovichak | W - Kara W - MC M: 03 - 04
2014-04-01 | Compass Group Canada (ESS) | RFP - 3 year Contract - Estimated Value $24MM. SOW: Catering and Housekeeping Services for Brintnell and Woodenhouse Camp T&C's approved by BU. Pending Legal Approval then Commercial Ops Approval before issuing to vendor for signing. Execution of Schedules Pending, following the outcome of the service improvement plan to be implemented by ESS at the camp locations next week and roll-out of CNQ’s KPI’s. Issues: moldy food at self serve lines, kitchen staff not wearing proper PPE on serving lines, overall food quality and preparation issues, guests assigned to unclean rooms, daily reporting errors since inception of services, consistently understaffed, attempted pricing increases above awarded pricing. Action: ESS to implement a 3 week improvement plan, beginning April 7th. CNQ issuing "Notice of Default" as per service requirements outlined and awarded from the RFP. If significant improvements are not realized after the ESS plan, CNQ will exercise remedies including changing the service provider. Update April 9th: Notice of Default issued on April 9th, 2014. Update April 15th: Issued T&C's to Contractor. Update April 29th: Held an update meeting with ESS regarding their Improvement Plan. CNQ shared their ongoing concerns and issues. Provided ESS an additional 2 weeks to improve the services or CNQ will take corrective action. ESS notified CNQ that the RVP will be changing to be the same rep as the Horizon Contract. Update May 12 (Laurence): decision made for ESS to continue providing Catering and Housekeeping Services at our Brintnell Camp Locations. ESS has been notified that a maximum of 2 additional notices will be provided if disruptions continue before Canadian Natural will consider alternative options. The monthly KPI’s Audits will also be commencing in the coming weeks across all 4 camps. Quarterly reviews will be conducted with ESS on their performance and findings from of audits. T&Cs signed by both parties. Schedules in progress. Update June 24th: Schedules issued to ESS. Pending returned signed copy. | In progress | Lesley Dovichak | W-Kara W-MC: emerging issue 04 M: 03-04
2014-04-01 | Telus | Minor Construction agreement for radio tower in Lloydminster office parking lot. April 9 - Documents have been sent to Telus for review - June 2 - Document received back from Telus and forwarded to CNRL legal for review. - June 17 - Reviewed Telus concerns with BU and Legal. Scope development is under way in collaboration with Field, IS, and SM. | In progress | Stuart Kinnear | tbr
2014-04-01 | Tuboscope | MGSA negotiations. April 9 - Next meeting scheduled for April 16th. - April 22 Met with Tuboscope for further negotiations. Reached agreement on some clauses. Stuck on a few more. Have initiated discussions with management for direction on resolving remaining issues. - June 2 - Communication has been kept up with Tuboscope's legal team, and another draft of proposed changes was sent to them on the 2nd of June. This addressed all outstanding exceptions, but has not been agreed to at this time. - July 6 - Followed up with Tubo Legal to request completion. | In progress | Stuart Kinnear
2014-04-01 | Service Rig | Service Rig Stop Paying list. Working with Cassie and Colleen to finalize a top 10 list of items to remove from all service rig invoices such as PPE and Radios. Also getting total average spend for major vendors. - May 22 - Meetings scheduled with service rig vendors to discuss restructuring of rate tables. - July 9 - Meetings will be held during CAODC contract review period in October. | In progress | Stuart Kinnear | W - Kara W - MC: tbr when more advanced M: tbr
2014-04-01 | Galleon | Waiting for Galleon Well Servicing to provide CAODC contract documents - April 11 - In approval process. - May 1 - Executed | Closed | Stuart Kinnear
2014-04-02 | SFCA | UPDATE: Created 6 new SFCA's (see comments) and negotiating 3 of the 6. - The 1 contract are now pending legal approval in Upside. Pending vendor signed copy. All three complete. | Closed | Candice MacLean
2014-04-02 | SFCA | Executed 4 SFCA's (see comments) | Closed | Candice MacLean
2014-04-02 | MPSA | MPSA to put in place with robust CA clause. Worked with IS and Legal to advise Jaimie Juan on contract for Tim Ward (there will be no contract in place) | Closed | Candice MacLean
2014-07-07 | GeoFrabric | Began drafting Procurement Plan for Lease Construction Geo Fabric - Met with Construction Manager to discuss progress. Finalizing this week (May 12th). Procurement Plan has been signed by Commercial Operations. Pending BU's approval. Planning to send out RFQ on June 13th. RFQ issued June 13th. Closing on June 26th. RFQ Evaluations. Awarded on July 3rd to Nilex. Working out est. cost savings. | In progress | Candice MacLean | W -K: 06/05 M: 03
2014-04-02 | Filing System RFx | Meeting with Carlos Aular to create RFP/RFQ filing system - Meeting with Support Services on April 17th to discuss filing RFP's/RFQ's in Upside. | Closed | Candice MacLean | W kara: tbr M: 03
2014-04-02 | SFCA | Meetings with Laura Gerber to teach/transition SFCA's - on going | In progress | Candice MacLean
2014-04-02 | ComplyWorks | Working with Support Services on vendor compliance in ComplyWorks - Done. Consultants are now acceptable in CW. | Closed | Candice MacLean
2014-04-02 | CDC | Assisting Colleen with sourcing for the CDC | In progress | Cassie Doucette
2014-04-02 | Cascade Energy | Received Kara's approval for the Cascade Energy Septic Schedule (see comments) | In progress | Cassie Doucette
2014-04-02 | Service Rig | Collecting total billable hrs./rig/month for 2013 for service rigs (assisting Stuart) | In progress | Cassie Doucette
2014-04-02 | Lakeland Security | Lakeland Security MGSA and schedule have been released and are pending business area approval (see comments) | In progress | Cassie Doucette
2014-04-02 | T-Bar | 1 MGSA has been approved, signed, and is ready to be executed (see comments) | In progress | Cassie Doucette
2014-04-02 | Field Ops - Devon Operators | March 21: sent 100% offer letters to Contractors April: Collected and recorded return of executed offer letters from former Devon Operators/Admin Contractor Companies. 86/90 acceptance letters. April 2: Issued list of former Devon Contract Operating Companies to Account Payable for E1 entry April 9: Working with Laura Gerber in refining Devon Operator company information and checking clearances for Workers Compensation. Update April 22: Issued request for insurance documentation with CNRL requirements defined. Update May 5: Laura receiving insurance certificates, trained with Allan Romero for COAs. Only 4 requests for contracts have been submitted to date. Update June 5: See Laurence's e-mail please Update June 9: See email sent to Julie June 6 from Laura Gerber Update June 20: Email sent to Field Managers (June 19) with list of Devon Operators for a) Who is no longer with CQN b) When and if the rest are going to be put on contract Update June 26: 6 Operators on the list from Devon have Executed Contracts | In progress | Elaine Cantlon / Laura Gerber | W-Kara W-MC: 04/03+11 M: 03
2014-04-02 | ComplyWorks | Meeting with Terry Heck, Mark Nergaard and Bonnie Lind to discuss ComplyWorks classification for Seismic clearing and acquisition companies. Decided that all Seismic companies to be deemed high risk, Classification 1. Some companies had been listed as Classification 2 and Bonnie working with companies to change this. | Closed | Elaine Cantlon
2014-04-02 | Newalta | Filter skid negotiations for Wolf Lake with Newalta | Closed | Kevin Ross
2014-04-02 | Elk Pointe | Elk Pointe Landfill negotiations - Cost savings $180,000/year | Closed | Kevin Ross
2014-04-02 |  | Discussions on heavy oil plant waste processing opportunities and technologies w/ Justin and Production Eng. | Closed | Kevin Ross
2014-04-02 | Tervita | Tervita MGSA Executed (806972) - Estimated spend $50 Mill/year (based on 2013 spend). SOW: anything outside of Service Rigs | Closed | Kevin Ross | W-Kara W-MC 04/03 M-03
2014-04-02 |  | Looking at 'Inreach' hotspot product that runs on iridium satellite network for communications | Closed | Kevin Ross
2014-04-02 | AGAT | AGAT rate negotiations - 2 year extension on current rates | Closed | Kevin Ross
2014-04-02 | Visser | Visser contract extension or new MGSA meeting | Closed | Kevin Ross
2014-04-02 | Haz waste bin | Called EVERY field superintendent in field ops to discuss Haz waste bin solutions | Closed | Kevin Ross
2014-04-02 | ComplyWorks | Added 2 new suppliers to our vendor's list in ComplyWorks | Closed | Renato Lanfranchi
2014-04-02 | ComplyWorks | Working with Support Services on ComplyWorks testing | In progress | Renato Lanfranchi
2014-04-02 | Task Force | Meeting with Hecmy and task force team | In progress | Renato Lanfranchi
2014-04-02 | Coil Tubing RFP | Reviewed Coil Tubing RFP # 334 Commercial Evaluation with BU. Update 04/09: Reviewed Revised Commercial Evaluation with BU. - RFP #334 | In progress | Renato Lanfranchi
2014-04-02 |  | Created 3 new MGSA's (see comments) | In progress | Renato Lanfranchi
2014-04-02 |  | Created 4 new schedules (see comments) | In progress | Renato Lanfranchi
2014-04-02 |  | Created 1 new supplement to schedules (see comments) | In progress | Renato Lanfranchi
2014-04-03 | E-can | Proposed contract award to E-can for vacuum trucks being delayed due to contractor’s request for 5.5% price increase above RFP prices before contract execution. BU reviewing the decision to award to E-can at the new rate. - April 14 - Waiting for Comm Ops approval - April 19 - Contracts sent to vendors for signature. | Closed | Stuart Kinnear | W-K W-MC 04/03 M - 04
2014-04-08 | Drilling | Schedule Amendment - Halliburton Cementing | Closed | Colleen Gibson
2014-04-09 | SFCA | Discussed with several BU's (including HR) SFCA process | Closed | Candice MacLean
2014-04-09 |  | Supplier meeting to discuss Septimus (RFP) contract | Closed | Candice MacLean
2014-05-08 | Condo Units | Kickoff meeting with HR to plan and discuss condo unit Reserve Fund Study RFQ. Now drafting RFQ - RFQ complete. Met with BU on April 15 to finalize. RFQ will be issued to 3 proponents on April 17. Site Tour(s) April 23rd. RFQ closed on Monday. Review evaluation with BU on April 30th. Contract awarded to Wade Engineering on May 7th. Reviewing Wade's contract. | Closed | Candice MacLean | W-Kara: 05/12 W-MC: 04/11 M: 04
2014-06-02 |  | Created 1 MGSA and 9 Sup. For Safety RFP #335. Executed. | Closed | Candice MacLean
2014-04-09 | Ernst & Young | MPSA with Ernst Young LLC for Consulting (Audit), Total value of contract at this time is approx. $500,000 - Issued for signature to EY Update April 15: EY Legal reviewing contract for exceptions Update April 22: Reviewing EY exceptions with Julie and Kara (April 24). Update April 29: Reviewing EY exceptions with Legal and return comments to EY Update May 5: Legal reviewing. Expected returned with comments end of business May 5, to be forwarded back to EY Update May 21: EY's Legal reviewing CNRL's comments for exceptions. Expected return by May 23. Update May 27: EYs second exceptions received. Meeting with Kara and Stephanie to discuss Friday, Meeting with EY June 5th Updated June 9: Second review of EY exceptions (Julie, Stephanie, Kara). Telephone conference call with EY including EY legal planned for June 10 to discuss exceptions. June 21: Agreement with EY legal to review. Expected return Monday June 23. June 27: Agreement returned from EY with further changes. Reviewed by Legal and to be sent back with comments by end of day today. July 8: Meeting with Kara July 10 to review EY's latest comments and exceptions. This meeting will finalize the contract terms for approval. | In progress | Elaine Cantlon | W kara: tbr
2014-04-09 | Seismic | Procurement Plan for Seismic contracting - for review Update April 22: Reviewed and working on recommended changes to procurement plan. Update April 29: Julie to review Procurement Plan for signoff. Update May 5: Signed off by Kara Slemko and Business Area. Updated June 9: Exceptions for CGG handed off to Michella Pritchard to negotiate with CGG. Michella has a pressing Scope of Work to attach. Seismic acquistion scope will not be required immediately. Seismic will not be using CGG for data management going forward. | In progress | Elaine Cantlon | W-Kara
2014-04-09 | AGAT | Investigating AGAT's pricing inaccuracies for Oil and Gas Chemistry in field. Pricing for Safety Implementation and Set Up charge will be discontinued. Update April 22:Issues in the manner in which Tech overtime is charged. (GP office) Update May 5: Meeting planned for near future. Key participants are busy with Devon acquisition. | In progress | Elaine Cantlon | Savings tbr?
2014-04-09 | SiGNa Chemistry/Exploitation | Working throught exceptions for Reciprocal Confidentiality Agreement between EOR Exploitation BA and SiGNa Chemistry, Inc to start discussion regarding SiGNa's technology and application for EOR/IOR/ Update April 15 :NDA accepted and signed by SiGNa, working on getting BA approver on Upside for approvals Update April 22: BA VP delay in requesting Upside. Expected to complete to BA approver by April 23. Update April 29: BA VP reviewing with Sr. VP for approval. Approval expected by April 30. Update May 5: Fully executed. | Closed | Elaine Cantlon
2014-04-09 | AP/HR | Reviewing Q1 list of vendors with spend in BC where no WorkSafe BC account is in system, report to WorkSafe BC to be filed by HR April 11 | Closed | Elaine Cantlon
2014-04-09 |  | Training on Upside & ComplyWorks | Closed | Laura Gerber
2014-04-09 |  | Training from Elaine Cantlon on WCB clearance letters | Closed | Laura Gerber
2014-04-09 | SFCA | Executed 1 SFCA this week (see comments) | Closed | Candice MacLean
2014-04-09 | Banner Environmental | Had initial Scope of Work review meeting on Wednesday April 2nd. Banner to review T&C's and provide "fixed annual costs" and "variable costs rate sheet" by Thursday April 17th. Update April 17th: Received updated costs from Banner. | Closed | Lesley Dovichak
2014-04-09 | Data-4 | Drafted Notice of Cancellation for the Kirby Scope of Work. Waiting confirmation from the BU and IS to issue the 60 Notice. An additional notice will be sent for the remaining work (Woodenhouse, North and Central Brintnell and Primrose) after the RFP #347 Award Rec Approval by the BU and discussions with the award proponent on an implementation timeline. Update April 10th: Notice of Cancellation - Kirby Camp issued Thursday April 10th. Update April 22nd: Issued notice of cancellation, for Woodenhouse, Central Brintnell and Primrose camps. North Brintnell services continue as is. | Closed | Lesley Dovichak
2014-04-09 | Camp KPI's | Reviewed KPI Audit with BU and Compliance Officer; monthly audits to be executed by the Compliance Officer. To be reviewed and agreed upon with the Contractor (beginning with ESS Camps, will rollout to remaining camps thereafter). Roll-out audit program in May. Update April 29th: Due to changes in the ESS management, review of the KPI's will be delayed until the new team has fully transitioned into their rolls. Udpate June 24th: KPI Audit Overview meeting and Q2 review scheduled for June 27th with ESS, BU and SM. | In progress | Lesley Dovichak | W: tbr M 04
2014-04-09 | Tidy Trucking | Supplier meeting to discuss Septimus (RFP) contract - Tidy Trucking / Fluid Hauling | Closed | Renato Lanfranchi
2014-04-09 | HSE Integrated | Suppliers meeting to discuss Safety Services contracts - HSE Integrated | Closed | Renato Lanfranchi
2014-04-09 | NWFR | Suppliers meeting to discuss Safety Services contracts - NWFR | Closed | Renato Lanfranchi
2014-04-09 | Accede | meeting with Accede to discuss their services - Equipment Rentals | Closed | Renato Lanfranchi
2014-04-09 | TTS | Executed 1 new MGSA & Schedules - TTS / Milling Services | Closed | Renato Lanfranchi
2014-04-09 | Firemaster | Executed 1 new Schedules - Firemaster / Safety Services, Septimus | Closed | Renato Lanfranchi
2014-04-09 | Firemaster | Executed 1 new Supplement - Firemaster / Safety Services | Closed | Renato Lanfranchi
2014-04-09 | Tidy Trucking | Executed 1 new Supplement - Tidy Trucking / Fluid Hauling | Closed | Renato Lanfranchi
2014-04-09 | FMC | Created 1 new supplement to schedules (see comments) | In progress | Renato Lanfranchi
2014-04-09 | Vertex | meeting with Vertex to discuss their services - Safety Services and SCVF&GM | Closed | Renato Lanfranchi / Candice maclean
2014-04-14 | CDC | Continuing to assist Colleen with equipment procurement | In progress | Cassie Doucette
2014-04-14 | ALE Roll Lift | Received BA approval. Contract to be issued for signature this week following Kara's approval July 8 - Still discussing issues with Transportation and Logistics to understand Canadian Natural's stance on exceptions provided by ALE. | In progress | Cassie Doucette
2014-04-14 | Lakeland Security | Received BA approval. Contract to be issued for signature this week following Kara's approval | In progress | Cassie Doucette
2014-04-14 | Supply Management | Working with Justin to develop a spend dashboard to act as a tool for Thermal business unit. | Closed | Stuart Kinnear
2014-04-15 | Field Ops | Negotiated and contracted Newalta waste treatment pilot project in Heavy Oil. w/ Justin (see their reporting for cost savings and contract values) | Closed | Kevin Ross
2014-04-15 | Field Ops | Met with SLC to discuss potential waste treatment technologies, going to test samples. w/ Justin | In progress | Kevin Ross
2014-04-15 | Ops, Enviro, Drilling | Changed from 2.3m3 bins to 23m3 bins (save $75,000 this year) | Closed | Kevin Ross
2014-04-15 | Horizon | Cancelled engineering plans for Landfill - Savings $200,000 | Closed | Kevin Ross
2014-04-15 | All | Ran RA sandbox for BU and IS | Closed | Kevin Ross
2014-04-15 | All | Dealing with Skybase to further develop a distance matrix for CNRL | Closed | Kevin Ross
2014-04-15 | SFCA | Starting 2 new SFCA's | Closed | Candice MacLean
2014-04-15 |  | Created 3 new schedules (see comments) | In progress | Renato Lanfranchi
2014-04-15 |  | Created 2 new supplements to schedules (see comments) | In progress | Renato Lanfranchi
2014-04-15 |  | Supplier meeting to discuss Elaine RFP results - Baker Hughes | Closed | Renato Lanfranchi
2014-04-15 |  | $163 K during March in asset reutilization ($608K YTD) - GE conventional wellheads | Closed | Renato Lanfranchi
2014-04-16 | Corporate Services | Starting RFP for Bonnyville General Contractor - approved by MC via Bonnyville Office Renovation Budget Bonnyville General Contractor - Bids are currently being evaluated, extended award date to June 6. Award made to Synergy Projects Ltd. for an amount of $323,635.00 (lowest bid). | Closed | Colleen Gibson
2014-04-23 | Camps/Waste | Met with Remote Waste LP to discuss potential waste solutions for biohaz waste on Camps - W/ Lesley | Closed | Kevin Ross
2014-04-23 | Enviro/Waste/Ops | CNRL acquired 31.2% stake and operating authority from Devon in a JV for Swan Hills Class II landfill. Landfill requires new runoff pond as per Directive 58 guidelines. Project supposed to commence June 2014 and be completed for June 2015. CNRL will apply for extension on this project while we decide on what to do with the landfill as a whole. | Closed | Kevin Ross | M-04
2014-04-23 | Enviro/Waste/Ops | Created a detailed monthly KPI bin tracker for Haz waste bins | Closed | Kevin Ross
2014-04-23 | All | Continuing to Demo RA softwares | Closed | Kevin Ross
2014-04-25 | Corporate Services | Reviewing Contract Renewal Terms for Loomis | Closed | Colleen Gibson
2014-04-01 | Early Pay Program | Working with Drillers Directional to join Early Pay Program | Closed | Colleen Gibson
2014-04-01 | Early Pay Program | Working with Razor Vac to join Early Pay Program | Closed | Colleen Gibson
2014-04-01 | Early Pay Program | Working with Automated Tank to join Early Pay Program | Closed | Colleen Gibson
2014-04-24 | C&T Catering / Field Ops / Chinchaga Camp Caterer, Manning | Discussed Field Service Agreement for a new operations camp caterer with Ken Miller the Field Ops Team. Provided suggestions for updating the FSA with additional catering and housekeeping scope of work details. Sent to the foreman for review. Making updates and sending a final copy to them for execution. | Closed | Lesley Dovichak
2014-04-29 | Norken Security | Updated May 5: MGSA draft of Schedules A&B with Mike for review Update May 21: Agreement requested by and with Julie Easthope for review. Update May 27: Nothing to update. | In progress | Elaine Cantlon
2014-04-29 | CGG Services (Canada) Inc. exceptions | Update May 5: Reviewing exceptions to MGSA. BA also reviewing exceptions which involves a business decision. Update May 21: BA returned comments to CGG exceptions. Update May 27: Nothing to update. Update June 9: MGSA comments passed on to Michella Pritchard July 9: CGG contract returned to myself for issue. CGG will not be considered for Horizon work. | In progress | Elaine Cantlon
2014-04-25 | Field Operations | Procurement plan for Service Rig Commitment Pricing is with Julie for review and feedback. May 9 - On hold until pricing negotiations have completed. May 22 - PP is being re-structured to include a pilot project to reduce the risk to Canadian Natural and to ensure that a large scale roll out will not affect production operations. June 25 - PP Reviewed by Cam Kinniburgh. Booked meeting with Mike Catley for review on July 14th. | In progress | Stuart Kinnear
2014-04-29 | SFCA | Executed 4 SFCA's (see comments) | Closed | Candice MacLean
2014-05-05 | Precision Well Servicing | New Pricing proposed. Analysis presented to Business Unit for discussion. May 12 - Met with Precision and Business Unit. May 16 - Letter sent to Precision Well Servicing outlining why Canadian Natural will not accept new pricing. Have had no response from Precision after dropping three of their rigs and the letter. June 01 - New Pricing from Precision is in place. In the process of determining next steps with the Field Ops Managers. A letter has been drafted explaing CNRL's actions, but has not been sent. June 13 - Rate Increase Response Letter sent to Precision by Field Operations requesting detailed breakdown of the proposed rate increase June 20 - Received Detailed breakdown from Precision Sales Rep. July 7 - Meeting to discuss breakdown rescheduled for July 21st. | In progress | Stuart Kinnear | W-K: 05/12 + 06/05 W-MC: y M: tbr when more info
2014-05-05 | Document Records Management - Well Files Scanning | Update May 5: RFP for Scanning Wellfiles. Met with BA May 1, draft RFP and D&B reports for 6 proponents to be reviewed May 7 Update May 21: RFP #426 issued to 8 proponents May 14. All proponents have accepted. Site Tours have been scheduled between May 21 and 23. BA have been charged with deciding on Technical Evaluation criteria for meeting booked for May 27. Update May 27: Clarification #2 sent Friday. Site tours completed. Clarification #3 to be issued today. Update June 9: Proposals received June 3rd. Opened June 6. Technical component distributed to BA for evaluation. June 21: Evaluation near completion. Prelimiary meeting with Business AreaJune 18. Further clarifications and evaluations followed up by additional meeting June 20 or 23. June 27: LOR signed by Steve Suche and Ron Laing. Award made to TAB, Products of Canada, Co. and regret letters issued to other proponents. Meetings for work on Scope Development Plan with TAB to be set up for week of July 7th. Estimated value 2.3MM+ (Work Developement plan will need to be completed to report on savings). July 9: Met with TAB Canada July 8 to develop Work Plan with BU. Overall planning addressed, including tour of well file locations. TAB and BU will continue with technical meetings for complete SOW for week of July 21. Plan to have approvals for issue July 25 or sooner. | In progress | Elaine Cantlon | W-K: 05/12 + 06/05 W-MC: 06/30 M: 04
2014-05-06 | CNC Heart Lake Catering JV / Camps and Stakeholder Relations / Kirby North Camp | Discussion with Camps and Stakeholder relations about proposing catering and housekeeping services to the Heart Lake and CNC JV for the new Kirby North Operations Camp. Supply Management will review existing PDCNC agreement and draft a similar proposal to review with Camps to propose to the CNC Heart Lake JV. Update May 27th: Meeting schedule on Monday June 2nd to review requirements etc with Stakeholder relations and define a go-forward plan for Kirby North new service provider and renewing Kirby South. Update June 9th: Kirby North - Catering & Housekeeping services will be Bid excluding CNC participation. Wording will be included in the bid that the awarded contractor will be expected to work with Heart Lake first nations. Bid expected to be issued by Friday June 20th. Services to being Sept 1st. Kirby South - PDCNC Catering and Housekeeping SOW will be extended for 1 year. | Closed | Lesley Dovichak | W-MC: 05/06
2014-05-08 | SFCA | Executed AMEC schedule | Closed | Candice MacLean
2014-05-08 | Completions | Reviewed 2 wellheads lists from Devon with GE and Materials Management. Total of 20 items that are currently with Streamflo and FMC will be transferred to GE. The total value for these assets is $34,186.25 ($29,325.00 from FMC and $4,861.25 from Streamflo). | In progress | Renato Lanfranchi | W-K:05/12 W-MC: 05/13 M:04
2014-05-08 | Completions | Met with Precision Well Service and Business Unit to discuss Snubbing and Coil Tubing Services for Septimus project. Reviewed lessons learned from 5 wells completed on Pad 9.21. | closed | Renato Lanfranchi
2014-05-08 | Completions | $79 K during April in asset reutilization ($687K YTD) - GE conventional wellheads | closed | Renato Lanfranchi
2014-05-05 | CampTek | Update May 5: Calculated changes to the WIFI and Ethernet costs based on no minimum and completed an evaluation of pricing implications if CNQ agreed to an increase in the monthly WIFI and Ethernet fee instead. Camps to discuss this and Cancellation costs with vendor while I am away May 9 -23. Update May 27th: Camp Group and CAMPtek confirmed cancellation calculation etc. Update June 17: meeting with camps, IS and SM to review the implementation. Updated June 24th: Meeting with BU, IS and CAMPtek scheduled for June 25th to finalize Woodenhouse VDM services. Pending outcome, CAMPtek will review and agreement and if updates are required. | In progress | Lesley Dovichak
2014-05-12 |  | Field visit on May 13th. Meeting with Heart Lake Construction in Kirby | Closed | Candice MacLean
2014-05-12 |  | Field visit - Tervita Big Valley (purchasing onsite centrifuge system) - SLC Black Falds (seeing if pyrolysis will treat our slop oil) | Closed | Kevin Ross | Y see justin/javier's
2014-05-12 | E-Procurement Software | Ran Demo Day for eprocurement solutions - shortlisting to two SAAS providers Update May 26: Shortlisted to two eprocurement SAAS systems - Running tests for next three weeks | In progress | Kevin Ross
2014-05-12 | Abudata | Trying ABUDATA to see if it will map Haz bins | In progress | Kevin Ross
2014-05-12 | CanAm | CANAM and survey rate analysis | Closed | Kevin Ross
2014-05-12 | Tervita | Tervita invoicing issues | Closed | Kevin Ross
2014-05-13 | KMC Oilfield Maintenance | MGSA for Slave Lake Production Services executed | Closed | Stuart Kinnear
2014-05-19 | Safety Initiative | Meetings HS & Env & BU with 20 vendors with the highest TRIF to improve safety awareness and reduce TRIF and spills. Deadline for meeting: June 30 Update June 5: 13/20 meetings scheduled - Update June 10: 17/20 meetings scheduled. Update June 17: 19/20 meetings scheduled (DLM Oilfield -ex leeway- remaining) Update June 23: 20/20 meetings schedules | In progress | Laurence Dubuc
2014-05-22 | Supply Management | Developing Dashboard for Service Rig Performance Data using Tableau 8.1. July 9 - Dashboard ready for review with Field Operations Leadership. | In progress | Stuart Kinnear
2014-05-26 | Materials Management | New pricing proposed by Guardian Inspections. Comparing current vendors to new pricing to determine best course of action going forward regarding where CNRL is getting it's downhole tubing inspected and repaired. | In progress | Stuart Kinnear
2014-05-26 | CANAM | CANAM Rate Negotiations. Update June 3: Negotiated Survey rates with one of our largest providers $1,285,000 savings per year achieved. | Closed | Kevin Ross | W-MC: 06/10
2014-05-26 | Meridian | Meridian Rate Negotiations | Closed | Kevin Ross
2014-05-26 | SLC | SLC by product sent to lab for analysis | Closed | Kevin Ross
2014-05-26 | AGAT | Met with AGAT to discuss new lab opening. Potentially a class II landfill | Closed | Kevin Ross
2014-05-26 | Trace Associates | Trace Associates Negotiations (fees down, disbursements down, volume discount) save ~ $70k/year | Closed | Kevin Ross | Y
2014-05-26 | SFCAs | Terralogix Negotiations (fees down, disbursements down) Save $18k/year | Closed | Kevin Ross | Y
2014-05-26 | Drilling | Developing Extension Amendment for Schlumberger Drill Bit Contract | In progress | Colleen Gibson
2014-05-26 | Drilling | Developing Extension Amendment for Gmack Drill Bit Contract | Closed | Colleen Gibson
2014-05-26 | Drilling | Developing Extension Amendment for J&L Supply Drill Bit Contract | Closed | Colleen Gibson
2014-05-26 | Drilling | Developing Extension Amendment for Halliburton Drill Bit Contract | Closed | Colleen Gibson
2014-05-26 | Drilling | Developing Amendment for Legal Name change for Marquis Alliance Contract to Secure Energy (Drilling Services) | Closed | Colleen Gibson
2014-05-26 | Drilling | Developing Amendment for Legal Name change for RigManager Contract to Stream Services | Closed | Colleen Gibson
2014-05-26 | Drilling | Developing MGSA for Black Knight Energy Services (Drill Bits) | In progress | Colleen Gibson
2014-05-27 | Black Opal | Sent draft of Field Service Agreement to Camp Group for review for trial Environmental Services (water & wate water treatment) at the Woodenhouse camp in replacement of Banner Environmental. If services and costs are satisfactory, will reevaluate adding other camp locations and executing an MGSA. Update June 2: FSA Draft Complete. Will issue once vendor confirms available start date. Update June 24th:FSA executed by BU. In place for 1 year. If BU is satisfied with work, SM and BU will re-evaluate and execute an MGSA. | Closed | Lesley Dovichak | W-K: to be reported when more information w/estimated spend & savings
2014-06-02 | SFCA | Executed SFCA's | Closed | Candice MacLean
2014-06-03 | Sequoia | Added a new preffered helicopter supplier | Closed | Kevin Ross
2014-06-03 | Meridian & Vertex | Rate negotiations | Closed | Kevin Ross
2014-06-03 | Owl Moon | New avian monitoring program in Horizon | In progress | Kevin Ross
2014-06-04 | Tervita & RBW | Field visit - process audit of our two largest Haz bin suppliers | Closed | Kevin Ross
2014-06-03 | CH2M Hill | Dealing with CH2M's acquisition of Tera. | In progress | Kevin Ross
2014-05-28 | Supply Management | Kickoff meeting with SM team to review the RFQ template (Lesley, Elaine, Joel) | In progress | Colleen Gibson
2014-05-30 | SFCA reporting | Ron L. checking the 2014 request forms for the SFCAs. 165 Request Forms pullled out for Ron's review by May 30. Agreement not to change the current process. Update June 5: Mary-Jo and Ron wants the reporting to be changed. Deadline to provide the packages: June 6 | In progress | Laurence Dubuc
2014-06-02 | Early Pay Program | Working with Clayton Construction to join Early Pay Program (working with Candice) | Closed | Colleen Gibson
2014-06-03 | Drilling | Kickoff meeting with PD to review the CAODC contract and special conditions (the document template requires an update to ensure it is aligned with current business practices) | In progress | Colleen Gibson
2014-06-09 | Corporate Services | Developing MGSA for Synergy Projects Ltd. (Bonnyville General Contractor) | In progress | Colleen Gibson
2014-05-26 | Drilling | Developing Extension Amendment for Stream Services Communications Contract | Closed | Colleen Gibson
2014-06-09 | Camps / Kirby North Rfx Catering & Houskeeping Services (Heart Lake?) | Forwarded RFx participant list to Julie to send to Ron Laing and Bill Clapperton for review Drafting the RFx with the BU. Plan to issue the document by Friday June 20th. Update June 24th: Pending conversation with Bill Clapperton and Heart Lake before SM can issue the RFQ. Update June 27th: RFQ will be issued Monday June 30th. June 30: on hold until meeting on July 3rd with BU, Marjor Projects Kirby North, SM and Stakeholder to determine go-forward plan for all the Kirby Camps. | In progress | Lesley Dovichak
2014-09-06 | Maxxam Analytics International Inc. | Business Review meeting held with Maxxam Analytics on June 2. CNQ Measurement Specialist Jonathon Wasylik, Eirenne Rawson and Natalie Liang (Financial Accts and Controls - Protrend Admin, Derek Fraser (Maxxam) and Michael Gordon (Maxxam) attended. Maxxam presented Business review of 1st quarter of business and rebate cheque for year 2013 ($85,958.18).Marked improvement with business process and any problems identified in October 2012. Next meeting will be scheduled for Fall 2014. | Closed | Elaine Cantlon
2014-09-06 | Glori Energy Inc. | Received MGSA exceptions from Glori Energy Inc. who will be working with CNQ on a pilot of Microbial Enhanced Oil Recovery on CNRL's pools. Business area is Exploitation Central. June 27: BU concerned about getting to far in agreement with Glori before sampling to establish further busines is done. Glori to submit insurances and be escorted to field to obtain samples. Success of sample testing will determine going to agreement with Glori. | in Progress | Elaine Cantlon
2014-09-06 | Tervita & RBW | Field visit/environmental audit to see the processes of two Haz material vendors | Closed | Kevin Ross
2014-09-06 | Stantec | Having Stantec provide background infromation regarding professional delegation levels of it's employees and the applicable compensation | in Progress | Kevin Ross
2014-09-06 | Frontline/Secure | Added to Frontline's Decom scope for 2014 | Closed | Kevin Ross
2014-06-09 | Completions | $65.7 K during May in asset reutilization ($752K YTD) - GE conventional wellheads | closed | Renato Lanfranchi
2014-06-10 | SFCA | Executed 2 SFCA's | Closed | Candice MacLean
2014-06-10 | Bailey Helicopters | Meeting with Bailey Helicopters to discuss contract - pending discussion with BU (Bill Muss) next week | In progress | Candice MacLean
2014-06-10 | SFCA | Produced SFCA report for MC. Meeting on Friday, June 20th to discuss. | Closed | Candice MacLean
2014-06-20 | Early Pay Program | Early Pay negotiations with Lease Construction vendor - Signed up. Contract executed | Closed | Candice MacLean
2014-06-10 | Firemaster | Meeting with FireMaster to discuss safety services at Septimus | Closed | Candice Maclean / Renato Lanfranchi
2014-06-18 | Eagle Well Servicing | Met with Eagle Well Servicing to discuss: -Line Items on Invoices and Creating Budled Pricing -Possible fuel increase/allowance -Changing discount that is currently in place from a line item to a quarterly rebate -Eagle was concerned that they dropped their rates for CNRL and did not see any change in work volume. Next Meeting scheduled for June 27, 2014 | In progress | Stuart Kinnear
2014-07-07 | Regulatory | Update June 23 (Laurence): Issued RFP #443 - Enviro. Assessment - Candice is covering for Kevin until July 1. Environmental baseline survey work is to begin in summer 2014 to support submission of the regulatory Application to the Alberta Energy Regulator (AER) by June 15, 2015. 3 proponents: Millenium, Matrix, Stantec. Closing date July 14 Update June 20 (Candice): Issued RFP No. 443 on June 20th - Enviro. Assessment for Kevin Ross. Passed on to Kevin Ross; however, still acting as the sole point of contact. | In progress | Candice MacLean
2014-06-20 | Drilling | Developing Extension Amendment for Pason (Communications Contract) | In progress | Colleen Gibson
21/06/2014 | RPS Energy Inc. | MPSA for wellsite geology. Contract exceptions reviewed and completed for agreed terms. Delay in issue to week of June 30 MPSA issued for approval and issue for July 10. | In Progress | Elaine Cantlon
2014-06-20 | Drilling | Developing Procurement Plan for Emergency Services | In progress | Colleen Gibson
2014-06-20 | SFCA | Executed 2 SFCA's | Closed | Candice MacLean
2014-06-20 | Early Pay | Working on vendor list for potentials for early pay program (Lease Consturction) | In progress | Candice MacLean
2014-06-23 | Data-4 / Camps / VDM | Issued notice of transition dates to Data-4 for Primrose and Central Brintnell. Woodenhouse transition dates are TBD. | In progress | Lesley Dovichak
2014-06-24 | PDCNC / Camps / Kirby South and Primrose | Issuing RFI to PD for information their Catering & houskeeeping services pending conversation btwn Steve Lepp and James Blackman from PD. Update June 27th: On hold until we hear more about the status of the PDCNC JV. | In progress | Lesley Dovichak
2014-06-24 | ATCO / Camps & Stakeholder/ Kirby North | Began drafting supplement to ATCO Maintenance MGSA to include the new Kirby North Camp. ATCO will sub-contract the aborigional group CNQ designates. Conversation with Stakeholder, Camps and SM to determine if a specific group should be identified; Heart Lake? | In progress | Lesley Dovichak
2014-06-24 | ATCO / South Brintnell Ops Camp / Kirby North | Evaluting if Luke Vondermuhl wants to explore asking ATCO to provide plant maintenance at the South Brintnell Plant. Luke V, Randy P and Erik H will discuss. Concerns are with CNQ having to pay for PPE, H2S etc. SM provided wording from Camp Maintenance SOW that Contractor supplies all personnel PPE. Sch G stipulates Contractor to provide all necessary training for the SOW, including H2S Alive/h2S awareness component only. TBD...waiting feedback from BU. | In progress | Lesley Dovichak
2014-06-24 | Temp Camp / Facilities and Pipelines / Primrose | Cody Klatt requires a temp camp as there is no sapce this fall/winter at the Primrose camp; 70 rooms, 14 VIP and 56 Craft from Mid November - March possibly into April. Cody was obtaining a quote from Camp Corp Structures. SM advised management direction not to use CNC or any subsidary business. SM offered assistance to helping source alternative providers and forwardeda price list from Precision Drilling. Pending acknowledgement and request back from BU. | In progress | Lesley Dovichak
2014-06-25 | Supply Management | Currently working on 20 SFCAs | In progress | Laura Gerber
2014-06-25 | Supply Management | Currently working on 19 COAs | In progress | Laura Gerber
2014-06-27 | Drilling | Developing Procurement Plan for Coring Services (with Elaine) | In progress | Colleen Gibson
2014-06-27 | Drilling | Developing Extension Amendment for Pe Ben (Transportation Contract) | In progress | Colleen Gibson
2014-06-27 | Drilling | Developing MGSA for Halliburton (all services) | In progress | Colleen Gibson
2014-06-27 | Drilling | Developing Procurement Plan for Strat Rig Services | In progress | Colleen Gibson
2014-06-27 | CBO | Met with outside counsel regarding CBO agreement. Hoping to issue revised Ts & Cs next week. Meeting with outside counsel and Jerry Harvey on July 16th to finalize contract Ts&Cs | In progress | Candice MacLean
27/06/2014 | Wintershall Holding GmbH | June 27:Winterhall's exceptions to Reciprocal Confidentiality Agreement received, reviewed by Legal and returned to Wintershall for comment/acceptance June 26. July 9: Wintershall returned NDA with additional exceptions. Legal reviewed and requested BU agreement before returning for final acceptance by Wintershall. | In Progress | Elaine Cantlon
27/06/2014 | Procurement Plan - Coring and Logging | Working with Colleen Gibson on Procurement Plan for Coring in preparation for RFP. Met with Cory Hanger, Drilling for background for vendors and business for last 5 years. Will be meeting with Thermal Geology (SAGD, CCS) who use same vendors as Drilling. July 9: Met with Thermal Geology. Both Managers in agreement with procurement plan and plan to send out RFP for the services. Will complete Procurment Plan for sign off. | In Progress | Elaine Cantlon
2014-07-07 | Enviro Projects | Working with Candice on an RFP (which she did/is doing a great job covering for me!) | In progress | Kevin Ross
2014-07-07 | Vertex | Finalized Rate negotiations (Savings of $403,000 per year) | Closed | Kevin Ross | Y
2014-07-07 | Sequoia | Onboarded new helicopter company | Closed | Kevin Ross
2014-07-07 | Horizon | Changing waste companiess for Horizon projects/ops | In progress | Kevin Ross
2014-07-07 | SFCA | Completed 1 SFCA | Closed | Candice MacLean
2014-07-08 | Suncor | Began process of crosstraining on the Suncor fuels contract with Dale Palmer. Currently reading and gaining context on the contract. Deliverables for the end of 2014 have been discussed and preliminary list has been sent to Julie, Laurence and Hamilton for review. | In progress | Stuart Kinnear
2014-07-08 | Supply Management | Met with the Tableau Analytics Business Steering Committee to identify potential data sources and reporting capabilities made possible using Tableau Software. Next step is to work with Damian Jordan to gain access to the currently available analytics data for use in contract administration. | In progress | Stuart Kinnear
2014-07-09 | Supply Management | Working with Support Services to begin understanding the reporting requirements of Supply Management. This is as a part of the process of increasing the reporting quality, and data integrity. | In progress | Stuart Kinnear
2014-09-07 | Workers Compensation | July 9: Reviewed Worksafe BC list of vendors requiring coverage for Q1-Q2. 3 AB water/liquid haulers working for Drilling operations in BC but no Worksafe BC. Spend and time in BC requiresWorksafe BC registration. Discussed with Drilling superintendent. Will submit list for CNRL Worksafe BC list Q2 to AP/HR July 10. | In Progress | Elaine Cantlon
2014-09-07 | NDA | Issue Reciprocal Confidentiality Agmt to HTC02 Systems. BU to provide details for "purpose" . Issue July 10.
2014-07-02 | Completions | Created 4 new MGSA's (see comments) | In progress | Renato Lanfranchi
2014-07-02 | Completions | Completed Coil Tubing RFP 334 | closed | Renato Lanfranchi
Note on C30: Candice MacLean: Brad Ferguson Raimund Honsek Ron Hamm Piotr Kukialks Orest kotelko David Thomson
Note on C31: Candice MacLean: Mike Weisbrod Russ Bacon Patrick McLellan Keith Hirsche
Note on C38: Cassie Doucette: Contract: 810221-2 Value: $2,000,000.00 Sent to vendor for signature
Note on C40: Cassie Doucette: Contract: 810929 & 810929-1 Value: $500,000.00
Note on C41: Cassie Doucette: Contract: 810556, -1, & -2. Value -1: $1,200,000.00 Value -2: $800,000.00
Note on C56: Renato Lanfranchi: TTS - 810948 NWFR - 811079 Wespro - 810845
Note on C57: Renato Lanfranchi: TTS - 810948-1 NWFR - 811079-1 Wespro - 810845-1 Firemaster - 808022-2
Note on C58: Renato Lanfranchi: Firemaster - 808022-1 sup #1
Note on C72: Candice MacLean: David Thomson
Note on C80: Renato Lanfranchi: TTS - 810948 NWFR - 811079 Wespro - 810845
Note on C81: Renato Lanfranchi: TTS - 810948 NWFR - 811079 Wespro - 810845
Note on C82: Renato Lanfranchi: TTS - 810948 NWFR - 811079 Wespro - 810845
Note on C83: Renato Lanfranchi: TTS - 810948 NWFR - 811079 Wespro - 810845
Note on C84: Renato Lanfranchi: FMC Thechnologies #806567-1 Production testing Services, Septimus
Note on C97: Renato Lanfranchi: Haltec - 810560-1 Dawson - 810547-1 FMC - 806567-2
Note on C98: Renato Lanfranchi: Voltage 805590-1 sup #1 TC Mobile 805591-1 sup #1
Note on C114: Candice MacLean: Orest, Chantal, Wayne,Terry
Note on C147: Candice MacLean: Ron H Raimund H Stephanie C
Note on C203: Renato Lanfranchi: Leader - 811876 Canyon - 811879 wise - 811871 essential - 811880
Note on C204: Renato Lanfranchi: Leader - 811876 Canyon - 811879 wise - 811871 essential - 811880

## Highlights
Date | Vendor / BU / Area | Task Details | SMA/SMP | Reported?
2014-04-09 | ESS / Camps / Brintnell Camps | Issued formal Notice of Default to ESS with a cure date of April 29th, 2014. | Lesley Dovichak
2014-04-09 | VDM RFP #347 / Camps / Woodenhouse, Brintnell, Primrose | • Supply Management Award Recommendation: CampTek • Award notice to be issued by Friday April 11th; pending BU sign-off on Award Recommendation • Implementation 8 – 10 weeks • Total estimated savings; $5.6 MM • Proposal Summary – 3 Year Term with a 6-month rental agreement for North Brintnell Camp Proponent Total Cost Savings Savings % Data-4 (current provider) $6,909,165.00 CampTek $1,292,236.40 $5,616,928.60 81% 3CIS & Shaw $2,370,499.00 $4,538,666.00 66% TELUS & Switch $3,898,656.00 $3,010,509.00 44% | Lesley Dovichak
2014-04-17 | VDM RFP #347 / Camps / Woodenhouse, Brintnell, Primrose | UPDATE: VDM AWARD RECOMMENDATION Award CampTek Woodenhouse, Central Brintnell and Primrose on 3 year term. Life expectancy of NB camp unknown pending uncertain economic conditions. Maintain Data-4 services at North Brintnell as they provide the lowest monthly cost. Data-4 contract expires Dec 31, 2014. CampTek holding NB pricing options for 180 days if NB remains open past 6 months. CampTek NB options: 1. 3 year term; cancellation fee after 6 months; ~$389k - $160k; 2. Monthly rental $28k; $7K/month more than monthly Data-4 costs. Proponent Total Cost Savings Savings % Data-4 (current provider) $6,909,165.00 CampTek $1,292,236.40 $5,616,928.60 81% Camp Tek w/ Data-4 $1,250,231.90 $5,658,933.10 82% | Lesley Dovichak
2014-04-10 | Data-4 / Camp / Kirby Camp | Notice of Cancellation issued for Kirby Camp SOW. Cancellation notice for remaining camps will be issued once award letters from VDM RFP #347 are issued and implementation of new services confirmed. | Lesley Dovichak
2014-04-22 | Early Pay Program | Recognized Savings of $320,280.00 through the Early Pay Program in Q1 with 9 Vendors | Colleen Gibson
2014-04-17 | VDM RFP #347 / Camps / Woodenhouse, Brintnell, Primrose | Award notice issued to CAMPtek. Regret letters issued to remaining proponents; TELUS, Switch Inc, 3CIS and Shaw. | Lesley Dovichak
2014-04-22 | Data-4 / Camp / Woodenhouse, Central Brintnell and Primrose Camps | Notice of Cancellation issued for Woodenhouse, Central Brintnell and Primrose SOW. North Brintnell services remain as is until further decision about the camps longevity is determined. | Lesley Dovichak
2014-04-24 | ESS / Camps / Brintnell Camps | Held meeting to discuss ESS 3 week Improvement Plan Progress. CNQ expressed on-going concerns regarding the legibility and accuracy of reports and slight improvements in catering services. improvements seen in one area drop when focus is shifted to another. ESS will be provided an additional 2 weeks to improve all the services or CNQ will explore alternative service providers. ESS contract management team will be making a transition to new representatives. | Lesley Dovichak
2014-04-28 | ESS / Camps / Brintnell Camps | ESS made a change to the Brintnell Regional Vice President to the same RVP as Horizon. SM met with the new RVP and ESS President to discuss remaining improvements needed and their commitment to improve the situation and salvage the working relationship. ESS has deployed additional resources to the site and are working to resolve remaining issues. | Lesley Dovichak
2014-05-01 | Drilling | As of end of Q1, 95% of Cementing spend since contract effective date of September 1, 2014 is with the 5 preferred vendors | Colleen Gibson
2014-05-01 | Drilling | As of end of Q1, 99% of Directional Drilling spend since contract effective date of September 1, 2014 is with the 5 preferred vendors | Colleen Gibson
2014-05-01 | Drilling | As of end of Q1, 85% of Drilling Bit spend since contract effective date of July 1, 2012 is with the 6 preferred vendors | Colleen Gibson
2014-05-01 | Drilling | As of end of Q1, 98% of Drilling Fluids spend since contract effective date of September 1, 2014 is with the 4 preferred vendors | Colleen Gibson
2014-05-01 | All | SNF - 2012 negotiated freight prices (Gary Dahl) measured $3.2M in cost avaoidance in 2013. The savings are based on having the Supplier match known Flat car rates. Negotiation conduced by G. Dahl in 2012. | Dale Palmer
2014-05-01 | All | Univar quaterly rebate received -$ 77327.31 with $44K to follow for Methanol rebate. | Dale Palmer
2014-05-01 | Brintnell | SNF - offered CNRL a volume discount of 5% for Polymer product (1.8% total value) if contract was extended for 5 yrs. Business plan in circulation reciommneding issuing an RFP for Polymer at Brintell. | Cam Woo/ Dale Palmer
2014-05-06 | CNC Heart Lake Catering JV / Camps and Stakeholder Relations / Kirby North Camp | Discussion with Camps and Stakeholder relations about proposing catering and housekeeping services to the Heart Lake and CNC JV for the new Kirby North Operations Camp. Action: Supply Management will review existing PDCNC agreement and draft a similar proposal to review with Camps to propose to the CNC Heart Lake JV. Update May 27th: Camps, Stakeholder Relations and SM to review go-forward plan on Monday June 2nd for Kirby North and disucss extending the existing term for PDCNC at Kirby South Camp. Update June 9th: Kirby North - Catering & Housekeeping services will be Bid excluding CNC participation. Wording will be included in the bid that the awarded contractor will be expected to work with Heart Lake first nations. Bid expected to be issued by Friday June 20th. Services to being Sept 1st. Kirby South - PDCNC Catering and Housekeeping SOW will be extended for 1 year. | Lesley Dovichak
2014-05-26 | All | Shortlisted to two eprocurement SAAS systems - Running tests for next three weeks | Kevin Ross
2014-06-09 | ESS / Camps / Brintnell Camps | Significant service improvements have been made. Schedules are being finalized with ESS. | Lesley Dovichak
2014-06-27 | PDCNC / Camps / Kirby South and Primrose Camps | Decision pending on next steps once we know more about the status if the PDCNC JV. | Lesley Dovichak
2014-06-27 | Kirby North RFQ / Camps | Issuing RFQ Monday June 30th | Lesley Dovichak