## SRM
Canadian Natural and Quinn Contracting Dashboard
MGSA # 810354-1 - Supplement 3
Q1 2018
Review held on March 22, 2018
Safety
Leading Indicator | 2015 | 2016 | 2017 | Jan 2018 | Feb 2018 | Key Notes - Leading
Man-Hours | 231066 | 210544 | 214425 | 18795 | 17500 | - Work being done to fully transition to metal-based scaffolding parts (currently at 95%) - Other??
Hazard ID's | 843 | 935 | 1267 | 109 | 85
Safety Meetings | 15 | 15 | 18 | 1 | 2
Work Site Inspections | 289 | 265 | 336 | 63 | 45
Pre-Task Analysis Cards | 7770 | 6373 | 5982 | 439 | 400
Pre-job Toolbox Meetings | 1828 | 1606 | 1829 | 178 | 150
BBSO | 2243 | 1946 | 2033 | 260 | 200
Near Hit/Near miss | 2 | 16 | 6 | 1 | 0
Lagging Indicator | 2015 | 2016 | 2017 | Jan 2018 | Feb 2018 | Key Notes - Lagging
TRIF - Quinn Staff | 0 | 0 | 0 | 0 | 0 | Trevan will insert key notes here once Feb 2018 info updated from Amber
TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0
Lost Time Incidents | 0 | 0 | 0 | 0 | 0
Recordable Medical Aid | 0 | 0 | 0 | 0 | 1
First Aid | 3 | 2 | 7 | 1 | 0
Vehicle Incidents | 1 | 2 | 6 | 1 | 1
Modified Work | 0 | 0 | 0 | 0 | 0
Environmental Events | 2 | 1 | 1 | 0 | 0
Operational Performance | [8 empty] | Continuous Improvement & Value Opportunities
Measure | Target | 2015 | 2016 | 2017 | Jan 2017 | Feb 2017 | Jan 2018 | Feb 2018 | Initiative | Measure | Savings Goal | Status
Rework | <$10,000 / year / unit | 2714.72 | 3125.68 | 2487.47 | 0 | 0 | 0 | 0 | 1) Cost Avoidance from using a Canadian Natural Skid Steer | Rental Cost Avoided | $24k per Year | Delivered
NCR's | <10 / year / operating unit | 7 | 3 | 5 | 0 | 0 | 0 | 0 | 2) Vehicle cost & Safety Optimization | #of vehicles & km's driven | Estimated: $0.5M | In Progress
Repair Rate | <3% All Weld Counts | No Data | No Data | 1.284% | 0.7353% | 2.21% | 1.515% | 5.263% | 3) 7 x7 Schedule Optimization | Less OT - lower labour cost | Estimated: $0.5M | In Progress
Total Welds | # of Welds (Actual) | No Data | No Data | 1168 | 136 | 181 | 66 | 95 | 4) Scaffolding optimization | Reduce break-in | TBD | In Progress
Total Repairs | # of Repairs (Actual) | No Data | No Data | 15 | 1 | 4 | 1 | 5 | 5) Indirect labour / Site Manager Labour role optimiization | Improved value delivery | TBD | In Progress
Packages: Signed off by Quinn/In CNRL Review | TBD | 313 | 399 | 1275 | 4 | 17 | 4 | 19 | 6) QC Package process streaminling | Time spent | TBD | In Progress
Packages: In Review by Quinn | TBD | 27 | 16 | 92 | 0 | 0 | 0 | 2
Packages: Completed and Scanned | TBD | 225 | 304 | 714 | 0 | 0 | 5 | 19
Non-Productive Time
- Quinn will review Non-Productive KPI process and themes
- Themes can then be used to identify opportunities for efficiency and cost improvement
- Opportunities can then be prioritized and work by team
Canadian Natural Operational Feedback / Updates
- Spring Wolf Lake Turnaround set to begin first week of April
Quinn Natural Operational Feedback / Updates
- 934,624 recordable free hours as at Sep 30, 2017
2017 Jan + Feb = 32,721
2018 Jan + Feb = TBD - once Amber updates = + or - x % from same period in 2017
November OT hours drop:
Turnaround related
2018 Goal: Annual Value Improvement = 5% of Spend
5% x $15 M = $0.75 M
Over $1M CAD in Value Improvement Pipeline for 2018
2016 to '17 spend increase partly due to bi-annual OTSG maintenance

## Input - Safety Data
Quinn - Staff
TRIF and Exposure Hours
| TRIF | Exposure Hours
2015 | 0 | 207536
2016 | 0 | 187194
2017-01-01 | 0 | 14632
2017-02-01 | 0 | 14473
2017-03-01 | 0 | 16343
2017-04-01 | 0 | 17532
2017-05-01 | 0 | 19257
2017-06-01 | 0 | 19222
2017-07-01 | 0 | 15712
2017-08-01 | 0 | 17418
2017-09-01 | 0 | 15912
2017-10-01 | 0 | 16122
2017-11-01 | 0 | 14519
2017-12-01 | 0 | 12841
2017 | 0 | 193983
2018-01-01 | 0 | 16810
2018-02-01 | 0 | 17110
Quinn - Sub-contractors
TRIF and Exposure Hours
| TRIF | Exposure Hours
2015 | 0 | 23530
2016 | 0 | 23350
2017-01-01 | 0 | 1855
2017-02-01 | 0 | 1761
2017-03-01 | 0 | 2048
2017-04-01 | 0 | 1980
2017-05-01 | 0 | 1822
2017-06-01 | 0 | 2026
2017-07-01 | 0 | 1485
2017-08-01 | 0 | 1525
2017-09-01 | 0 | 1536
2017-10-01 | 0 | 1822
2017-11-01 | 0 | 1323
2017-12-01 | 0 | 1259
2017 | 0 | 20442
2018-01-01 | 0 | 1985
2018-02-01 | 0 | 1679
Blue Bold = Inputs
|  | 2015 | 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2017 | 2018-01-01 | 2018-02-01
Leading | Man-Hours | 231066 | 210544 | 16487 | 16234 | 18391 | 19512 | 21079 | 21248 | 17197 | 18943 | 17448 | 17944 | 15842 | 14100 | 214425 | 18795 | 17500
Leading | Hazard ID's | 843 | 935 | 92 | 119 | 86 | 115 | 99 | 119 | 99 | 106 | 111 | 111 | 113 | 97 | 1267 | 109 | 85
Leading | Safety Meetings | 15 | 15 | 2 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 2
Leading | Work Site Inspections | 289 | 265 | 23 | 26 | 21 | 28 | 52 | 28 | 17 | 11 | 39 | 44 | 27 | 20 | 336 | 63 | 45
Leading | Pre-Task Analysis Cards | 7770 | 6373 | 492 | 509 | 450 | 460 | 604 | 581 | 500 | 487 | 526 | 532 | 444 | 397 | 5982 | 439 | 400
Leading | Pre-job Toolbox Meetings | 1828 | 1606 | 160 | 115 | 115 | 129 | 146 | 300 | 124 | 135 | 209 | 153 | 138 | 105 | 1829 | 178 | 150
Leading | Behaviour Based Safety Observations | 2243 | 1946 | 177 | 157 | 151 | 152 | 158 | 185 | 154 | 178 | 191 | 169 | 149 | 212 | 2033 | 260 | 200
Leading | Near Hit/Near miss | 2 | 16 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6 | 1 | 0
Lagging | TRIF - Quinn Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | Recordable Medical Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Lagging | First Aid | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 7 | 1 | 0
Lagging | Vehicle Incidents | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 6 | 1 | 1
Lagging | Modified Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | Environmental Events | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Off the Job Injury/Illness | 16 | 17 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | Leave out and if it is important we can bring back in - we left it out of Q3 2017's SRM |  |  | 12 | 3 | 2

## Input - Operational Raw Data
Blue Bold = Inputs
OT Exposure Hours - by Group
|  | Maintenance | Turnaround | Maint. Scaffolding | Turnaround Scaffolding | % Overtime | Total OT Exposure Hours | Total Exposure Hours
| 2017-10-01 | 317.5 | 1190.5 | 0 | 234 | 9.839% | 1742 | 17705.5
| 2017-11-01 | 260.5 | 305 | 21 | 28 | 3.898% | 614.5 | 15764.5
| 2017-12-01 | 155 | 1000.5 | 0 | 93.5 | 8.96% | 1249 | 13939.5
| 2018-01-01 | 263.5 | 1280 | 417 | 292.5 | 12.06% | 2253 | 18687
| 2018-02-01 | 250 | 1200 | 30 | 150 | 9.056% | 1630 | 18000
Operational Performance - Work Quality
|  | Rework | NCR's | Repair Rate | Total Welds | Total Repairs
|  | <$10,000 / year / unit | < 10 / year / operating unit | <3% All Weld Counts | # of Welds (Actual) | # of Repairs (Actual)
| 2015 | 2714.72 | 7 | No Data | No Data | No Data
| 2016 | 3125.68 | 3 | No Data | No Data | No Data
| 2017-01-01 | 0 | 0 | 0.7353% | 136 | 1
| 2017-02-01 | 0 | 0 | 2.21% | 181 | 4
| 2017-03-01 | 300 | 1 | 2.105% | 190 | 4
| 2017-04-01 | 0 | 0 | 0.6579% | 152 | 1
| 2017-05-01 | 0 | 2 | 1.852% | 54 | 1
| 2017-06-01 | 1500 | 0 | 1.538% | 65 | 1
| 2017-07-01 | 0 | 1 | 2.062% | 97 | 2
| 2017-08-01 | 687.47 | 0 | 0% | 100 | 0
| 2017-09-01 | 0 | 0 | 1.282% | 78 | 1
| 2017-10-01 | 0 | 0 | 0% | 38 | 0
| 2017-11-01 | 0 | 0 | 0% | 35 | 0
| 2017-12-01 | 0 | 1 | 0% | 42 | 0
| 2017 | 2487.47 | 5 | 1.284% | 1168 | 15
| 2018-01-01 | 0 | 0 | 1.515% | 66 | 1
| 2018-02-01 | 0 | 0 | 5.263% | 95 | 5
Operational Performance - Work Quality
Note: These KPI's reflect a "snap-shot" in time
|  | Packages: Signed off by Quinn/In CNRL Review | Packages: In Review by Quinn | Packages: Completed and Scanned
| 2015 | 313 | 27 | 225
| 2016 | 399 | 16 | 304
| 2017-01-01 | 4 | 0 | 0
| 2017-02-01 | 17 | 0 | 0
| 2017-03-01 | 32 | 4 | 0
| 2017-04-01 | 53 | 3 | 9
| 2017-05-01 | 65 | 4 | 18
| 2017-06-01 | 106 | 6 | 33
| 2017-07-01 | 144 | 8 | 38
| 2017-08-01 | 157 | 22 | 52
| 2017-09-01 | 241 | 10 | 84
| 2017-10-01 | 162 | 12 | 115
| 2017-11-01 | 139 | 12 | 179
| 2017-12-01 | 155 | 11 | 186
| 2017 | 1275 | 92 | 714
| 2018-01-01 | 4 | 0 | 5
| 2018-02-01 | 19 | 2 | 19

## Output - Safety & Ops
Exposure Hours
| Staff | Sub
2015 | 207536 | 23530
2016 | 187194 | 23350
2017 | 193983 | 20442
2017-01-01 | 14632 | 1855
2017-02-01 | 14473 | 1761
2018-01-01 | 16810 | 1985
2018-02-01 | 17110 | 1679
OT Exposure Hours - by Group
| Maint. | TA | Maint. Scaff. | TA Scaff. | % OT
2017-10-01 | 317.5 | 1190.5 | 0 | 234 | 9.839%
2017-11-01 | 260.5 | 305 | 21 | 28 | 3.898%
2017-12-01 | 155 | 1000.5 | 0 | 93.5 | 8.96%
2018-01-01 | 263.5 | 1280 | 417 | 292.5 | 12.06%
2018-02-01 | 250 | 1200 | 30 | 150 | 9.056%
All up OT Exposure Hours
|  | Exposure Hours: All Staff + Sub | OT only: All Staff + Sub
| 2015 | 231066 | 23000
| 2016 | 210544 | 22000
| 2017 | 214425 | 23000
Safety Stats
Leading Indicator | 2015 | 2016 | 2017 | 2018-01-01 | 2018-02-01
Man-Hours | 231066 | 210544 | 214425 | 18795 | 17500
Hazard ID's | 843 | 935 | 1267 | 109 | 85 |  | For Q1 2018 SRM: note comments as applicable
Safety Meetings | 15 | 15 | 18 | 1 | 2
Work Site Inspections | 289 | 265 | 336 | 63 | 45
Pre-Task Analysis Cards | 7770 | 6373 | 5982 | 439 | 400
Pre-job Toolbox Meetings | 1828 | 1606 | 1829 | 178 | 150
BBSO | 2243 | 1946 | 2033 | 260 | 200
Near Hit/Near miss | 2 | 16 | 6 | 1 | 0
Lagging Indicator | 2015 | 2016 | 2017 | 2018-01-01 | 2018-02-01
TRIF - Quinn Staff | 0 | 0 | 0 | 0 | 0
TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0
Lost Time Incidents | 0 | 0 | 0 | 0 | 0
Recordable Medical Aid | 0 | 0 | 0 | 0 | 1
First Aid | 3 | 2 | 7 | 1 | 0
Vehicle Incidents | 1 | 2 | 6 | 1 | 1
Modified Work | 0 | 0 | 0 | 0 | 0
Environmental Events | 2 | 1 | 1 | 0 | 0
ComplyWork Status = | Acceptable
Operational Performance
Measure | Target | 2015 | 2016 | 2017 | 2017-01-01 | 2017-02-01 | 2018-01-01 | 2018-02-01
Rework | <$10,000 / year / unit | 2714.72 | 3125.68 | 2487.47 | 0 | 0 | 0 | 0
NCR's | <10 / year / operating unit | 7 | 3 | 5 | 0 | 0 | 0 | 0
Repair Rate | <3% All Weld Counts | No Data | No Data | 1.284% | 0.7353% | 2.21% | 1.515% | 5.263%
Total Welds | # of Welds (Actual) | No Data | No Data | 1168 | 136 | 181 | 66 | 95
Total Repairs | # of Repairs (Actual) | No Data | No Data | 15 | 1 | 4 | 1 | 5
Packages: Signed off by Quinn/In CNRL Review | TBD | 313 | 399 | 1275 | 4 | 17 | 4 | 19
Packages: In Review by Quinn | TBD | 27 | 16 | 92 | 0 | 0 | 0 | 2
Packages: Completed and Scanned | TBD | 225 | 304 | 714 | 0 | 0 | 5 | 19

## Cost Savings & Avoidance
Blue Bold = Inputs
|  | Cost Avoidance | Cost Savings | Total | Description
| 2017-09-01 | 24000 | 0 | 24000 | Skid Steer rental - details in cost savings log
| 2017-10-01 | 0 | 0 | 0
| 2017-11-01 | 0 | 0 | 0
| 2017-12-01 | 0 | 0 | 0
| 2017 | 24000 | 0 | 24000
| 2018-01-01 | 0 | 0 | 0
| 2018-02-01 | 0 | 0 | 0
| 2018-03-01 | 0 | 0 | 0
| 2018-04-01 | 0 | 0 | 0
| 2018-05-01 | 0 | 0 | 0
| 2018-06-01 | 0 | 0 | 0
| 2018-07-01 | 0 | 0 | 0
| 2018-08-01 | 0 | 0 | 0
Outputs - Value Improvement
|  | Cost Avoidance | Cost Savings
| 2017 | 24000 | 0
| 2018-01-01 | 0 | 0
| 2018-02-01 | 0 | 0
| 2018-03-01 | 0 | 0
| 2018-04-01 | 0 | 0
| 2018-05-01 | 0 | 0
| 2018-06-01 | 0 | 0
| 2018-07-01 | 0 | 0
| 2018-08-01 | 0 | 0
- Non Productive KPI will be tool to be used for identifying furture opportunities
- Goal: Annual value Improvement of 10% annual spend

## 2015 - Wolf Lake
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2015
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 1100072.08
25272 | Quinn Contracting Ltd. | 3130 | Environmental Costs | 3130-145 | Equipment | 22991.07
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-245 | Mobilization / Unit Lay | 1370.95
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-194 | Const/Super/Inspect Mgt | 112.86
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 24965.16
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-415 | Instrument Materials | 5737.42
25272 | Quinn Contracting Ltd. | 3210 | Major Controllable Equipment | 3210-230 | Building Over 200 Sq. Ft. | 10052.57
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-305 | Earthworks/Fencing/Sign | 282.68
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-310 | Foundatn/Piling Mat&Lbr | 6609.05
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 15061.17
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 1100971.53
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-335 | Insulation, Painting, Coating | 41846.96
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-350 | Non Destructive Testing | 515.53
25272 | Quinn Contracting Ltd. | 3210 | Office / Administration | 3210-605 | Eng. Reports & Studies | 11829.3
2342418.33
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 2801087.02
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 71111.72
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-105 | Salary Admin | 12893.33
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 82.01
25272 | Quinn Contracting Ltd. | 6040 | Lease & Road Maintenance | 6040-105 | Lease & Road Maintenance | 668.55
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 11608051.04
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 3742.01
25272 | Quinn Contracting Ltd. | 6070 | Fuel | 6070-105 | Fuel | 1018.89
25272 | Quinn Contracting Ltd. | 6080 | Trucking | 6080-110 | Trucking - Produced Water | 997.47
25272 | Quinn Contracting Ltd. | 6100 | Equipment Rental | 6100-105 | Equipment Rental | 34770.4
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 330.96
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 6008.37
25272 | Quinn Contracting Ltd. | 6130 | Downhole Services | 6130-130 | Steamer/Chem Wash/Vacuum Truck | 3159.51
25272 | Quinn Contracting Ltd. | 6180 | Processing Fees | 6180-115 | Fluid Disposal | 4731.87
11747566.13

## 2016 - Wolf Lake
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2016
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 315421.35
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 1348646.13
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 25834.25
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 773.68
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-325 | Miscellaneous | 702.53
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-196 | Equipment Rentals | 5029.48
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-199 | Non-Destructive Testing | 6996.61
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 5523.25
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-415 | Instrument Materials | 854.94
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-425 | Control Systems MTL&LBR | 1347.34
25272 | Quinn Contracting Ltd. | 3210 | Major Controllable Equipment | 3210-230 | Building Over 200 Sq. Ft. | 26595.47
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 5597.06
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 1036484.77
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-350 | Non Destructive Testing | 398.92
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-905 | Overhead | 627.72
2780833.5
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 3586362.37
25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-105 | Parts & Supplies | 3014.7
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 84063
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 1409.21
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 7445408.92
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 6073.76
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-115 | R&M - Labour | 216.76
25272 | Quinn Contracting Ltd. | 6070 | Fuel | 6070-105 | Fuel | 413.81
25272 | Quinn Contracting Ltd. | 6100 | Equipment Rental | 6100-105 | Equipment Rental | 7606.8
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 3031.6
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 26478.93
25272 | Quinn Contracting Ltd. | 6180 | Processing Fees | 6180-115 | Fluid Disposal | 313.86
7578031.35

## 2017 - Wolf Lake
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2017 to Dec 31, 2017
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 9, 2018 - 11:00am
2017
Vendor Number | Vendor Name | GL Code | GL Sub Desc | 560 Wolf Lake | OBJECT_NAME
25272 | Quinn Contracting Ltd. | 3110-650 | ICC-Production Testing | 5573.29 | 3110 ICC-Completion Services
25272 | Quinn Contracting Ltd. | 3110-660 | ICC-Treating / Stimulation | 4873.28 | 3110 ICC-Completion Services
25272 | Quinn Contracting Ltd. | 3110-205 | ICC-Lease & Road Restoration | 336.6 | 3110 ICC-Lease, Road, Access Cost
25272 | Quinn Contracting Ltd. | 3110-405 | ICC-Service Rig & Rig Move | 2337.78 | 3110 ICC-Rig Costs
25272 | Quinn Contracting Ltd. | 3200-220 | Equipment Installation&Setting | 261923.83 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-235 | Pipe Fab & Install | 69186.85 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-280 | Pipe, Valves & Fittings | 901.09 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-285 | P/L Test/Cleaning/Inspc | 85914.36 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-325 | Miscellaneous | 5839.68 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-335 | Non-Operated Equipment&Labour | 1512.22 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-199 | Non-Destructive Testing | 696.92 | 3200 Well Equip/Tie-In Costs
25272 | Quinn Contracting Ltd. | 3210-410 | E&I Labour | 16458.46 | 3210 Electrical & Instrumentation
25272 | Quinn Contracting Ltd. | 3210-425 | Control Systems MTL&LBR | 2513 | 3210 Electrical & Instrumentation
25272 | Quinn Contracting Ltd. | 3210-505 | Catalyst / Chemical | 2436.85 | 3210 Field Cost
25272 | Quinn Contracting Ltd. | 3210-515 | Start-Up / Commissioning | 3511.37 | 3210 Field Cost
25272 | Quinn Contracting Ltd. | 3210-320 | Pipe/Valves & Fittings | 4535.52 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-325 | Mechanical Labour | 882119.23 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-335 | Insulation, Painting, Coating | 3483.99 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-340 | Equipment Rental | 2528.3 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-350 | Non Destructive Testing | 3050.68 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-610 | Inspect/Supr/Const Supp | 68903.18 | 3210 Office / Administration
1428636.48
25272 | Quinn Contracting Ltd. | 3210-710 | Plant / Battery Turnaround | 3234566.46 | 3210 Others
25272 | Quinn Contracting Ltd. | 6010-105 | Parts & Supplies | 45794.36 | 6010 Parts & Supplies
25272 | Quinn Contracting Ltd. | 6010-110 | Lubricants | 6344.36 | 6010 Parts & Supplies
25272 | Quinn Contracting Ltd. | 6020-115 | Contract Operations | 64087.08 | 6020 Labour
25272 | Quinn Contracting Ltd. | 6020-120 | Engineering,Superv.,Consulting | 668.09 | 6020 Labour
25272 | Quinn Contracting Ltd. | 6030-130 | Vehicle Costs | 2752.17 | 6030 Other Labour
25272 | Quinn Contracting Ltd. | 6050-105 | Repairs & Maintenance | 10567777.88 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6050-110 | Pipeline Patrol | 16285.34 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6100-105 | Equipment Rental | 2311.97 | 6100 Equipment Rental
25272 | Quinn Contracting Ltd. | 6110-105 | Instrumentation / Electrical | 2214.14 | 6110 Instrumentation
25272 | Quinn Contracting Ltd. | 6110-110 | Instrumentation - Labour | 41004.42 | 6110 Instrumentation
10749239.81
Total | Total | Total | Total | 15412442.75 | Grand Total

## 2018 YTD - Wolf Lake
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2018 to Feb 28, 2018
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 9, 2018 - 11:00am
2018
Vendor Number | Vendor Name | GL Code | GL Sub Desc | 560 Wolf Lake | OBJECT_NAME
25272 | Quinn Contracting Ltd. | 3200-220 | Equipment Installation&Setting | 29.78 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-235 | Pipe Fab & Install | 7343.4 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-285 | P/L Test/Cleaning/Inspc | 501.94 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-325 | Miscellaneous | 2541.27 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3210-410 | E&I Labour | 7874.61 | 3210 Electrical & Instrumentation
25272 | Quinn Contracting Ltd. | 3210-310 | Foundatn/Piling Mat&Lbr | 1192.47 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-325 | Mechanical Labour | 93586.96 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-335 | Insulation, Painting, Coating | 1920.8 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-340 | Equipment Rental | 562.87 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-610 | Inspect/Supr/Const Supp | 880.69 | 3210 Office / Administration
116434.79
25272 | Quinn Contracting Ltd. | 3210-710 | Plant / Battery Turnaround | 694013.36 | 3210 Others
25272 | Quinn Contracting Ltd. | 6010-105 | Parts & Supplies | 340.54 | 6010 Parts & Supplies
25272 | Quinn Contracting Ltd. | 6020-115 | Contract Operations | 4967.02 | 6020 Labour
25272 | Quinn Contracting Ltd. | 6050-105 | Repairs & Maintenance | 897839 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6050-110 | Pipeline Patrol | 891.3 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6100-105 | Equipment Rental | 640.45 | 6100 Equipment Rental
25272 | Quinn Contracting Ltd. | 6110-105 | Instrumentation / Electrical | 597.51 | 6110 Instrumentation
25272 | Quinn Contracting Ltd. | 6110-110 | Instrumentation - Labour | 2335.17 | 6110 Instrumentation
907610.99
Total | Total | Total | Total | 1718059.14 | Grand Total

## Spend Chart
| 2015 | 2016 | 2017 | 2018 YTD Jan + Feb
Operations | 11747566 | 7578731 | 10749239.81 | 907610.99
Wells Servicing | 2342418 | 2780334 | 1428636.48 | 116434.79
Turnaround | 2801087 | 3586352 | 3234566.46 | 694013.36
| 16891071 | 13945417 | 15412442.75 | 1718059.14
| 2015 | 2016 | 2017 | 2018 YTD Jan + Feb
Total | 16891071 | 13945417 | 15412442.75 | 1718059.14