## SRM
Canadian Natural and Quinn Contracting Dashboard
MGSA # 810354-1 - Supplement 3
Q1 2018
Review held on March 22, 2018
I. Safety
Leading Indicator | 2015 | 2016 | Q1 2017 | Q2 2017 | Q3 2017 | 2017 YTD | 2017F* | 2017F* vs 2016 | Safety Performance Observations - Leading Indicators
Man-Hours | 231066 | 210544 | 51112 | 61839 | 53588 | 166539 | 222052 | 5.466% | - Any value in targets for each Safety Indicator? - Volume of Pre-Task Analysis Cards & BBSO's has dropped compared to other Leading Indicator workstreams (2017F vs 2016) - What drives level of work-site inspections? 70 in Q1 vs 108 in Q2
Hazard ID's | 843 | 935 | 297 | 333 | 316 | 946 | 1261.3333 | 34.9%
Safety Meetings | 15 | 15 | 4 | 8 | 3 | 15 | 20 | 33.33%
Work Site Inspections | 289 | 265 | 70 | 108 | 67 | 245 | 326.6667 | 23.27%
Pre-Task Analysis Cards | 7770 | 6373 | 1451 | 1645 | 1513 | 4609 | 6145.3333 | -3.572%
Pre-job Toolbox Meetings | 1828 | 1606 | 390 | 575 | 468 | 1433 | 1910.6667 | 18.97%
Behavior-Based Safety Observations (BBSO) | 2243 | 1946 | 485 | 495 | 523 | 1503 | 2004 | 2.98%
Lagging Indicator | 2015 | 2016 | Q1 2017 | Q2 2017 | Q3 2017 | 2017 YTD | 2017F* | 2017F* vs 2016 | Safety Performance Observations - Lagging Indicators
TRIF - Quinn Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - Clarify Near Miss/Near Hit definitions and reporting method. - There has been a reduction in Near Hit/Near Misses project, compared to projected rate of First Aids and Vehicle Incidents. - What are the root causes of the forecasted increase in First Aid's for 2017? Is there a Summary of 2016 vs 2017 First Aid incidents, root causes, and action plans to correct? - Vehicle incidents - Root cause and preventative measures for us to take?
TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Recordable Medical Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
First Aid | 3 | 2 | 1 | 2 | 3 | 6 | 8 | 300%
Near Hit/Near miss | 2 | 16 | 4 | 1 | 0 | 5 | 6.6667 | -58.33%
Vehicle Incidents | 1 | 2 | 2 | 1 | 0 | 3 | 4 | 50%
Modified Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Environmental Events | 2 | 1 | 1 | 0 | 0 | 1 | 1.3333 | -
III. Operational Performance | [8 empty] | IV. Continuous Improvement & Value Opportunities
Measure | Target | 2016 | Q1 2017 | Q2 2017 | Q3 2017 | 2017 YTD | 2017F* | 2017F* vs 2016 | Initiative | Measure | Savings Goal | Status
Rework | <$10,000 / year / unit | 3125.68 | 300 | 1500 | 687.47 | 2487.47 | 3316.6267 | 6.109% | 1) Cost Avoidance from using a Canadian Natural Skid Steer | Rental Cost Avoided | $24k per Year | Implemented
NCR's | <10 / year / operating unit | 3 | 1 | 2 | 1 | 4 | 5.3333 | 77.78% | 2) Reduction of Administration processes for LEM approvals | Time saved (Labour) | $95/hour x 52 weeks = $4,940 | Being Reviewed
Repair Rate | <3% All Weld Counts | No Data | 0.0505 | 0.0405 | 0.0334 | 0.1244 | 0.16587 | No Data | 3) Confined Space Permiting | Clarifying Objectives of Watch | Benefit from operations clarity of who does what | Contining with proposed Roll-out
Total Welds | # of Welds (Actual) | No Data | 507 | 271 | 275 | 1053 | 1404 | No Data | 4) Intiative #1 - link to Non-Productive Time section below - data for Q1 2018
Total Repairs | # of Repairs (Actual) | No Data | 9 | 3 | 3 | 15 | 20 | No Data | 5) Intiative #2 - link to Non-Productive Time section below - data for Q1 2018
Packages: Signed off by Quinn/In CNRL Review | TBD | 399 | 53 | 224 | 542 | 819 | 1092 | 173.7% | 6) Intiative #3 - link to Non-Productive Time section below - data for Q1 2018
Packages: In Review by Quinn | TBD | 16 | 4 | 13 | 40 | 57 | 76 | 375%
Packages: Completed and Scanned | TBD | 304 | 0 | 60 | 174 | 234 | 312 | 2.632%
IV. Non-Productive Time [Placeholder for Q1 2018 Review]
- Top 5 Non-Productive time drivers
- Prioritize which ones we can support each other on
- Link to Targets
Canadian Natural Operational Feedback / Updates
- Confined space permit draft
- Audit Team appreciates the support received from Quinn (Dick Dornstauder)
Quinn Natural Operational Feedback / Updates
- 934,624 recordable free hours as at Sep 30, 2017
*F = Trend for full year should rate continue
Sep 2017: Use Canadian Natural Bobcat at Primrose, and rent Bobcat at Wolf Lake
Goal: Annual Value Improvement = 5% of Spend
5% x $12 MM = $0.6 MM
2017 Forecasted Exposure Hours = 105% of 2016 levels

## Input - Raw Safety Data
Quinn - Staff
TRIF and Exposure Hours
| TRIF | Exposure Hours
2015 | 0 | 207536
2016 | 0 | 187194
2017-01-01 | 0 | 14632
2017-02-01 | 0 | 14473
2017-03-01 | 0 | 16343
2017-04-01 | 0 | 17532
2017-05-01 | 0 | 19257
2017-06-01 | 0 | 19222
2017-07-01 | 0 | 15712
2017-08-01 | 0 | 17418
2017-09-01 | 0 | 15912
2017-10-01 | 0
2017-11-01 | 0
2017-12-01 | 0
2017 | 0 | 150501
2018-01-01 | 0
Quinn - Sub-contractors
TRIF and Exposure Hours
| TRIF | Exposure Hours
2015 | 0 | 23530
2016 | 0 | 23350
2017-01-01 | 0 | 1855
2017-02-01 | 0 | 1761
2017-03-01 | 0 | 2048
2017-04-01 | 0 | 1980
2017-05-01 | 0 | 1822
2017-06-01 | 0 | 2026
2017-07-01 | 0 | 1485
2017-08-01 | 0 | 1525
2017-09-01 | 0 | 1536
2017-10-01 | 0
2017-11-01 | 0
2017-12-01 | 0
2017 | 0 | 16038
2018-01-01 | 0
Blue Bold = Inputs
|  | 2015 | 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2017 | 2018-01-01
Leading | Man-Hours | 231066 | 210544 | 16487 | 16234 | 18391 | 19512 | 21079 | 21248 | 17197 | 18943 | 17448 |  |  |  | 166539 | 18795
Leading | Hazard ID's | 843 | 935 | 92 | 119 | 86 | 115 | 99 | 119 | 99 | 106 | 111 |  |  |  | 946 | 109
Leading | Safety Meetings | 15 | 15 | 2 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 |  |  |  | 15 | 1
Leading | Work Site Inspections | 289 | 265 | 23 | 26 | 21 | 28 | 52 | 28 | 17 | 11 | 39 |  |  |  | 245 | 63
Leading | Pre-Task Analysis Cards | 7770 | 6373 | 492 | 509 | 450 | 460 | 604 | 581 | 500 | 487 | 526 |  |  |  | 4609 | 439
Leading | Pre-job Toolbox Meetings | 1828 | 1606 | 160 | 115 | 115 | 129 | 146 | 300 | 124 | 135 | 209 |  |  |  | 1433 | 178
Leading | Behaviour Based Safety Observations | 2243 | 1946 | 177 | 157 | 151 | 152 | 158 | 185 | 154 | 178 | 191 |  |  |  | 1503 | 260
Leading | Near Hit/Near miss | 2 | 16 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  | 5 | 1
Lagging | TRIF - Quinn Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Lagging | TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Lagging | Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Lagging | Recordable Medical Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Lagging | First Aid | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 1 | 1 | 1 |  |  |  | 6 | 1
Lagging | Vehicle Incidents | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3 | 1
Lagging | Modified Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Lagging | Environmental Events | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | 0
| Off the Job Injury/Illness | 16 | 17 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | Leave out and if it is important we can bring back in - we left it out of Q3 2017's SRM |  |  | 12 | 3

## Input - Operational Raw Data
Blue Bold = Inputs
Inputs | [12 empty] | Amber: These monthly #'s are "nice to have", but not a "need to have" if it's a lot of work so no worries if it's too much trouble
Measure | Target | 2015 | 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Q4 2017 | 2018-01-01
Rework | <$10,000 / year / unit | 2714.72 | 3125.68 | 0 | 0 | 300 | 0 | 0 | 1500 | 0 | 687.47 | 0 |  |  |  | 0 | 0
NCR's | < / year / operating unit | 7 | 3 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 |  |  |  | 4 | 0
Repair Rate | <3% All Weld Counts | No Data | No Data | 0.74% | 2.21% | 2.1% | 0.66% | 1.85% | 1.54% | 2.06% | 0% | 1.28% |  |  |  | 1.72% | 1.51%
Total Welds | # of Welds (Actual) | No Data | No Data | 136 | 181 | 190 | 152 | 54 | 65 | 97 | 100 | 78 |  |  |  | 145 | 81
Total Repairs | # of Repairs (Actual) | No Data | No Data | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 0 | 1 |  |  |  | 0 | 1
Amber to confirm calculation
Amber: These monthly #'s are "nice to have", but not a "need to have" if it's a lot of work so no worries if it's too much trouble
Packages |  | 2015 | 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Q4 2017 | 2018-01-01
Packages: Signed off by Quinn/In CNRL Review |  | 313 | 399 | 4 | 17 | 32 | 53 | 65 | 106 | 144 | 157 | 241 |  |  |  | 155 | 4
Packages: In Review by Quinn |  | 27 | 16 | 0 | 0 | 4 | 3 | 4 | 6 | 8 | 22 | 10 |  |  |  | 11 | 0
Packages: Completed and Scanned |  | 225 | 304 | 0 | 0 | 0 | 9 | 18 | 33 | 38 | 52 | 84 |  |  |  | 186 | 5
Trevan to add in OT Hours and %
Table | [6 empty] | Amber confirming math
Measure | Target | 2016 | Q1 2017 | Q2 2017 | Q3 2017 | Q4 2017 | 2017 | 2018-01-01 |  |  |  | 2015
Rework | <$10,000 / year / unit | 3125.68 | 300 | 1500 | 687.47 | 0 | 2487.47 | 0 |  |  |  | 2714.72
NCR's | <10 / year / operating unit | 3 | 1 | 2 | 1 | 4 | 8 | 0 |  |  |  | 7
Repair Rate | <3% All Weld Counts | No Data | 5.05% | 4.05% | 3.34% | 1.72% | 1.252% | 1.669% |  |  |  | No Data
Total Welds | # of Welds (Actual) | No Data | 507 | 271 | 275 | 145 | 1198 | 1597.3333 |  |  |  | No Data
Total Repairs | # of Repairs (Actual) | No Data | 9 | 3 | 3 | 0 | 15 | 20 |  |  |  | No Data
Packages: Signed off by Quinn/In CNRL Review |  | 399 | 53 | 224 | 542 | 155 | 155 | 206.6667 |  |  |  | 313
Packages: In Review by Quinn |  | 16 | 4 | 13 | 40 | 11 | 11 | 14.6667 |  |  |  | 27
Packages: Completed and Scanned |  | 304 | 0 | 60 | 174 | 186 | 420 | 560 |  |  |  | 225
Amber please would you kindly confirm:
Packages: Signed off by Quinn/In CNRL Review | is a "snap-shot" in time i.e. at the end of the month, or at the end of the quarter. Adding up each month for the full year doesn't make sense.
Packages: In Review by Quinn | is a "snap-shot" in time i.e. at the end of the month, or at the end of the quarter. Adding up each month for the full year doesn't make sense.
Packages: Completed and Scanned | total completed for year, can be added up and is cumulative.

## Output - Safety Charts and Info
[9 empty] | Staff | Sub Contractors |  |  | Staff | Sub Contractors
[8 empty] | 2015 | 207536 | 23530 |  | TRIF 2015 | 0 | 0
[8 empty] | 2016 | 187194 | 23350 |  | TRIF 2016 | 0 | 0
[8 empty] | 2017-01-01 | 14632 | 1855 |  | TRIF 2017 YTD | 0 | 0
[8 empty] | 2017-02-01 | 14473 | 1761
[8 empty] | 2017-03-01 | 16343 | 2048
[8 empty] | 2017-04-01 | 17532 | 1980
[8 empty] | 2017-05-01 | 19257 | 1822
[8 empty] | 2017-06-01 | 19222 | 2026
[8 empty] | 2017-07-01 | 15712 | 1485
[8 empty] | 2017-08-01 | 17418 | 1525
[8 empty] | 2017-09-01 | 15912 | 1536
2017-10-01
2017-11-01
2017-12-01
[8 empty] | 2017 | 150501 | 16038
[8 empty] | 2017 F | 200668 | 21384
Leading Indicator | 2015 | 2016 | Q1 2017 | Q2 2017 | Q3 2017 | 2017 YTD | 2017 Projected At current rates | 2017F vs 2016 |  |  | 210544
Man-Hours | 231066 | 210544 | 51112 | 61839 | 53588 | 166539 | 222052 | 5.466% |  |  | 222052
Hazard ID's | 843 | 935 | 297 | 333 | 316 | 946 | 1261.3333 | 34.9%
Safety Meetings | 15 | 15 | 4 | 8 | 3 | 15 | 20 | 33.33%
Work Site Inspections | 289 | 265 | 70 | 108 | 67 | 245 | 326.6667 | 23.27%
Pre-Task Analysis Cards | 7770 | 6373 | 1451 | 1645 | 1513 | 4609 | 6145.3333 | -3.572%
Pre-job Toolbox Meetings | 1828 | 1606 | 390 | 575 | 468 | 1433 | 1910.6667 | 18.97%
BBSO | 2243 | 1946 | 485 | 495 | 523 | 1503 | 2004 | 2.98%
Near Hit/Near miss | 2 | 16 | 4 | 1 | 0 | 5 | 6.6667 | -58.33%
Lagging Indicator | 2015 | 2016 | Q1 2017 | Q2 2017 | Q3 2017 | 2017 YTD | 2017 Projected At current rates | 2017F vs 2016
TRIF - Quinn Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Recordable Medical Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
First Aid | 3 | 2 | 1 | 2 | 3 | 6 | 8 | 300%
Vehicle Incidents | 1 | 2 | 2 | 1 | 0 | 3 | 4 | 100%
Modified Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Environmental Events | 2 | 1 | 1 | 0 | 0 | 1 | 1.3333 | 33.33%
ComplyWork Status = | Acceptable

## Value Improvement Charts
| Cost Avoidance | Cost Savings
2017-09-01 | 24000
2017-10-01
2017-11-01
2017-12-01
2018-01-01
2018-02-01
2018-03-01
2018-04-01
2018-05-01
2018-06-01
2018-07-01
2018-08-01

## 2015 - Wolf Lake
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2015
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 1100072.08
25272 | Quinn Contracting Ltd. | 3130 | Environmental Costs | 3130-145 | Equipment | 22991.07
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-245 | Mobilization / Unit Lay | 1370.95
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-194 | Const/Super/Inspect Mgt | 112.86
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 24965.16
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-415 | Instrument Materials | 5737.42
25272 | Quinn Contracting Ltd. | 3210 | Major Controllable Equipment | 3210-230 | Building Over 200 Sq. Ft. | 10052.57
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-305 | Earthworks/Fencing/Sign | 282.68
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-310 | Foundatn/Piling Mat&Lbr | 6609.05
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 15061.17
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 1100971.53
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-335 | Insulation, Painting, Coating | 41846.96
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-350 | Non Destructive Testing | 515.53
25272 | Quinn Contracting Ltd. | 3210 | Office / Administration | 3210-605 | Eng. Reports & Studies | 11829.3
2342418.33
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 2801087.02
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 71111.72
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-105 | Salary Admin | 12893.33
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 82.01
25272 | Quinn Contracting Ltd. | 6040 | Lease & Road Maintenance | 6040-105 | Lease & Road Maintenance | 668.55
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 11608051.04
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 3742.01
25272 | Quinn Contracting Ltd. | 6070 | Fuel | 6070-105 | Fuel | 1018.89
25272 | Quinn Contracting Ltd. | 6080 | Trucking | 6080-110 | Trucking - Produced Water | 997.47
25272 | Quinn Contracting Ltd. | 6100 | Equipment Rental | 6100-105 | Equipment Rental | 34770.4
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 330.96
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 6008.37
25272 | Quinn Contracting Ltd. | 6130 | Downhole Services | 6130-130 | Steamer/Chem Wash/Vacuum Truck | 3159.51
25272 | Quinn Contracting Ltd. | 6180 | Processing Fees | 6180-115 | Fluid Disposal | 4731.87
11747566.13

## 2016 - Wolf Lake
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2016
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 315421.35
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 1348646.13
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 25834.25
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 773.68
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-325 | Miscellaneous | 702.53
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-196 | Equipment Rentals | 5029.48
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-199 | Non-Destructive Testing | 6996.61
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 5523.25
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-415 | Instrument Materials | 854.94
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-425 | Control Systems MTL&LBR | 1347.34
25272 | Quinn Contracting Ltd. | 3210 | Major Controllable Equipment | 3210-230 | Building Over 200 Sq. Ft. | 26595.47
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 5597.06
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 1036484.77
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-350 | Non Destructive Testing | 398.92
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-905 | Overhead | 627.72
2780833.5
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 3586362.37
25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-105 | Parts & Supplies | 3014.7
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 84063
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 1409.21
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 7445408.92
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 6073.76
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-115 | R&M - Labour | 216.76
25272 | Quinn Contracting Ltd. | 6070 | Fuel | 6070-105 | Fuel | 413.81
25272 | Quinn Contracting Ltd. | 6100 | Equipment Rental | 6100-105 | Equipment Rental | 7606.8
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 3031.6
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 26478.93
25272 | Quinn Contracting Ltd. | 6180 | Processing Fees | 6180-115 | Fluid Disposal | 313.86
7578031.35

## 2017 YTD as at Sep 20
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2017
25272 | Quinn Contracting Ltd. | 3110 | ICC-Completion Services | 3110-650 | ICC-Production Testing | 5573.29
25272 | Quinn Contracting Ltd. | 3110 | ICC-Completion Services | 3110-660 | ICC-Treating / Stimulation | 63.6
25272 | Quinn Contracting Ltd. | 3110 | ICC-Lease, Road, Access Cost | 3110-205 | ICC-Lease & Road Restoration | 336.6
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 2337.78
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 261923.83
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 48565.24
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-280 | Pipe, Valves & Fittings | 901.09
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 15382.85
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 3155.7
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-425 | Control Systems MTL&LBR | 2513
25272 | Quinn Contracting Ltd. | 3210 | Field Cost | 3210-505 | Catalyst / Chemical | 2436.85
25272 | Quinn Contracting Ltd. | 3210 | Field Cost | 3210-515 | Start-Up / Commissioning | 3511.37
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 3638.59
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 392073.97
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-335 | Insulation, Painting, Coating | 426.76
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-340 | Equipment Rental | 1393.33
25272 | Quinn Contracting Ltd. | 3210 | Office / Administration | 3210-610 | Inspect/Supr/Const Supp | 60487.25
804721.1
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 2093962.58
25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-105 | Parts & Supplies | 5841.25
25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-110 | Lubricants | 6344.36
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 35698.34
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 2216.07
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 6339205.22
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 6288.97
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 1550.64
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 33351.69
6430496.54

## 2017 YTD as at Sep 30, 2017
Premises:
Includes all field offices noted with spend (Wolf Lake is majority however spend report looks at it all).
|  | Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2017
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3110 | ICC-Completion Services | 3110-650 | ICC-Production Testing | 5573.29
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3110 | ICC-Completion Services | 3110-660 | ICC-Treating / Stimulation | 4873.28
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3110 | ICC-Lease, Road, Access Cost | 3110-205 | ICC-Lease & Road Restoration | 336.6
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 2337.78
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 261923.83
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 64383.38
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-280 | Pipe, Valves & Fittings | 901.09
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 30064.57
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-325 | Miscellaneous | 3669.06
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 3155.7
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-425 | Control Systems MTL&LBR | 2513
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Field Cost | 3210-505 | Catalyst / Chemical | 2436.85
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Field Cost | 3210-515 | Start-Up / Commissioning | 3511.37
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 3638.59
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 577409.13
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-335 | Insulation, Painting, Coating | 2297.48
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-340 | Equipment Rental | 1679.38
| Wells Servicing | 25272 | Quinn Contracting Ltd. | 3210 | Office / Administration | 3210-610 | Inspect/Supr/Const Supp | 69571.16
1040275.54
| Turnaround | 25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 2475114.08
| Operations | 25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-105 | Parts & Supplies | 41936.82
| Operations | 25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-110 | Lubricants | 6344.36
| Operations | 25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 50225.13
| Operations | 25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-120 | Engineering,Superv.,Consulting | 9160.58
| Operations | 25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 19217.58
| Operations | 25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 7189224.66
| Operations | 25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 7004.42
| Operations | 25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 1550.64
| Operations | 25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 33351.69
| Operations | 25272 | Quinn Contracting Ltd. | 6740 | M/C-Repairs & Maintenance | 6740-105 | Repairs & Maintenance | 340174.25
7698190.13

## Chart
| 2015 | 2016 | 2017 YTD | 2017 Full Year Projection
Operations | 11747566 | 7578731 | 7698190 | 10264253.3333
Wells Servicing | 2342418 | 2780334 | 1040276 | 1387034.6667
Turnaround | 2801087 | 3586352 | 2475114 | 3300152
| 16891071 | 13945417 | 11213580 | 14951440
| 2015 | 2016 | 2017 YTD | 2017 Full Year Projection
Total | 16891071 | 13945417 | 11213580 | 14951440