## Dashboard
Canadian Natural and Quinn Contracting Dashboard
MGSA # 810354-1 - Supplement 4
Q1 2019
Review held on March 26, 2019
Safety
Leading Indicator | 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019 | Key Notes - Leading
Man-Hours | 231066 | 210544 | 214425 | 291324 | 20779 | 0
Hazard ID's | 843 | 935 | 1267 | 1414 | 117 | 0
Safety Meetings | 15 | 15 | 18 | 15 | 1 | 0
Work Site Inspections | 289 | 265 | 336 | 573 | 33 | 0
Pre-Task Analysis Cards | 7770 | 6373 | 5982 | 7436 | 619 | 0
Pre-job Toolbox Meetings | 1828 | 1606 | 1829 | 2070 | 165 | 0
Behaviour-based Safety Observations | 2243 | 1946 | 2033 | 2801 | 213 | 0
Near Hit/Near miss | 2 | 16 | 6 | 6 | 0 | 0
Lagging Indicator | 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019 | Key Notes - Lagging
TRIF - Quinn Staff (as at Period end) | 0.62 | 0 | 0.97 | 0.83 | 0 | 0 | - comment on first aid / environmental event
TRIF - Subs (as at Period End) | 0 | 0 | 0 | 0 | 0 | 0
Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0
Recordable Medical Aid | 0 | 0 | 0 | 1 | 0 | 0
First Aid | 3 | 2 | 7 | 7 | 1 | 0
Vehicle Incidents | 1 | 2 | 6 | 2 | 0 | 0
Modified Work | 0 | 0 | 0 | 0 | 0 | 0
Environmental Events | 2 | 1 | 1 | 2 | 1 | 0
Operational Performance | [8 empty] | Continuous Improvement & Value Opportunities
Measure | Target | 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019 | Q1 2019 Trend | Initiative | Measure | Savings Goal | Status
Rework | <$10,000 / year / unit | 2714.72 | 3125.68 | 2487.47 | 0 | 0 | 0 | 0 | 1) Vehicle cost & Safety Optimization | #of vehicles & km's driven | $0.13M + 911,748 km's per year reduced HSE exposure | Estimate launch: November 1, 2018
NCR's | <10 / year / operating unit | 7 | 3 | 5 | 2 | 0 | 0 | 0 | 2) 7 x7 Schedule Optimization | Less OT - lower labour cost | Estimated: $0.3M | Being Reviewed: Q4 2018 / Q1 2019
Repair Rate | <3% All Weld Counts | No Data | No Data | 1.284% | 2.461% | 0.885% | #DIV/0! | 0.885% | 3) Scaffolding optimization | Reduce break-in | TBD | In Progress
Total Welds | # of Welds (Actual) | No Data | No Data | 1168 | 1219 | 226 | 0 | 339 | 4) Non-productive KPI tool | Improved value delivery | Based on root non-productive causes | In Progress
Total Repairs | # of Repairs (Actual) | No Data | No Data | 15 | 30 | 2 | 0 | 3 | 5) Huddle Board | Idea Generation & Recognition | Generate ideas to implement | In Progress: See Note below
Packages: Signed off by Quinn/In CNRL Review | Data is "snap-shot" in time as at end of period noted | 313 | 399 | 155 | 196 | 1 | 0 |  | 6) 2018 Fall TA - Mass Orientation/SUV's | Time not invoiced | 10236.42 | Delivered
Packages: In Review by Quinn |  | 27 | 16 | 11 | 59 | 7 | 0
Packages: Completed and Scanned |  | 225 | 304 | 186 | 162 | 3 | 0
Overtime Drivers
- Material & equipment availability/ Operations delays
- Emergent /as found work. Schedule conflicts/ simultaneous operations conflict.
- Inclement weather.
- Manpower shortage. 3 shift cycles.
Canadian Natural Operational Feedback / Updates
- Quinn to confirm Bondstrand certification progress and completion %
- Canadian Natural & Quinn to work together to foster pro-active and accountable approach to continuous improvement for both companies - how can we both re-energize this?
Quinn Natural Operational Feedback / Updates
2018 Turnaround/outage and activity driving labour hours higher than 2017
Larger Turnarounds in both Apr/May and Sep/Oct 2018
Anticipated start of Vehicle HSE initiative: Nov 1, 2018
Key efforts of Quinn/Canadian Natural team focused on:
1) Safe TA executions Q2 and Q3 2018
2) Mechanics, value proposition, and implementation plan for Vehicle Cost and HSE Improvement Initative
3) Overtime clarification currently underway
2016 to '17 spend increase partly due to bi-annual OTSG maintenance
Fall 2018 Turnaround: Personnel time; 1-day SUV not charged
Update if info available
input Feb 2019 info
input Feb 2019 info
$1.1
$0.7
2017 to '18 spend due to turnaround/outage activities

## Input - Safety Data
Quinn - Staff
TRIF and Exposure Hours
| TRIF | Exposure Hours
2015 | 0.62 | 207536
2016 | 0 | 187194
2017-01-01 | 0 | 14632
2017-02-01 | 0 | 14473
2017-03-01 | 0 | 16343
2017-04-01 | 0 | 17532
2017-05-01 | 0 | 19257
2017-06-01 | 0 | 19222
2017-07-01 | 0 | 15712
2017-08-01 | 0 | 17418
2017-09-01 | 0 | 15912
2017-10-01 | 0 | 16122
2017-11-01 | 0 | 14519
2017-12-01 | 0 | 12841
2017 | 0.97 | 193983
2018-01-01 | 0 | 16810
2018-02-01 | 0 | 17110
2018-03-01 | 0 | 19510
2018-04-01 | 0 | 29107
2018-05-01 | 0 | 19571
2018-06-01 | 0 | 19540
2018-07-01 | 8.54 | 21724
2018-08-01 | 0 | 22107
2018-09-01 | 0 | 33943
2018-10-01 | 0 | 28526
2018-11-01 | 0 | 18997
2018-12-01 | 0 | 17522
2018 | 0.83 | 264467
2019-01-01 | 0 | 18969
2019-02-01
Quinn - Sub-contractors
TRIF and Exposure Hours
| TRIF | Exposure Hours
2015 | 0 | 23530
2016 | 0 | 23350
2017-01-01 | 0 | 1855
2017-02-01 | 0 | 1761
2017-03-01 | 0 | 2048
2017-04-01 | 0 | 1980
2017-05-01 | 0 | 1822
2017-06-01 | 0 | 2026
2017-07-01 | 0 | 1485
2017-08-01 | 0 | 1525
2017-09-01 | 0 | 1536
2017-10-01 | 0 | 1822
2017-11-01 | 0 | 1323
2017-12-01 | 0 | 1259
2017 | 0 | 20442
2018-01-01 | 0 | 1985
2018-02-01 | 0 | 1679
2018-03-01 | 0 | 1867
2018-04-01 | 0 | 2913
2018-05-01 | 0 | 1773
2018-06-01 | 0 | 1493
2018-07-01 | 0 | 1682 |  |  | `
2018-08-01 | 0 | 2025
2018-09-01 | 0 | 4832
2018-10-01 | 0 | 3207
2018-11-01 | 0 | 1625
2018-12-01 | 0 | 2132
2018 | 0 | 27213
2019-01-01 | 0 | 1810
2019-02-01
Blue Bold = Inputs
|  | 2015 | 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2017 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2018 | 2019-01-01 | 2019-02-01
Leading | Man-Hours | 231066 | 210544 | 16487 | 16234 | 18391 | 19512 | 21079 | 21248 | 17197 | 18943 | 17448 | 17944 | 15842 | 14100 | 214425 | 18795 | 18789 | 21377 | 32020 | 21344 | 21033 | 23406 | 24132 | 38775 | 31733 | 20266 | 19654 | 291324 | 20779
Leading | Hazard ID's | 843 | 935 | 92 | 119 | 86 | 115 | 99 | 119 | 99 | 106 | 111 | 111 | 113 | 97 | 1267 | 109 | 123 | 126 | 179 | 51 | 121 | 97 | 107 | 178 | 144 | 112 | 67 | 1414 | 117
Leading | Safety Meetings | 15 | 15 | 2 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 15 | 1
Leading | Work Site Inspections | 289 | 265 | 23 | 26 | 21 | 28 | 52 | 28 | 17 | 11 | 39 | 44 | 27 | 20 | 336 | 63 | 16 | 47 | 80 | 23 | 52 | 91 | 42 | 65 | 55 | 21 | 18 | 573 | 33
Leading | Pre-Task Analysis Cards | 7770 | 6373 | 492 | 509 | 450 | 460 | 604 | 581 | 500 | 487 | 526 | 532 | 444 | 397 | 5982 | 439 | 436 | 669 | 850 | 509 | 659 | 581 | 631 | 714 | 763 | 678 | 507 | 7436 | 619
Leading | Pre-job Toolbox Meetings | 1828 | 1606 | 160 | 115 | 115 | 129 | 146 | 300 | 124 | 135 | 209 | 153 | 138 | 105 | 1829 | 178 | 108 | 172 | 209 | 160 | 172 | 179 | 158 | 187 | 228 | 177 | 142 | 2070 | 165
Leading | Behaviour Based Safety Observations | 2243 | 1946 | 177 | 157 | 151 | 152 | 158 | 185 | 154 | 178 | 191 | 169 | 149 | 212 | 2033 | 260 | 250 | 299 | 293 | 152 | 219 | 216 | 226 | 240 | 235 | 218 | 193 | 2801 | 213
Leading | Near Hit/Near miss | 2 | 16 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6 | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
Lagging | TRIF - Quinn Staff (at Period end) | 0.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97 | 0 | 0 | 0 | 0 | 0 | 0 | 8.54 | 0 | 0 | 0 | 0 | 0 | 0.83 | 0
Lagging | TRIF - Subcontractors (at Period end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | Recordable Medical Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Lagging | First Aid | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 7 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 7 | 1
Lagging | Vehicle Incidents | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Lagging | Modified Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lagging | Environmental Events | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1
| Off the Job Injury/Illness | 16 | 17 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | Leave out and if it is important we can bring back in - we left it out of Q3 2017's SRM |  |  | 12 | 3 | 5 | 2 | 1 | 2 | 3 | 0 | 1 | 3 | 2 | 1 | 0 | 23 | 0
Note on B7: Trevan Williams: As at Year end per ComplyWorks
Note on B8: As at year end per ComplyWorks
Note on B21: As at Year End per ComplyWorks
Note on B34: Trevan Williams: As at Year End per ComplyWorks
Note on B45: As at year end per ComplyWorks
Note on B46: As at year end per ComplyWorks
Note on B59: As at year end per ComplyWorks
Note on B72: As at year end per ComplyWorks
Note on C95: Trevan Williams: per ComplyWorks
Note on D95: Trevan Williams: Per ComplyWorks
Note on Q95: Trevan Williams: per ComplyWorks
Note on AD95: Trevan Williams: per ComplyWorks
Note on C96: Trevan Williams: per ComplyWorks
Note on D96: Trevan Williams: per ComplyWorks
Note on Q96: Trevan Williams: per ComplyWorks
Note on AD96: Trevan Williams: per ComplyWorks

## Input - Operational Raw Data
Blue Bold = Inputs
OT Exposure Hours - by Group |  |  | NOTE: These include all Quinn staff and their subcontractors
|  | Maintenance | Turnaround | Maint. Scaffolding | Turnaround Scaffolding | % Overtime |  | Total OT Exposure Hours | Total Exposure Hours
| 2017-10-01 | 317.5 | 1190.5 | 0 | 234 | 9.708% |  | 1742 | 17944
| 2017-11-01 | 260.5 | 305 | 21 | 28 | 3.879% |  | 614.5 | 15842
| 2017-12-01 | 155 | 1000.5 | 0 | 93.5 | 8.858% |  | 1249 | 14100
| 2018-01-01 | 263.5 | 1280 | 417 | 292.5 | 11.99% |  | 2253 | 18795
| 2018-02-01 | 190.5 | 1954.5 | 77.5 | 216.5 | 12.98% |  | 2439 | 18789
| 2018-03-01 | 406.5 | 1362 | 0 | 130.5 | 8.883% |  | 1899 | 21377
| 2018-04-01 | 439.5 | 5081.5 | 165 | 1753.5 | 23.23% |  | 7439.5 | 32020
| 2018-05-01 | 440.5 | 1086.5 | 0 | 938 | 11.55% |  | 2465 | 21344
| 2018-06-01 | 260.5 | 1865 | 59 | 833.5 | 14.35% |  | 3018 | 21033
| 2018-07-01 | 666.5 | 1842 | 17 | 1176.5 | 15.82% |  | 3702 | 23406
| 2018-08-01 | 324.5 | 1433.5 | 0 | 255 | 8.342% |  | 2013 | 24132
| 2018-09-01 | 502.5 | 7871.5 | 733.5 | 2888 | 30.94% |  | 11995.5 | 38775
| 2018-10-01 | 262 | 4752 | 114.5 | 1221 | 20.01% |  | 6349.5 | 31733
| 2018-11-01 | 226.5 | 1241 | 4 | 70.5 | 7.477% |  | 1542 | 20622
| 2018-12-01 | 117.5 | 1899.5 | 3 | 6.5 | 10.31% |  | 2026.5 | 19654
| Full Year 2018 | 4100.5 | 31669 | 1590.5 | 9782 | 16.16% |  | 47142 | 291680
| 2019-01-01 | 74 | 638 | 0 | 90 | 3.86% |  | 802 | 20779
| 2019-02-01 |  |  |  |  | #DIV/0! |  | 0 | 0
Operational Performance - Work Quality
|  |  | 2015 | 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2017 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2018 | 2019-01-01 | 2019-02-01
| Rework | <$10,000 / year / unit | 2714.72 | 3125.68 | 0 | 0 | 300 | 0 | 0 | 1500 | 0 | 687.47 | 0 | 0 | 0 | 0 | 2487.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NCR's | < 10 / year / operating unit | 7 | 3 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Repair Rate | <3% All Weld Counts | No Data | No Data | 0.7353% | 2.21% | 2.105% | 0.6579% | 1.852% | 1.538% | 2.062% | 0% | 1.282% | 0% | 0% | 0% | 1.284% | 1.515% | 5.263% | 0% | 3.268% | 2.941% | 0% | 0% | 0.9009% | 1.325% | 4.571% | 1.111% | 4.918% | 2.461% | 0.885% | #DIV/0!
| Total Welds | # of Welds (Actual) | No Data | No Data | 136 | 181 | 190 | 152 | 54 | 65 | 97 | 100 | 78 | 38 | 35 | 42 | 1168 | 66 | 95 | 111 | 153 | 34 | 50 | 61 | 111 | 151 | 175 | 90 | 122 | 1219 | 226
| Total Repairs | # of Repairs (Actual) | No Data | No Data | 1 | 4 | 4 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 15 | 1 | 5 | 0 | 5 | 1 | 0 | 0 | 1 | 2 | 8 | 1 | 6 | 30 | 2
| Packages: Signed off by Quinn/In CNRL Review | Data is "snap-shot" in time as at end of period noted | 313 | 399 | 4 | 17 | 32 | 53 | 65 | 106 | 144 | 157 | 241 | 162 | 139 | 155 | 155 | 4 | 19 | 27 | 36 | 53 | 50 | 84 | 93 | 133 | 159 | 161 | 196 | 196 | 1
| Packages: In Review by Quinn |  | 27 | 16 | 0 | 0 | 4 | 3 | 4 | 6 | 8 | 22 | 10 | 12 | 12 | 11 | 11 | 0 | 2 | 4 | 11 | 16 | 38 | 38 | 42 | 53 | 50 | 60 | 59 | 59 | 7
| Packages: Completed and Scanned |  | 225 | 304 | 0 | 0 | 0 | 9 | 18 | 33 | 38 | 52 | 84 | 115 | 179 | 186 | 186 | 5 | 19 | 21 | 27 | 27 | 45 | 45 | 58 | 76 | 122 | 154 | 162 | 162 | 3

## Output - Safety & Ops
Exposure Hours
| Staff | Sub
2015 | 207536 | 23530
2016 | 187194 | 23350
2017 | 193983 | 20442
2018 | 264467 | 27213
Jan 2019 | 18969 | 1810
Feb 2019 | 0 | 0
OT Exposure Hours - by Group
NOTE: These include all Quinn staff and their subcontractors
| Maint. | TA | Maint. Scaff. | TA Scaff. | % OT
Q4 2017 | 733 | 2496 | 21 | 355.5 | 7.529%
Q1 2018 | 860.5 | 4596.5 | 494.5 | 639.5 | 11.18%
Q2 2018 | 1140.5 | 8033 | 224 | 3525 | 17.37%
Q3 2018 | 1493.5 | 11147 | 750.5 | 4319.5 | 20.52%
Q4 2018 | 606 | 7892.5 | 121.5 | 1298 | 13.77%
Jan 2019 | 74 | 638 | 0 | 90 | 3.86%
Feb 2019 | 0 | 0 | 0 | 0 | #DIV/0!
2017-10-01 | 317.5 | 1190.5 | 0 | 234 | 9.708%
2017-11-01 | 260.5 | 305 | 21 | 28 | 3.879%
2017-12-01 | 155 | 1000.5 | 0 | 93.5 | 8.858%
2018-01-01 | 263.5 | 1280 | 417 | 292.5 | 11.99%
2018-02-01 | 190.5 | 1954.5 | 77.5 | 216.5 | 12.98%
2018-03-01 | 406.5 | 1362 | 0 | 130.5 | 8.883%
2018-04-01 | 439.5 | 5081.5 | 165 | 1753.5 | 23.23%
2018-05-01 | 440.5 | 1086.5 | 0 | 938 | 11.55%
2018-06-01 | 260.5 | 1865 | 59 | 833.5 | 14.35%
2018-07-01 | 666.5 | 1842 | 17 | 1176.5 | 15.82%
2018-08-01 | 324.5 | 1433.5 | 0 | 255 | 8.342%
2018-09-01 | 502.5 | 7871.5 | 733.5 | 2888 | 30.94%
2018-10-01 | 262 | 4752 | 114.5 | 1221 | 20.01%
2018-11-01 | 226.5 | 1241 | 4 | 70.5 | 7.477%
2018-12-01 | 117.5 | 1899.5 | 3 | 6.5 | 10.31%
2019-01-01 | 74 | 638 | 0 | 90 | 3.86%
2019-02-01 | 0 | 0 | 0 | 0 | #DIV/0!
All up OT Exposure Hours
can leave this chart out for now
|  | Exposure Hours: All Staff + Sub | OT only: All Staff + Sub
| 2015 | 231066 | 18760
| 2016 | 210544 | 29652
| 2017 | 214425 | 28993
| 2018 | 291680 | 47142
| Jan 2019 | 20779 | 802
| Feb 2019 | 0 | 0
| Q4 2018 F-Cast | #REF! | #REF!
| 2018 F-Cast | #REF! | #REF!
Safety Stats
Leading Indicator | 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019
Man-Hours | 231066 | 210544 | 214425 | 291324 | 20779 | 0
Hazard ID's | 843 | 935 | 1267 | 1414 | 117 | 0
Safety Meetings | 15 | 15 | 18 | 15 | 1 | 0
Work Site Inspections | 289 | 265 | 336 | 573 | 33 | 0
Pre-Task Analysis Cards | 7770 | 6373 | 5982 | 7436 | 619 | 0
Pre-job Toolbox Meetings | 1828 | 1606 | 1829 | 2070 | 165 | 0
BBSO | 2243 | 1946 | 2033 | 2801 | 213 | 0
Near Hit/Near miss | 2 | 16 | 6 | 6 | 0 | 0
Lagging Indicator | 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019
TRIF - Quinn Staff | 0.62 | 0 | 0.97 | 0.83 | 0 | 0
TRIF - Subcontractors | 0 | 0 | 0 | 0 | 0 | 0
Lost Time Incidents | 0 | 0 | 0 | 0 | 0 | 0
Recordable Medical Aid | 0 | 0 | 0 | 1 | 0 | 0
First Aid | 3 | 2 | 7 | 7 | 1 | 0
Vehicle Incidents | 1 | 2 | 6 | 2 | 0 | 0
Modified Work | 0 | 0 | 0 | 0 | 0 | 0
Environmental Events | 2 | 1 | 1 | 2 | 1 | 0
ComplyWork Status = | Acceptable
Operational Performance
Measure | Target | 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019 | Q1 2019 Trend
Rework | <$10,000 / year / unit | 2714.72 | 3125.68 | 2487.47 | 0 | 0 | 0 | 0
NCR's | <10 / year / operating unit | 7 | 3 | 5 | 2 | 0 | 0 | 0
Repair Rate | <3% All Weld Counts | No Data | No Data | 1.284% | 2.461% | 0.885% | #DIV/0! | 0.885%
Total Welds | # of Welds (Actual) | No Data | No Data | 1168 | 1219 | 226 | 0 | 339
Total Repairs | # of Repairs (Actual) | No Data | No Data | 15 | 30 | 2 | 0 | 3
Packages: Signed off by Quinn/In CNRL Review | TBD | 313 | 399 | 155 | 196 | 1 | 0
Packages: In Review by Quinn | TBD | 27 | 16 | 11 | 59 | 7 | 0
Packages: Completed and Scanned | TBD | 225 | 304 | 186 | 162 | 3 | 0

## Cost Savings & Avoidance
Blue Bold = Inputs
|  | Cost Avoidance | Cost Savings | Total | Description
| 2017-09-01 | 24000 | 0 | 24000 | Skid Steer rental - details in cost savings log
| 2017-10-01 | 0 | 0 | 0
| 2017-11-01 | 0 | 0 | 0
| 2017-12-01 | 0 | 0 | 0
| 2017 | 24000 | 0 | 24000
| 2018-01-01 | 0 | 0 | 0
| 2018-02-01 | 0 | 0 | 0
| 2018-03-01 | 0 | 0 | 0
| 2018-04-01 | 0 | 0 | 0
| 2018-05-01 | 0 | 0 | 0
| 2018-06-01 | 0 | 0 | 0
| 2018-07-01 | 0 | 0 | 0
| 2018-08-01 | 0 | 0 | 0
| 2018-09-01 | 10236.42 | 0 | 10236.42
| 2018-10-01 | 0 | 0 | 0
| 2018-11-01 | 0 | 128676 | 128676
Outputs - Value Improvement
|  | Cost Avoidance | Cost Savings
| 2017 | 24000 | 0
| 2018-01-01 | 0 | 0
| 2018-02-01 | 0 | 0
| 2018-03-01 | 0 | 0
| 2018-04-01 | 0 | 0
| 2018-05-01 | 0 | 0
| 2018-06-01 | 0 | 0
| 2018-07-01 | 0 | 0
| 2018-08-01 | 0 | 0
| 2018-09-01 | 10236.42 | 0
| 2018-10-01 | 0 | 0
| 2018-11-01 | 0 | 128676
- Non Productive KPI will be tool to be used for identifying furture opportunities
- Goal: Annual value Improvement of 10% annual spend
Note on D18: Related to Fall 2018 TA outage:$10,236.42 Per email sent from Joe McGuire to Trevan Williams on Oct 12, 2018 with subject line "RE: Quinn - OT review / Contract draft" Mass Orientation (no site forman, site coordinator, recruiter time paid). 1 day of SUV's Site Wide BBQ

## Spend Chart
| 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019
Operations | 11747566 | 7578731 | 10749239.81 | 8663752 | 642257 | 365925
Wells Servicing | 2342418 | 2780334 | 1428636.48 | 4307384 | 296172.73 | 99682
Turnaround | 2801087 | 3586352 | 3234566.46 | 5938895 | 192913 | 212382
| 16891071 | 13945417 | 15412442.75 | 18910031 | 1131342.73 | 677989
| 2015 | 2016 | 2017 | 2018 | Jan 2019 | Feb 2019
Total | 16891071 | 13945417 | 15412442.75 | 18910031 | 1131342.73 | 677989

## 2019 - Feb - Wolf Lake
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Feb 1, 2019 to Feb 28, 2019
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 11, 2019 - 10:00am
2019
OBJECT_NAME | GL Code | GL Sub Desc | Vendor Number | Vendor Name | 560 Wolf Lake
3200 Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 25272 | Quinn Contracting Ltd. | 47.89
3200 Well Equip/Tie-In Costs | 3200-194 | Const/Super/Inspect Mgt | 25272 | Quinn Contracting Ltd. | 289.05
3210 Electrical & Instrumentation | 3210-410 | E&I Labour | 25272 | Quinn Contracting Ltd. | 2245.04
3210 Electrical & Instrumentation | 3210-415 | Instrument Materials | 25272 | Quinn Contracting Ltd. | 2913.62
3210 Mechanical | 3210-320 | Pipe/Valves & Fittings | 25272 | Quinn Contracting Ltd. | 185.81
3210 Mechanical | 3210-325 | Mechanical Labour | 25272 | Quinn Contracting Ltd. | 47983.06
3210 Mechanical | 3210-335 | Insulation, Painting, Coating | 25272 | Quinn Contracting Ltd. | 44747.01
3210 Mechanical | 3210-340 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 18.04
3210 Office / Administration | 3210-610 | Inspect/Supr/Const Supp | 25272 | Quinn Contracting Ltd. | 1252.84
99682.36
3210 Others | 3210-710 | Plant / Battery Turnaround | 25272 | Quinn Contracting Ltd. | 212381.86
6010 Parts & Supplies | 6010-105 | Parts & Supplies | 25272 | Quinn Contracting Ltd. | 1686.93
6020 Labour | 6020-115 | Contract Operations | 25272 | Quinn Contracting Ltd. | 2329.36
6020 Labour | 6020-120 | Engineering,Superv.,Consulting | 25272 | Quinn Contracting Ltd.
6030 Other Labour | 6030-130 | Vehicle Costs | 25272 | Quinn Contracting Ltd.
6050 Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd. | 353937.89
6050 Repairs & Maintenance | 6050-110 | Pipeline Patrol | 25272 | Quinn Contracting Ltd. | 4177.67
6100 Equipment Rental | 6100-105 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 2033.92
6110 Instrumentation | 6110-105 | Instrumentation / Electrical | 25272 | Quinn Contracting Ltd. | 422.81
6110 Instrumentation | 6110-110 | Instrumentation - Labour | 25272 | Quinn Contracting Ltd. | 1336.68
365925.26
Grand Total | Total | Total | Total | Total | 677989.48

## 2019 - Jan - Wolf Lake
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2019 to Jan 31, 2019
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 11, 2019 - 10:00am
2019
OBJECT_NAME | GL Code | GL Sub Desc | Vendor Number | Vendor Name | 560 Wolf Lake
3200 Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 25272 | Quinn Contracting Ltd. | 2962.02
3200 Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 25272 | Quinn Contracting Ltd. | 53.86
3200 Well Equip/Tie-In | 3200-335 | Non-Operated Equipment&Labour | 25272 | Quinn Contracting Ltd. | 137
3210 Electrical & Instrumentation | 3210-410 | E&I Labour | 25272 | Quinn Contracting Ltd. | 367.39
3210 Mechanical | 3210-310 | Foundatn/Piling Mat&Lbr | 25272 | Quinn Contracting Ltd. | 183.25
3210 Mechanical | 3210-325 | Mechanical Labour | 25272 | Quinn Contracting Ltd. | 283368.59
3210 Mechanical | 3210-340 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 2944.21
3210 Office / Administration | 3210-605 | Eng. Reports & Studies | 25272 | Quinn Contracting Ltd. | 1719.18
3210 Office / Administration | 3210-610 | Inspect/Supr/Const Supp | 25272 | Quinn Contracting Ltd. | 4437.23
296172.73
3210 Others | 3210-710 | Plant / Battery Turnaround | 25272 | Quinn Contracting Ltd. | 192913.02
6010 Parts & Supplies | 6010-105 | Parts & Supplies | 25272 | Quinn Contracting Ltd. | 2913.84
6020 Labour | 6020-120 | Engineering,Superv.,Consulting | 25272 | Quinn Contracting Ltd.
6030 Other Labour | 6030-130 | Vehicle Costs | 25272 | Quinn Contracting Ltd. | 361.49
6050 Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd. | 625931.85
6050 Repairs & Maintenance | 6050-110 | Pipeline Patrol | 25272 | Quinn Contracting Ltd. | 777.85
6050 Repairs & Maintenance | 6050-115 | R&M - Labour | 25272 | Quinn Contracting Ltd. | 298.65
6100 Equipment Rental | 6100-105 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 10158.54
6110 Instrumentation | 6110-105 | Instrumentation / Electrical | 25272 | Quinn Contracting Ltd. | 1691.24
6110 Instrumentation | 6110-110 | Instrumentation - Labour | 25272 | Quinn Contracting Ltd. | 123.63
6740 M/C-Repairs & Maintenance | 6740-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd.
642257.09
Grand Total | Total | Total | Total | Total | 1131342.84

## 2018 - Wolf Lake
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2018 to Dec 31, 2018
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 11, 2019 - 10:00am
2018
OBJECT_NAME | GL Code | GL Sub Desc | Vendor Number | Vendor Name | 560 Wolf Lake
3110 ICC-Rig Operations | 3110-530 | ICC-Equipment Rentals | 25272 | Quinn Contracting Ltd. | 1449.26
3200 Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 25272 | Quinn Contracting Ltd. | 20302.75
3200 Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 25272 | Quinn Contracting Ltd. | 190162.9
3200 Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 25272 | Quinn Contracting Ltd. | 30566.25
3200 Well Equip/Tie-In | 3200-325 | Miscellaneous | 25272 | Quinn Contracting Ltd. | 2541.27
3200 Well Equip/Tie-In | 3200-335 | Non-Operated Equipment&Labour | 25272 | Quinn Contracting Ltd. | 645.4
3200 Well Equip/Tie-In Costs | 3200-196 | Equipment Rentals | 25272 | Quinn Contracting Ltd. | 6501.56
3210 Electrical & Instrumentation | 3210-410 | E&I Labour | 25272 | Quinn Contracting Ltd. | 13043.65
3210 Electrical & Instrumentation | 3210-415 | Instrument Materials | 25272 | Quinn Contracting Ltd. | 1263.49
3210 Electrical & Instrumentation | 3210-425 | Control Systems MTL&LBR | 25272 | Quinn Contracting Ltd. | 71042.65
3210 Mechanical | 3210-310 | Foundatn/Piling Mat&Lbr | 25272 | Quinn Contracting Ltd. | 1440.88
3210 Mechanical | 3210-315 | Steel Works and Supply | 25272 | Quinn Contracting Ltd. | 2463.2
3210 Mechanical | 3210-320 | Pipe/Valves & Fittings | 25272 | Quinn Contracting Ltd. | 38750.75
3210 Mechanical | 3210-325 | Mechanical Labour | 25272 | Quinn Contracting Ltd. | 3844834.58
3210 Mechanical | 3210-330 | Equipment Setting | 25272 | Quinn Contracting Ltd. | 5638.16
3210 Mechanical | 3210-335 | Insulation, Painting, Coating | 25272 | Quinn Contracting Ltd. | 18729.84
3210 Mechanical | 3210-340 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 18067.24
3210 Mechanical | 3210-350 | Non Destructive Testing | 25272 | Quinn Contracting Ltd. | 618.37
3210 Office / Administration | 3210-610 | Inspect/Supr/Const Supp | 25272 | Quinn Contracting Ltd. | 39002.1
3210 Office / Administration | 3210-615 | Safety / Ambulance | 25272 | Quinn Contracting Ltd. | 319.72
4307384.02
3210 Others | 3210-710 | Plant / Battery Turnaround | 25272 | Quinn Contracting Ltd. | 5938895.03
6010 Parts & Supplies | 6010-105 | Parts & Supplies | 25272 | Quinn Contracting Ltd. | 8604.98
6020 Labour | 6020-115 | Contract Operations | 25272 | Quinn Contracting Ltd. | 72554.98
6020 Labour | 6020-120 | Engineering,Superv.,Consulting | 25272 | Quinn Contracting Ltd.
6020 Labour | 6020-125 | Camp Costs | 25272 | Quinn Contracting Ltd.
6030 Other Labour | 6030-130 | Vehicle Costs | 25272 | Quinn Contracting Ltd. | 1204.05
6040 Lease & Road Maintenance | 6040-105 | Lease & Road Maintenance | 25272 | Quinn Contracting Ltd. | 646.12
6050 Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd. | 8532851.79
6050 Repairs & Maintenance | 6050-110 | Pipeline Patrol | 25272 | Quinn Contracting Ltd. | 6649.83
6050 Repairs & Maintenance | 6050-115 | R&M - Labour | 25272 | Quinn Contracting Ltd. | 1420.12
6070 Fuel | 6070-105 | Fuel | 25272 | Quinn Contracting Ltd. | 61.12
6100 Equipment Rental | 6100-105 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 3606.98
6110 Instrumentation | 6110-105 | Instrumentation / Electrical | 25272 | Quinn Contracting Ltd. | 2071.71
6110 Instrumentation | 6110-110 | Instrumentation - Labour | 25272 | Quinn Contracting Ltd. | 34080.58
6740 M/C-Repairs & Maintenance | 6740-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd.
6740 M/C-Repairs & Maintenance | 6740-140 | R&M-Miscellaneous | 25272 | Quinn Contracting Ltd.
8663752.26
Grand Total | Total | Total | Total | Total | 18910031.31

## 2018 Jan-Sep YTD - Wolf Lake (hidden)
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2018 to Sep 30, 2018
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: TBD
[5 empty] | Grand Total | 2018 | 2018 | 2018 | 2018 | 2018 | 2018
OBJECT_NAME | GL Code | GL Sub Desc | Vendor Number | Vendor Name | Total | 518 Edson | 545 Bonnyville | 560 Wolf Lake | 565 Kirby | 650 Non Core Canada | 665 Midstream
3110 ICC-Rig Operations | 3110-530 | ICC-Equipment Rentals | 25272 | Quinn Contracting Ltd. | 1449.26 |  |  | 1449.26
3200 Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 25272 | Quinn Contracting Ltd. | 20188.26 |  |  | 20188.26
3200 Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 25272 | Quinn Contracting Ltd. | 12371.69 |  |  | 12371.69
3200 Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 25272 | Quinn Contracting Ltd. | 3040.78 |  |  | 3040.78
3200 Well Equip/Tie-In | 3200-325 | Miscellaneous | 25272 | Quinn Contracting Ltd. | 2541.27 |  |  | 2541.27
3200 Well Equip/Tie-In | 3200-335 | Non-Operated Equipment&Labour | 25272 | Quinn Contracting Ltd. | 382.94 |  |  | 382.94
3200 Well Equip/Tie-In Costs | 3200-196 | Equipment Rentals | 25272 | Quinn Contracting Ltd. | 161.04 |  |  | 161.04
3210 Electrical & Instrumentation | 3210-410 | E&I Labour | 25272 | Quinn Contracting Ltd. | 10477.49 |  |  | 10477.49
3210 Mechanical | 3210-310 | Foundatn/Piling Mat&Lbr | 25272 | Quinn Contracting Ltd. | 1440.88 |  |  | 1440.88
3210 Mechanical | 3210-320 | Pipe/Valves & Fittings | 25272 | Quinn Contracting Ltd. | 3166.74 |  |  | 3166.74
3210 Mechanical | 3210-325 | Mechanical Labour | 25272 | Quinn Contracting Ltd. | 1548750.4 |  |  | 1532859.39 | 15891.01
3210 Mechanical | 3210-335 | Insulation, Painting, Coating | 25272 | Quinn Contracting Ltd. | 16874.86 |  |  | 16874.86
3210 Mechanical | 3210-340 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 7395.53 |  |  | 7395.53
3210 Office / Administration | 3210-610 | Inspect/Supr/Const Supp | 25272 | Quinn Contracting Ltd. | 880.69 |  |  | 880.69
1629121.83
3210 Others | 3210-710 | Plant / Battery Turnaround | 25272 | Quinn Contracting Ltd. | 3492004.37 |  |  | 3492004.37
6010 Parts & Supplies | 6010-105 | Parts & Supplies | 25272 | Quinn Contracting Ltd. | 3707.6 |  |  | 3707.6
6020 Labour | 6020-115 | Contract Operations | 25272 | Quinn Contracting Ltd. | 43536.95 |  |  | 43536.95
6020 Labour | 6020-120 | Engineering,Superv.,Consulting | 25272 | Quinn Contracting Ltd. | 72411.13 |  |  |  |  | 72411.13
6020 Labour | 6020-125 | Camp Costs | 25272 | Quinn Contracting Ltd. | 3603.5 |  |  |  |  | 3603.5
6030 Other Labour | 6030-130 | Vehicle Costs | 25272 | Quinn Contracting Ltd. | 17126.31 |  |  | 584.73 |  | 16541.58
6050 Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd. | 4668931.18 | 64.04 | 5062.34 | 4656858.45 | 6946.35
6050 Repairs & Maintenance | 6050-110 | Pipeline Patrol | 25272 | Quinn Contracting Ltd. | 5741.15 |  |  | 5741.15
6050 Repairs & Maintenance | 6050-115 | R&M - Labour | 25272 | Quinn Contracting Ltd. | 1420.12 |  |  | 1420.12
6100 Equipment Rental | 6100-105 | Equipment Rental | 25272 | Quinn Contracting Ltd. | 3606.98 |  |  | 3606.98
6110 Instrumentation | 6110-105 | Instrumentation / Electrical | 25272 | Quinn Contracting Ltd. | 904.57 |  |  | 904.57
6110 Instrumentation | 6110-110 | Instrumentation - Labour | 25272 | Quinn Contracting Ltd. | 30015.34 |  |  | 30015.34
6740 M/C-Repairs & Maintenance | 6740-105 | Repairs & Maintenance | 25272 | Quinn Contracting Ltd. | 6933.01 | [5 empty] | 6933.01
4857937.84
Grand Total | Total | Total | Total | Total | 9979064.04 | 64.04 | 5062.34 | 9851611.08 | 22837.36 | 92556.21 | 6933.01

## 2017 - Wolf Lake
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2017 to Dec 31, 2017
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 9, 2018 - 11:00am
2017
Vendor Number | Vendor Name | GL Code | GL Sub Desc | 560 Wolf Lake | OBJECT_NAME
25272 | Quinn Contracting Ltd. | 3110-650 | ICC-Production Testing | 5573.29 | 3110 ICC-Completion Services
25272 | Quinn Contracting Ltd. | 3110-660 | ICC-Treating / Stimulation | 4873.28 | 3110 ICC-Completion Services
25272 | Quinn Contracting Ltd. | 3110-205 | ICC-Lease & Road Restoration | 336.6 | 3110 ICC-Lease, Road, Access Cost
25272 | Quinn Contracting Ltd. | 3110-405 | ICC-Service Rig & Rig Move | 2337.78 | 3110 ICC-Rig Costs
25272 | Quinn Contracting Ltd. | 3200-220 | Equipment Installation&Setting | 261923.83 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-235 | Pipe Fab & Install | 69186.85 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-280 | Pipe, Valves & Fittings | 901.09 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-285 | P/L Test/Cleaning/Inspc | 85914.36 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-325 | Miscellaneous | 5839.68 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-335 | Non-Operated Equipment&Labour | 1512.22 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-199 | Non-Destructive Testing | 696.92 | 3200 Well Equip/Tie-In Costs
25272 | Quinn Contracting Ltd. | 3210-410 | E&I Labour | 16458.46 | 3210 Electrical & Instrumentation
25272 | Quinn Contracting Ltd. | 3210-425 | Control Systems MTL&LBR | 2513 | 3210 Electrical & Instrumentation
25272 | Quinn Contracting Ltd. | 3210-505 | Catalyst / Chemical | 2436.85 | 3210 Field Cost
25272 | Quinn Contracting Ltd. | 3210-515 | Start-Up / Commissioning | 3511.37 | 3210 Field Cost
25272 | Quinn Contracting Ltd. | 3210-320 | Pipe/Valves & Fittings | 4535.52 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-325 | Mechanical Labour | 882119.23 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-335 | Insulation, Painting, Coating | 3483.99 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-340 | Equipment Rental | 2528.3 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-350 | Non Destructive Testing | 3050.68 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-610 | Inspect/Supr/Const Supp | 68903.18 | 3210 Office / Administration
1428636.48
25272 | Quinn Contracting Ltd. | 3210-710 | Plant / Battery Turnaround | 3234566.46 | 3210 Others
25272 | Quinn Contracting Ltd. | 6010-105 | Parts & Supplies | 45794.36 | 6010 Parts & Supplies
25272 | Quinn Contracting Ltd. | 6010-110 | Lubricants | 6344.36 | 6010 Parts & Supplies
25272 | Quinn Contracting Ltd. | 6020-115 | Contract Operations | 64087.08 | 6020 Labour
25272 | Quinn Contracting Ltd. | 6020-120 | Engineering,Superv.,Consulting | 668.09 | 6020 Labour
25272 | Quinn Contracting Ltd. | 6030-130 | Vehicle Costs | 2752.17 | 6030 Other Labour
25272 | Quinn Contracting Ltd. | 6050-105 | Repairs & Maintenance | 10567777.88 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6050-110 | Pipeline Patrol | 16285.34 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6100-105 | Equipment Rental | 2311.97 | 6100 Equipment Rental
25272 | Quinn Contracting Ltd. | 6110-105 | Instrumentation / Electrical | 2214.14 | 6110 Instrumentation
25272 | Quinn Contracting Ltd. | 6110-110 | Instrumentation - Labour | 41004.42 | 6110 Instrumentation
10749239.81
Total | Total | Total | Total | 15412442.75 | Grand Total

## 2016 - Wolf Lake
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2016
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 315421.35
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-220 | Equipment Installation&Setting | 1348646.13
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-235 | Pipe Fab & Install | 25834.25
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-285 | P/L Test/Cleaning/Inspc | 773.68
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-325 | Miscellaneous | 702.53
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-196 | Equipment Rentals | 5029.48
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-199 | Non-Destructive Testing | 6996.61
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 5523.25
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-415 | Instrument Materials | 854.94
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-425 | Control Systems MTL&LBR | 1347.34
25272 | Quinn Contracting Ltd. | 3210 | Major Controllable Equipment | 3210-230 | Building Over 200 Sq. Ft. | 26595.47
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 5597.06
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 1036484.77
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-350 | Non Destructive Testing | 398.92
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-905 | Overhead | 627.72
2780833.5
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 3586362.37
25272 | Quinn Contracting Ltd. | 6010 | Parts & Supplies | 6010-105 | Parts & Supplies | 3014.7
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 84063
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 1409.21
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 7445408.92
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 6073.76
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-115 | R&M - Labour | 216.76
25272 | Quinn Contracting Ltd. | 6070 | Fuel | 6070-105 | Fuel | 413.81
25272 | Quinn Contracting Ltd. | 6100 | Equipment Rental | 6100-105 | Equipment Rental | 7606.8
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 3031.6
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 26478.93
25272 | Quinn Contracting Ltd. | 6180 | Processing Fees | 6180-115 | Fluid Disposal | 313.86
7578031.35

## 2015 - Wolf Lake
Vendor Num | Vendor Name | GL_OBJ | GL_OBJ_DESC | GL Code | GL Sub Desc | 2015
25272 | Quinn Contracting Ltd. | 3110 | ICC-Rig Costs | 3110-405 | ICC-Service Rig & Rig Move | 1100072.08
25272 | Quinn Contracting Ltd. | 3130 | Environmental Costs | 3130-145 | Equipment | 22991.07
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In | 3200-245 | Mobilization / Unit Lay | 1370.95
25272 | Quinn Contracting Ltd. | 3200 | Well Equip/Tie-In Costs | 3200-194 | Const/Super/Inspect Mgt | 112.86
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-410 | E&I Labour | 24965.16
25272 | Quinn Contracting Ltd. | 3210 | Electrical & Instrumentation | 3210-415 | Instrument Materials | 5737.42
25272 | Quinn Contracting Ltd. | 3210 | Major Controllable Equipment | 3210-230 | Building Over 200 Sq. Ft. | 10052.57
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-305 | Earthworks/Fencing/Sign | 282.68
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-310 | Foundatn/Piling Mat&Lbr | 6609.05
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-320 | Pipe/Valves & Fittings | 15061.17
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-325 | Mechanical Labour | 1100971.53
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-335 | Insulation, Painting, Coating | 41846.96
25272 | Quinn Contracting Ltd. | 3210 | Mechanical | 3210-350 | Non Destructive Testing | 515.53
25272 | Quinn Contracting Ltd. | 3210 | Office / Administration | 3210-605 | Eng. Reports & Studies | 11829.3
2342418.33
25272 | Quinn Contracting Ltd. | 3210 | Others | 3210-710 | Plant / Battery Turnaround | 2801087.02
25272 | Quinn Contracting Ltd. | 6020 | Labour | 6020-115 | Contract Operations | 71111.72
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-105 | Salary Admin | 12893.33
25272 | Quinn Contracting Ltd. | 6030 | Other Labour | 6030-130 | Vehicle Costs | 82.01
25272 | Quinn Contracting Ltd. | 6040 | Lease & Road Maintenance | 6040-105 | Lease & Road Maintenance | 668.55
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-105 | Repairs & Maintenance | 11608051.04
25272 | Quinn Contracting Ltd. | 6050 | Repairs & Maintenance | 6050-110 | Pipeline Patrol | 3742.01
25272 | Quinn Contracting Ltd. | 6070 | Fuel | 6070-105 | Fuel | 1018.89
25272 | Quinn Contracting Ltd. | 6080 | Trucking | 6080-110 | Trucking - Produced Water | 997.47
25272 | Quinn Contracting Ltd. | 6100 | Equipment Rental | 6100-105 | Equipment Rental | 34770.4
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-105 | Instrumentation / Electrical | 330.96
25272 | Quinn Contracting Ltd. | 6110 | Instrumentation | 6110-110 | Instrumentation - Labour | 6008.37
25272 | Quinn Contracting Ltd. | 6130 | Downhole Services | 6130-130 | Steamer/Chem Wash/Vacuum Truck | 3159.51
25272 | Quinn Contracting Ltd. | 6180 | Processing Fees | 6180-115 | Fluid Disposal | 4731.87
11747566.13

## 2018 Jan-Feb YTD - Wolf Lake (hidden)
Quinn Spend - Wolf Lake
Tableau report: Vendor Spend by G/L Field Office
All Field Offices Spend - Wolf Lake Field Office
Time-frame: Jan 1, 2018 to Feb 28, 2018
All GL Spend - Have removed all $0 and negative $ values
Well Servicing: All 3000-series GL Code's except 3210-710
Turnaround: GL Code 3210-710 Plant / Battery Turnaround
Operations: All 6000-series GL Code's
Pulled from Tableau: Mar 9, 2018 - 11:00am
2018
Vendor Number | Vendor Name | GL Code | GL Sub Desc | 560 Wolf Lake | OBJECT_NAME
25272 | Quinn Contracting Ltd. | 3200-220 | Equipment Installation&Setting | 29.78 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-235 | Pipe Fab & Install | 7343.4 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-285 | P/L Test/Cleaning/Inspc | 501.94 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3200-325 | Miscellaneous | 2541.27 | 3200 Well Equip/Tie-In
25272 | Quinn Contracting Ltd. | 3210-410 | E&I Labour | 7874.61 | 3210 Electrical & Instrumentation
25272 | Quinn Contracting Ltd. | 3210-310 | Foundatn/Piling Mat&Lbr | 1192.47 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-325 | Mechanical Labour | 93586.96 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-335 | Insulation, Painting, Coating | 1920.8 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-340 | Equipment Rental | 562.87 | 3210 Mechanical
25272 | Quinn Contracting Ltd. | 3210-610 | Inspect/Supr/Const Supp | 880.69 | 3210 Office / Administration
116434.79
25272 | Quinn Contracting Ltd. | 3210-710 | Plant / Battery Turnaround | 694013.36 | 3210 Others
25272 | Quinn Contracting Ltd. | 6010-105 | Parts & Supplies | 340.54 | 6010 Parts & Supplies
25272 | Quinn Contracting Ltd. | 6020-115 | Contract Operations | 4967.02 | 6020 Labour
25272 | Quinn Contracting Ltd. | 6050-105 | Repairs & Maintenance | 897839 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6050-110 | Pipeline Patrol | 891.3 | 6050 Repairs & Maintenance
25272 | Quinn Contracting Ltd. | 6100-105 | Equipment Rental | 640.45 | 6100 Equipment Rental
25272 | Quinn Contracting Ltd. | 6110-105 | Instrumentation / Electrical | 597.51 | 6110 Instrumentation
25272 | Quinn Contracting Ltd. | 6110-110 | Instrumentation - Labour | 2335.17 | 6110 Instrumentation
907610.99
Total | Total | Total | Total | 1718059.14 | Grand Total