## Report
[11 empty] | Slicers for Safety Reports | Slicers for QC Reports
Safety Stats - Leading
| Key Notes Leading |  | 2016 | 2017 | 2018 | 2019 | 2020 | Grand Total
| ~26% reduction in hours between YTD 2019Q3 and 2020Q3, along with ~70% reduction on OT exposure in same time frame. | 1. Total Exposure Hours | 210544 | 214925 | 288661 | 248407 | 140327.75 | 1102864.75
|  | 2. Safety Meetings | 14 | 23 | 15 | 20 | 12 | 84
|  | 3. Work Site Inspections | 244 | 336 | 573 | 253 | 120 | 1526
|  | 4. FLRA Cards | 5971 | 5982 | 7424 | 7058 | 3445 | 29880
|  | 5. Toolbox Meetings | 1427 | 1826 | 2063 | 1908 | 1253 | 8477
|  | 6. BBS Cards | 1658 | 2033 | 2740 | 2099 | 1249 | 9779
|  | 7. Near Miss Incidents | 15 | 5 | 6 | 1 | 2 | 29
Safety Stats - Lagging
| Key Notes Lagging |  | 2016 | 2017 | 2018 | 2019 | 2020 | Grand Total
| TRIF calculations only represent CNRL PAW exposure. | 1. TRIF | 0 | 0 | 0.69285 | 1.6103 | 4.2757 | 1.0881
|  | 2. Lost Time Incident | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Medical Aid | 0 | 0 | 1 | 2 | 3 | 6
|  | 4. First Aid | 3 | 7 | 7 | 9 | 0 | 26
|  | 5. Vehicle Incident | 21 | 18 | 4 | 9 | 4 | 56
|  | 6. Modified Work Case | 0 | 0 | 0 | 1 | 0 | 1
|  | 7. Environmental Event | 0 | 1 | 2 | 2 | 0 | 5
Quality Stats
| Target |  | 2018 | 2019 | 2020 |  |  | Grand Total
[5 empty] | Q1 | Q2 | Q3
| < 10/year / op. unit | 1. NCRs | 2 | 0 | 0 | 0 | 0 | 2
|  | 2. Total Welds | 2866 | 3983 | 533 | 198 | 210 | 7790
|  | 3. Total Butt Welds | 1157 | 1593 | 204 | 161 | 135 | 3250
|  | 4. Total Butt Weld Repairs | 30 | 36 | 3 | 3 | 0 | 72
| < 3% All Weld Counts | 5. Total Butt Weld Repair Rate | 2.593% | 2.26% | 1.471% | 1.863% | 0% | 2.215%
| Snapshot at end of period | 6. Max of Packages: Signed off by Quinn / in CNRL Review | 196 | 531 | 425 | 256 | 269 | 531
| Snapshot at end of period | 7. Max of Packages: In Review by Quinn | 60 | 110 | 112 | 146 | 147 | 147
| Yearly running total | 8. Max of Packages: Completed and Scanned | 162 | 278 | 148 | 235 | 328 | 328
Continuous Improvement & Value Opportunities | [8 empty] | General Notes / Discussion Points
| 1. Automating timesheet process: Validating Work Order on timesheet prior to entry into payroll. | [8 empty] | 1. 2020 is trending significantly lower for hours compared to RFP basis. (Forecasting ~55% of 323k hours basis)
| 2. Management of invoicing process: Complete revamp, significant reduction in rework, increase in accuracy. | [8 empty] | 2. Indigenous engagement is low. $1,185 spend at Astec for training, only one employee self-identified as Indigenous.
| 3. Timesheet errors reduced from over a dozen per day to less than 5/week. | [8 empty] | Re-polling may increase numbers.
| 4. Audit of old timesheet & invoicing process (Nov 2019 - April 2020) ongoing. | [8 empty] | 3. Meeting with CLFN - outstanding
| 5. Site fuel management - looking for path forward from CNRL on requirements. | [8 empty] | 4. No major opportunities for Indigenous 3rd party spend. Seven Lakes has been engaged for waste management,
| 6. Truck fleet reduction - Quinn balancing requirements to move people to/from site and COVID restrictions. | [8 empty] | reached out to Ironhorse Janitorial for engagement.
| 7. Women In Construction summary: 18% Female workforce, with 38% in JM/FM/leadership roles (numbers for CNRL PAW only) | [8 empty] | 5. Invoice process still seeing some snags - Quinn working to align with CNRL processes (i.e. T/A WOs)
| 8. Engaging CLFN companies for future involvement: Seven Lakes Waste Management, Iron Horse Janitorial, Jiffy Lube | [8 empty] | 6. Cost recovery on Millwright tools, scaffold, both due to reduced hours
| 9. Graham is actively engaged with Women Building Futures (WBF) to provide future opportunities for women in construction | [8 empty] | 7. Site administrator costs - Quinn overhead or CNRL?
| 10. Registered Apprenticeship Program (RAP) - restarting in 2021 with a focus on Indigenous community outreach | [8 empty] | 8. Resolution of cost disagreements (ongoing issue at weekly meetings)
9. QC Level 2 requirement for NDE interpretation - as per AB-518 Section 3.3.12
10. ~25% of all vehicle incidents from 2013 to 2017 are due to wildlife interactions.
11. Spend profile based on Maximo data. Spend shown will have a 1-2 month delay from incurred hours data.
12. New-hire counts for 2020: Q1: 15 / Q2: 1 / Q3: 4
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
YTD Q3 spend down by 41% from 2019 to 2020 in Maximo.
YTD Q3 hours down by 26% from 2019 to 2020.
Note on N1: Joel Brochu: Expand above (click on [+] icon) if expanding pivot table reports in columns B-H

## Pivot Tables
Note: The Pivot Tables on this worksheet feed the Pivot Charts on the Report worksheet. The year.quarter slicer is linked to both Pivot Tables, and also controls the charts.
Basis of RFP - Total Hours for 2020 | 323510
Forecast hours @ end of 2020 | 210492 | 188327.75
Forecast % of RFP hours | 65.07% | 58.21%
| Hours | Spend
2019 up to Q3 | 188938 | 13894912.48
2020 up to Q3 | 140328 | 8156826.26
Relative change | -25.73% | -41.3%
Hours - Pivot Table |  |  |  | Spend - Pivot Table
Row Labels | Sum of Total Exposure Hours | OT Exposure Percentage |  |  | Operations | Wells Servicing | Turnaround / Outage | Relative Overall Spend Change From Previous Year
2012 | 294667 |  |  | 2015 | 11747565.96 | 2342418 | 2801087.04 | #NUM!
2013 | 366973 |  |  | 2016 | 7578731.04 | 2780334 | 3586352.04 | -17.44%
2014 | 501678 |  |  | 2017 | 10749239.76 | 1428636.48 | 3234566.52 | 10.52%
2015 | 214572 |  |  | 2018 | 8663751.96 | 4307384.04 | 5938895.04 | 22.69%
2016 | 210544 | 14.2% |  | 2019 | 10906339.41 | 3195040.73 | 4261838.73 | -2.892%
2017 | 214925 | 13.59% |  | 2020 | 5921718.6 | 611779.48 | 1623328.18 | -41.3%
2018 | 288661 | 16.33% |  | Q1 | 2460514.44 | 341409.55 | 601815.89 | -25.56%
2019 | 248407 | 11.87% |  | Q2 | 1651411.96 | 158939.88 | 647232.29 | -44.28%
2020 | 140327.75 | 3.767% |  | Q3 | 1809792.2 | 111430.05 | 374280 | -53.27%
Q1 | 64116.25 | 6.939% |  | Grand Total | 55567346.73 | 14665592.73 | 21446067.55 | 15.97%
Q2 | 34946 | 0.1846%
Q3 | 41265.5 | 1.871%
Grand Total | 2480754.75 | 5.685%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Safety Summary
year | month | Representative Date | Quarter | Quinn Hours | DSP-Subcontractor Hours | Total Exposure Hours | Overtime Exposure Hours | Safety Meetings | Work Site Inspections | Toolbox Meetings | FLRA Cards | BBS Cards | JHA | Near Miss | Lost Time Incident | Medical Aid | First Aid | Property/Equipment Damage | Vehicle Incident | Modified Work Case | Environmental Event | Off the Job Injury/Illness2
2012 | 1 | 2012-01-01 | Q1 | 25764 |  | 25764
2012 | 2 | 2012-02-01 | Q1 | 27135 |  | 27135
2012 | 3 | 2012-03-01 | Q1 | 28391 |  | 28391
2012 | 4 | 2012-04-01 | Q2 | 22308 |  | 22308
2012 | 5 | 2012-05-01 | Q2 | 25514 |  | 25514
2012 | 6 | 2012-06-01 | Q2 | 22478 |  | 22478
2012 | 7 | 2012-07-01 | Q3 | 21384 |  | 21384
2012 | 8 | 2012-08-01 | Q3 | 23328 |  | 23328
2012 | 9 | 2012-09-01 | Q3 | 22017 |  | 22017
2012 | 10 | 2012-10-01 | Q4 | 26315 |  | 26315
2012 | 11 | 2012-11-01 | Q4 | 30596 |  | 30596
2012 | 12 | 2012-12-01 | Q4 | 19437 |  | 19437
2013 | 1 | 2013-01-01 | Q1 | 25390 | 0 | 25390
2013 | 2 | 2013-02-01 | Q1 | 25561 | 0 | 25561
2013 | 3 | 2013-03-01 | Q1 | 27031 | 0 | 27031
2013 | 4 | 2013-04-01 | Q2 | 30084 | 0 | 30084
2013 | 5 | 2013-05-01 | Q2 | 31848 | 0 | 31848
2013 | 6 | 2013-06-01 | Q2 | 27494 | 0 | 27494
2013 | 7 | 2013-07-01 | Q3 | 25051 | 0 | 25051
2013 | 8 | 2013-08-01 | Q3 | 29323 | 0 | 29323
2013 | 9 | 2013-09-01 | Q3 | 45464 | 0 | 45464
2013 | 10 | 2013-10-01 | Q4 | 44855 | 0 | 44855
2013 | 11 | 2013-11-01 | Q4 | 29067 | 0 | 29067
2013 | 12 | 2013-12-01 | Q4 | 25805 | 0 | 25805
2014 | 1 | 2014-01-01 | Q1 | 41640 |  | 41640
2014 | 2 | 2014-02-01 | Q1 | 41671 |  | 41671
2014 | 3 | 2014-03-01 | Q1 | 41699 |  | 41699
2014 | 4 | 2014-04-01 | Q2 | 41730 |  | 41730
2014 | 5 | 2014-05-01 | Q2 | 41760 |  | 41760
2014 | 6 | 2014-06-01 | Q2 | 41791 |  | 41791
2014 | 7 | 2014-07-01 | Q3 | 41821 |  | 41821
2014 | 8 | 2014-08-01 | Q3 | 41852 |  | 41852
2014 | 9 | 2014-09-01 | Q3 | 41883 |  | 41883
2014 | 10 | 2014-10-01 | Q4 | 41913 |  | 41913
2014 | 11 | 2014-11-01 | Q4 | 41944 |  | 41944
2014 | 12 | 2014-12-01 | Q4 | 41974 |  | 41974
2015 | 1 | 2015-01-01 | Q1 | 19595 | 1709 | 21304
2015 | 2 | 2015-02-01 | Q1 | 18620 | 1999 | 20619
2015 | 3 | 2015-03-01 | Q1 | 21173 | 2694 | 23867
2015 | 4 | 2015-04-01 | Q2 | 19225 | 1922 | 21147
2015 | 5 | 2015-05-01 | Q2 | 10580 | 1536 | 12116
2015 | 6 | 2015-06-01 | Q2 | 19298 | 2566 | 21864
2015 | 7 | 2015-07-01 | Q3 | 15275 | 1509 | 16784
2015 | 8 | 2015-08-01 | Q3 | 19186 | 2200 | 21386
2015 | 9 | 2015-09-01 | Q3 | 12323 | 1987 | 14310
2015 | 10 | 2015-10-01 | Q4 | 12221 | 1987 | 14208
2015 | 11 | 2015-11-01 | Q4 | 10975 | 1993 | 12968
2015 | 12 | 2015-12-01 | Q4 | 12571 | 1428 | 13999
2016 | 1 | 2016-01-01 | Q1 | 17334 | 2245 | 19579 | 3566
2016 | 2 | 2016-02-01 | Q1 | 16792 | 2120 | 18912 | 3485 | 2 | 18 | 124 | 614 | 150 |  | 1 | 0 | 0 | 1 |  | 2 | 0 | 0 | 0
2016 | 3 | 2016-03-01 | Q1 | 18011 | 2562 | 20573 | 3697 | 2 | 18 | 124 | 614 | 150 |  | 1 | 0 | 0 | 1 |  | 2 | 0 | 0 | 0
2016 | 4 | 2016-04-01 | Q2 | 17066 | 1972 | 19038 | 2965 | 1 | 18 | 128 | 526 | 136 |  | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 1
2016 | 5 | 2016-05-01 | Q2 | 16495 | 1919 | 18414 | 2095 | 1 | 19 | 98 | 511 | 131 |  | 5 | 0 | 0 | 1 |  | 3 | 0 | 0 | 0
2016 | 6 | 2016-06-01 | Q2 | 15330 | 1863 | 17193 | 1576 | 1 | 23 | 164 | 587 | 154 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 3
2016 | 7 | 2016-07-01 | Q3 | 14520 | 1264 | 15784 | 2582 | 1 | 20 | 124 | 453 | 121 |  | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 3
2016 | 8 | 2016-08-01 | Q3 | 14378 | 1748 | 16126 | 1023 | 1 | 27 | 200 | 647 | 153 |  | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 3
2016 | 9 | 2016-09-01 | Q3 | 13705 | 1876 | 15581 | 1530 | 2 | 20 | 107 | 481 | 186 |  | 1 | 0 | 0 | 0 |  | 1 | 0 | 0 | 1
2016 | 10 | 2016-10-01 | Q4 | 16405 | 2594 | 18999 | 4433 | 1 | 42 | 116 | 586 | 226 |  | 2 | 0 | 0 | 0 |  | 6 | 0 | 0 | 1
2016 | 11 | 2016-11-01 | Q4 | 14432 | 1722 | 16154 | 1312 | 1 | 15 | 127 | 491 | 136 |  | 2 | 0 | 0 | 0 |  | 2 | 0 | 0 | 4
2016 | 12 | 2016-12-01 | Q4 | 12726 | 1465 | 14191 | 1638 | 1 | 24 | 115 | 461 | 115 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
2017 | 1 | 2017-01-01 | Q1 | 14632 | 1855 | 16487 | 1518 | 1 | 23 | 160 | 492 | 177 |  | 1 | 0 | 0 | 0 |  | 4 | 0 | 0 | 0
2017 | 2 | 2017-02-01 | Q1 | 14473 | 1761 | 16234 | 2507 | 1 | 26 | 115 | 509 | 157 |  | 3 | 0 | 0 | 0 |  | 6 | 0 | 0 | 0
2017 | 3 | 2017-03-01 | Q1 | 16343 | 2048 | 18391 | 2093 | 1 | 21 | 115 | 450 | 151 |  | 0 | 0 | 0 | 1 |  | 2 | 0 | 1 | 0
2017 | 4 | 2017-04-01 | Q2 | 17532 | 1980 | 19512 | 4554 | 1 | 28 | 129 | 460 | 152 |  | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 3
2017 | 5 | 2017-05-01 | Q2 | 19257 | 1822 | 21079 | 3487 | 6 | 52 | 146 | 604 | 158 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2
2017 | 6 | 2017-06-01 | Q2 | 19722 | 2026 | 21748 | 4678 | 1 | 28 | 300 | 581 | 185 |  | 0 | 0 | 0 | 2 |  | 1 | 0 | 0 | 1
2017 | 7 | 2017-07-01 | Q3 | 15712 | 1485 | 17197 | 1761 | 7 | 17 | 124 | 500 | 154 |  | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 1
2017 | 8 | 2017-08-01 | Q3 | 17418 | 1525 | 18943 | 2452 | 1 | 11 | 135 | 487 | 178 |  | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 3
2017 | 9 | 2017-09-01 | Q3 | 15912 | 1536 | 17448 | 2514 | 1 | 39 | 206 | 526 | 191 |  | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 2
2017 | 10 | 2017-10-01 | Q4 | 16122 | 1822 | 17944 | 1765 | 1 | 44 | 153 | 532 | 169 |  | 1 | 0 | 0 | 1 |  | 3 | 0 | 0 | 1
2017 | 11 | 2017-11-01 | Q4 | 14519 | 1323 | 15842 | 627 | 1 | 27 | 138 | 444 | 149 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1
2017 | 12 | 2017-12-01 | Q4 | 12841 | 1259 | 14100 | 1263 | 1 | 20 | 105 | 397 | 212 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1
2018 | 1 | 2018-01-01 | Q1 | 18795 |  | 18795 | 2253 | 1 | 63 | 178 | 439 | 260 |  | 1 | 0 | 0 | 1 |  | 1 | 0 | 0 | 3
2018 | 2 | 2018-02-01 | Q1 | 18789 |  | 18789 | 2439 | 1 | 16 | 108 | 436 | 250 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5
2018 | 3 | 2018-03-01 | Q1 | 21377 |  | 21377 | 1899 | 1 | 47 | 172 | 669 | 299 |  | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 2
2018 | 4 | 2018-04-01 | Q2 | 32020 |  | 32020 | 7439.5 | 2 | 80 | 202 | 845 | 232 |  | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1
2018 | 5 | 2018-05-01 | Q2 | 21344 |  | 21344 | 2465 | 1 | 23 | 160 | 509 | 152 |  | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2
2018 | 6 | 2018-06-01 | Q2 | 21033 |  | 21033 | 3018 | 1 | 52 | 172 | 652 | 219 |  | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 3
2018 | 7 | 2018-07-01 | Q3 | 23406 |  | 23406 | 3702 | 1 | 91 | 179 | 581 | 216 |  | 0 | 0 | 1 | 0 |  | 1 | 0 | 0 | 0
2018 | 8 | 2018-08-01 | Q3 | 24132 |  | 24132 | 2013 | 1 | 42 | 158 | 631 | 226 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2018 | 9 | 2018-09-01 | Q3 | 38775 |  | 38775 | 11995.5 | 2 | 65 | 187 | 714 | 240 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3
2018 | 10 | 2018-10-01 | Q4 | 30050 |  | 30050 | 6350 | 2 | 55 | 228 | 763 | 235 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
2018 | 11 | 2018-11-01 | Q4 | 19768 |  | 19768 | 1542 | 1 | 21 | 177 | 678 | 218 |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1
2018 | 12 | 2018-12-01 | Q4 | 19172 |  | 19172 | 2008 | 1 | 18 | 142 | 507 | 193 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
2019 | 1 | 2019-01-01 | Q1 | 20310 |  | 20310 | 802 | 1 | 33 | 165 | 619 | 213 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
2019 | 2 | 2019-02-01 | Q1 | 16464.5 |  | 16464.5 | 418 | 1 | 22 | 145 | 487 | 170 |  | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0
2019 | 3 | 2019-03-01 | Q1 | 18973.5 |  | 18973.5 | 1948 | 1 | 22 | 155 | 563 | 253 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
2019 | 4 | 2019-04-01 | Q2 | 21623 |  | 21623 | 2829 | 1 | 64 | 167 | 744 | 216 |  | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0
2019 | 5 | 2019-05-01 | Q2 | 19034.5 |  | 19034.5 | 957 | 0 | 12 | 135 | 495 | 223 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
2019 | 6 | 2019-06-01 | Q2 | 27587.5 |  | 27587.5 | 7191 | 4 | 11 | 306 | 847 | 179 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2019 | 7 | 2019-07-01 | Q3 | 26749 |  | 26749 | 5688 | 0 | 16 | 241 | 524 | 152 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
2019 | 8 | 2019-08-01 | Q3 | 19797.5 |  | 19797.5 | 1574 | 2 | 41 | 135 | 468 | 140 |  | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0
2019 | 9 | 2019-09-01 | Q3 | 18398 |  | 18398 | 1552 | 4 | 9 | 182 | 416 | 126 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
2019 | 10 | 2019-10-01 | Q4 | 19221 |  | 19221 | 1636 | 1 | 6 | 31 | 950 | 130 |  | 1 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0
2019 | 11 | 2019-11-01 | Q4 | 19669 |  | 19669 | 2661 | 2 | 8 | 112 | 434 | 159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2019 | 12 | 2019-12-01 | Q4 | 20579.5 |  | 20579.5 | 2240 | 3 | 9 | 134 | 511 | 138 |  | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0
2020 | 1 | 2020-01-01 | Q1 | 23228.5 |  | 23228.5 | 1660.5 | 1 | 12 | 184 | 539 | 194 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
2020 | 2 | 2020-02-01 | Q1 | 19043.75 |  | 19043.75 | 824.25 | 1 | 10 | 140 | 461 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
2020 | 3 | 2020-03-01 | Q1 | 21844 |  | 21844 | 1964.5 | 1 | 14 | 216 | 472 | 57 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 4 | 2020-04-01 | Q2 | 12262 |  | 12262 | 0 | 1 | 15 | 99 | 293 | 107 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 5 | 2020-05-01 | Q2 | 10168 |  | 10168 | 31.5 | 2 | 13 | 210 | 237 | 166 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 6 | 2020-06-01 | Q2 | 12516 |  | 12516 | 33 | 0 | 13 | 112 | 339 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 7 | 2020-07-01 | Q3 | 12635 |  | 12635 | 47 | 2 | 18 | 97 | 344 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 8 | 2020-08-01 | Q3 | 13902.5 |  | 13902.5 | 172 | 2 | 20 | 101 | 400 | 176 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 9 | 2020-09-01 | Q3 | 14728 |  | 14728 | 553 | 2 | 5 | 94 | 360 | 126 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0
2020 | 10 | 2020-10-01 | Q4 |  |  | 0
2020 | 11 | 2020-11-01 | Q4 |  |  | 0
2020 | 12 | 2020-12-01 | Q4 |  |  | 0
Formulas:
Representative Date = DATE(SafetySummary[[#This Row],[year]],SafetySummary[[#This Row],[month]],1)
Note on L1: Joel Brochu: Also known as "Pre-Task Analysis Cards"
Note on M1: Joel Brochu: Also known as "Behaviour Based Safety Observations"
Note on Q101: Joel Brochu: 4/27/2020 - Lifted water tank slipped off cat bar, pinching worker's finger between two skids. 7 sutures.
Note on Q105: Joel Brochu: 8/22/2020 - Pinch between AWP rail and impact gun.
Note on Q106: Joel Brochu: 9/23/2020 - Worker slipped while walking down a berm.

## Quality Summary
year | month | Representative Date | Quarter | Rework | NCRs | Total Welds | Total Butt Welds | Total Butt Weld Repairs | Total Socket Welds | Total Attachment Welds | Packages: Signed off by Quinn / in CNRL Review | Packages: In Review by Quinn | Outstanding | Packages: Completed and Scanned
2012 | 1 | 2012-01-01 | Q1 | 0
2012 | 2 | 2012-02-01 | Q1
2012 | 3 | 2012-03-01 | Q1
2012 | 4 | 2012-04-01 | Q2
2012 | 5 | 2012-05-01 | Q2
2012 | 6 | 2012-06-01 | Q2
2012 | 7 | 2012-07-01 | Q3
2012 | 8 | 2012-08-01 | Q3
2012 | 9 | 2012-09-01 | Q3
2012 | 10 | 2012-10-01 | Q4
2012 | 11 | 2012-11-01 | Q4
2012 | 12 | 2012-12-01 | Q4
2013 | 1 | 2013-01-01 | Q1
2013 | 2 | 2013-02-01 | Q1 | [9 empty] | 230 | 318
2013 | 3 | 2013-03-01 | Q1 | [9 empty] | 230 | 318
2013 | 4 | 2013-04-01 | Q2 | [9 empty] | 96 | 340
2013 | 5 | 2013-05-01 | Q2 | [9 empty] | 96 | 340
2013 | 6 | 2013-06-01 | Q2
2013 | 7 | 2013-07-01 | Q3 | [7 empty] | 359 | 77 |  | 304
2013 | 8 | 2013-08-01 | Q3 | [7 empty] | 359 | 78 |  | 304
2013 | 9 | 2013-09-01 | Q3 | [7 empty] | 359 | 78 |  | 304
2013 | 10 | 2013-10-01 | Q4 | [7 empty] | 359 | 78 |  | 326
2013 | 11 | 2013-11-01 | Q4 | [7 empty] | 359 | 78 |  | 329
2013 | 12 | 2013-12-01 | Q4 | [7 empty] | 25 | 78 |  | 334
2014 | 1 | 2014-01-01 | Q1
2014 | 2 | 2014-02-01 | Q1 | [9 empty] | 370 | 347
2014 | 3 | 2014-03-01 | Q1 | [9 empty] | 370 | 347
2014 | 4 | 2014-04-01 | Q2 | [9 empty] | 197 | 331
2014 | 5 | 2014-05-01 | Q2 | [9 empty] | 197 | 331
2014 | 6 | 2014-06-01 | Q2
2014 | 7 | 2014-07-01 | Q3 | [7 empty] | 342 | 186 |  | 261
2014 | 8 | 2014-08-01 | Q3 | [7 empty] | 343 | 189 |  | 261
2014 | 9 | 2014-09-01 | Q3 | [7 empty] | 343 | 189 |  | 261
2014 | 10 | 2014-10-01 | Q4 | [7 empty] | 343 | 189 |  | 262
2014 | 11 | 2014-11-01 | Q4 | [7 empty] | 344 | 188 |  | 275
2014 | 12 | 2014-12-01 | Q4 | [7 empty] | 63 | 187 |  | 283
2015 | 1 | 2015-01-01 | Q1
2015 | 2 | 2015-02-01 | Q1 | [9 empty] | 289 | 263
2015 | 3 | 2015-03-01 | Q1 | [9 empty] | 289 | 263
2015 | 4 | 2015-04-01 | Q2 | [9 empty] | 55 | 294
2015 | 5 | 2015-05-01 | Q2 | [9 empty] | 4 | 299
2015 | 6 | 2015-06-01 | Q2
2015 | 7 | 2015-07-01 | Q3 | [7 empty] | 309 | 70 |  | 202
2015 | 8 | 2015-08-01 | Q3 | [7 empty] | 309 | 80 |  | 202
2015 | 9 | 2015-09-01 | Q3 |  |  | 142 | 95 | 3 | 47 |  | 309 | 80 |  | 202
2015 | 10 | 2015-10-01 | Q4 |  |  | 176 | 73 |  | 103 |  | 311 | 79 |  | 203
2015 | 11 | 2015-11-01 | Q4 |  |  | 262 | 165 | 1 | 97 |  | 316 | 75 |  | 214
2015 | 12 | 2015-12-01 | Q4 |  |  | 59 | 59 |  |  |  | 100 | 75 |  | 219
2016 | 1 | 2016-01-01 | Q1 |  |  | 252 | 102 | 1 | 150
2016 | 2 | 2016-02-01 | Q1 |  |  | 187 | 161 | 3 | 26 |  |  |  | 42 | 14
2016 | 3 | 2016-03-01 | Q1 |  |  | 193 | 186 | 2 | 7 |  |  |  | 42 | 14
2016 | 4 | 2016-04-01 | Q2 |  |  | 145 | 129 | 4 | 16 |  |  |  | 53 | 45
2016 | 5 | 2016-05-01 | Q2 |  |  | 224 | 217 |  | 7 |  |  |  | 13 | 94
2016 | 6 | 2016-06-01 | Q2 |  |  | 140 | 87 |  | 53
2016 | 7 | 2016-07-01 | Q3 |  |  | 128 | 125 |  | 3 |  | 115 | 27 |  | 17
2016 | 8 | 2016-08-01 | Q3 |  |  | 33 | 33 |  |  |  | 142 | 26 |  | 17
2016 | 9 | 2016-09-01 | Q3 |  |  | 5 | 4 |  | 1 |  | 151 | 49 |  | 25
2016 | 10 | 2016-10-01 | Q4 |  |  | 0 |  |  |  |  | 157 | 46 |  | 25
2016 | 11 | 2016-11-01 | Q4 |  |  | 0 |  |  |  |  | 176 | 46 |  | 31
2016 | 12 | 2016-12-01 | Q4 |  |  | 0 |  |  |  |  | 131 | 56 |  | 50
2017 | 1 | 2017-01-01 | Q1 |  | 5 | 136 | 136 | 1 |  |  | 4 | 0 |  | 0
2017 | 2 | 2017-02-01 | Q1 |  |  | 181 | 181 | 4 |  |  | 17 | 0 |  | 0
2017 | 3 | 2017-03-01 | Q1 |  |  | 190 | 190 | 4 |  |  | 32 | 4 |  | 0
2017 | 4 | 2017-04-01 | Q2 |  |  | 152 | 152 | 2 |  |  | 53 | 3 |  | 9
2017 | 5 | 2017-05-01 | Q2 |  |  | 55 | 55 | 2 |  |  | 65 | 4 |  | 18
2017 | 6 | 2017-06-01 | Q2 |  |  | 65 | 65 | 2 |  |  | 106 | 6 |  | 33
2017 | 7 | 2017-07-01 | Q3 |  |  | 97 | 97 | 4 |  |  | 144 | 8 |  | 38
2017 | 8 | 2017-08-01 | Q3 |  |  | 100 | 100 | 0 |  |  | 157 | 22 |  | 52
2017 | 9 | 2017-09-01 | Q3 |  |  | 74 | 74 | 1 |  |  | 158 | 9 |  | 84
2017 | 10 | 2017-10-01 | Q4 |  |  | 38 | 38 | 0 |  |  | 162 | 12 |  | 115
2017 | 11 | 2017-11-01 | Q4 |  |  | 35 | 35 | 0 |  |  | 139 | 12 |  | 179
2017 | 12 | 2017-12-01 | Q4 |  |  | 42 | 42 | 0 |  |  | 155 | 11 |  | 186
2018 | 1 | 2018-01-01 | Q1 |  | 2 | 81 | 66 | 1 | 15 |  | 4 | 0 |  | 5
2018 | 2 | 2018-02-01 | Q1 |  |  | 98 | 95 | 5 | 3 |  | 19 | 2 |  | 19
2018 | 3 | 2018-03-01 | Q1 |  |  | 166 | 111 | 0 | 55 |  | 27 | 4 |  | 21
2018 | 4 | 2018-04-01 | Q2 |  |  | 402 | 153 | 5 | 249 |  | 36 | 11 |  | 27
2018 | 5 | 2018-05-01 | Q2 |  |  | 122 | 34 | 1 | 88 |  | 53 | 16 |  | 27
2018 | 6 | 2018-06-01 | Q2 |  |  | 123 | 50 | 0 | 73 |  | 50 | 38 |  | 45
2018 | 7 | 2018-07-01 | Q3 |  |  | 143 | 61 | 0 | 82 |  | 84 | 38 |  | 45
2018 | 8 | 2018-08-01 | Q3 |  |  | 165 | 111 | 1 | 54 |  | 93 | 42 |  | 58
2018 | 9 | 2018-09-01 | Q3 |  |  | 474 | 151 | 2 | 323 |  | 93 | 53 |  | 76
2018 | 10 | 2018-10-01 | Q4 |  |  | 663 | 175 | 8 | 488 |  | 159 | 50 |  | 122
2018 | 11 | 2018-11-01 | Q4 |  |  | 90 | 28 | 1 | 62 |  | 161 | 60 |  | 154
2018 | 12 | 2018-12-01 | Q4 |  |  | 339 | 122 | 6 | 217 |  | 196 | 59 |  | 162
2019 | 1 | 2019-01-01 | Q1 |  | 0 | 319 | 161 | 2 | 158 |  | 343 | 78 |  | 53
2019 | 2 | 2019-02-01 | Q1 |  | 0 | 187 | 24 | 1 | 163 |  | 370 | 65 |  | 67
2019 | 3 | 2019-03-01 | Q1 |  | 0 | 410 | 70 | 0 | 340 |  | 353 | 74 |  | 94
2019 | 4 | 2019-04-01 | Q2 |  | 0 | 341 | 170 | 4 | 171 |  | 357 | 78 |  | 118
2019 | 5 | 2019-05-01 | Q2 |  | 0 | 199 | 125 | 1 | 74 |  | 360 | 50 |  | 169
2019 | 6 | 2019-06-01 | Q2 |  | 0 | 896 | 184 | 1 | 712 |  | 381 | 56 |  | 177
2019 | 7 | 2019-07-01 | Q3 |  | 0 | 565 | 194 | 3 | 371 |  | 422 | 62 |  | 182
2019 | 8 | 2019-08-01 | Q3 |  | 0 | 260 | 172 | 9 | 88 |  | 404 | 67 |  | 188
2019 | 9 | 2019-09-01 | Q3 |  | 0 | 154 | 25 | 0 | 129 |  | 418 | 80 |  | 208
2019 | 10 | 2019-10-01 | Q4 |  | 0 | 150 | 100 | 3 | 50 |  | 422 | 82 |  | 237
2019 | 11 | 2019-11-01 | Q4 |  | 0 | 182 | 156 | 6 | 26 |  | 456 | 110 |  | 268
2019 | 12 | 2019-12-01 | Q4 |  | 0 | 320 | 212 | 6 | 108 |  | 531 | 106 |  | 278
2020 | 1 | 2020-01-01 | Q1 |  | 0 | 279 | 145 | 1 | 134 |  | 425 | 66 |  | 14
2020 | 2 | 2020-02-01 | Q1 |  | 0 | 199 | 45 | 1 | 154 |  | 389 | 71 |  | 83
2020 | 3 | 2020-03-01 | Q1 |  | 0 | 55 | 14 | 1 | 41 |  | 345 | 112 |  | 148
2020 | 4 | 2020-04-01 | Q2 |  | 0 | 71 | 47 | 1 | 24 |  | 254 | 144 |  | 235
2020 | 5 | 2020-05-01 | Q2 |  | 0 | 25 | 15 | 0 | 10 |  | 254 | 144 |  | 235
2020 | 6 | 2020-06-01 | Q2 |  | 0 | 102 | 99 | 2 | 3 |  | 256 | 146 |  | 235
2020 | 7 | 2020-07-01 | Q3 |  | 0 | 53 | 19 | 0 | 34 |  | 256 | 147 |  | 235
2020 | 8 | 2020-08-01 | Q3 |  | 0 | 59 | 46 | 0 | 13 |  | 257 | 118 |  | 269
2020 | 9 | 2020-09-01 | Q3 |  | 0 | 98 | 70 | 0 | 28 |  | 269 | 65 |  | 328
2020 | 10 | 2020-10-01 | Q4
2020 | 11 | 2020-11-01 | Q4
2020 | 12 | 2020-12-01 | Q4
Formulas:
Representative Date = DATE(OperationalSummary[[#This Row],[year]],OperationalSummary[[#This Row],[month]],1)
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total welds invlovled mutliple types of welds which was broken down in 2019
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - Outstanding involves both packages pending CNRL & QUINN review. - This category is later divided into two (Signed off/CNRL Review and In Review by QUINN).
Note on F62: Joel Brochu: Number carried from Q12020 dashboard.
Note on F74: Joel Brochu: 9/24/2020 - number carried from Q12020 dashboard.
Note on F86: Joel Brochu: Number carried from Q12020 dashboard.
Note on L86: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M86: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O86: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L87: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M87: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O87: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L88: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M88: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O88: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L89: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M89: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O89: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L90: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M90: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O90: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L91: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M91: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O91: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L92: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M92: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O92: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L93: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M93: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O93: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L94: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M94: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O94: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L95: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M95: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O95: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L96: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M96: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O96: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L97: Joel Brochu: Updated with total of 2015-2019 packages.
Note on M97: Joel Brochu: Updated with total of 2015-2019 packages.
Note on O97: Joel Brochu: Updated with total of 2015-2019 packages.
Note on L98: Joel Brochu: Updated with total of 2016-2020 packages
Note on M98: Joel Brochu: Updated with total of 2016-2020 packages
Note on O98: Joel Brochu: Updated with total of 2016-2020 packages
Note on L99: Joel Brochu: Updated with total of 2016-2020 packages
Note on M99: Joel Brochu: Updated with total of 2016-2020 packages
Note on O99: Joel Brochu: Updated with total of 2016-2020 packages
Note on L100: Joel Brochu: Updated with total of 2016-2020 packages
Note on M100: Joel Brochu: Updated with total of 2016-2020 packages
Note on O100: Joel Brochu: Updated with total of 2016-2020 packages
Note on L101: Joel Brochu: Updated with total of 2016-2020 packages
Note on M101: Joel Brochu: Updated with total of 2016-2020 packages
Note on O101: Joel Brochu: Updated with total of 2016-2020 packages
Note on L102: Joel Brochu: Updated with total of 2016-2020 packages
Note on M102: Joel Brochu: Updated with total of 2016-2020 packages
Note on O102: Joel Brochu: Updated with total of 2016-2020 packages
Note on L103: Joel Brochu: Updated with total of 2016-2020 packages
Note on M103: Joel Brochu: Updated with total of 2016-2020 packages
Note on O103: Joel Brochu: Updated with total of 2016-2020 packages
Note on L104: Joel Brochu: Updated with total of 2016-2020 packages
Note on M104: Joel Brochu: Updated with total of 2016-2020 packages
Note on O104: Joel Brochu: Updated with total of 2016-2020 packages
Note on L105: Joel Brochu: Updated with total of 2016-2020 packages
Note on M105: Joel Brochu: Updated with total of 2016-2020 packages
Note on O105: Joel Brochu: Updated with total of 2016-2020 packages
Note on L106: Joel Brochu: Updated with total of 2016-2020 packages
Note on M106: Joel Brochu: Updated with total of 2016-2020 packages
Note on O106: Joel Brochu: Updated with total of 2016-2020 packages

## Spend
year | month | Representative Date | Quarter | Spend_Operations | Spend_Wells_Servicing | Spend_Turnaround_Outage
2012 | 1 | 2012-01-01 | Q1
2012 | 2 | 2012-02-01 | Q1
2012 | 3 | 2012-03-01 | Q1
2012 | 4 | 2012-04-01 | Q2
2012 | 5 | 2012-05-01 | Q2
2012 | 6 | 2012-06-01 | Q2
2012 | 7 | 2012-07-01 | Q3
2012 | 8 | 2012-08-01 | Q3
2012 | 9 | 2012-09-01 | Q3
2012 | 10 | 2012-10-01 | Q4
2012 | 11 | 2012-11-01 | Q4
2012 | 12 | 2012-12-01 | Q4
2013 | 1 | 2013-01-01 | Q1
2013 | 2 | 2013-02-01 | Q1
2013 | 3 | 2013-03-01 | Q1
2013 | 4 | 2013-04-01 | Q2
2013 | 5 | 2013-05-01 | Q2
2013 | 6 | 2013-06-01 | Q2
2013 | 7 | 2013-07-01 | Q3
2013 | 8 | 2013-08-01 | Q3
2013 | 9 | 2013-09-01 | Q3
2013 | 10 | 2013-10-01 | Q4
2013 | 11 | 2013-11-01 | Q4
2013 | 12 | 2013-12-01 | Q4
2014 | 1 | 2014-01-01 | Q1
2014 | 2 | 2014-02-01 | Q1
2014 | 3 | 2014-03-01 | Q1
2014 | 4 | 2014-04-01 | Q2
2014 | 5 | 2014-05-01 | Q2
2014 | 6 | 2014-06-01 | Q2
2014 | 7 | 2014-07-01 | Q3
2014 | 8 | 2014-08-01 | Q3
2014 | 9 | 2014-09-01 | Q3
2014 | 10 | 2014-10-01 | Q4
2014 | 11 | 2014-11-01 | Q4
2014 | 12 | 2014-12-01 | Q4
2015 | 1 | 2015-01-01 | Q1 | 978963.83 | 195201.5 | 233423.92
2015 | 2 | 2015-02-01 | Q1 | 978963.83 | 195201.5 | 233423.92
2015 | 3 | 2015-03-01 | Q1 | 978963.83 | 195201.5 | 233423.92
2015 | 4 | 2015-04-01 | Q2 | 978963.83 | 195201.5 | 233423.92
2015 | 5 | 2015-05-01 | Q2 | 978963.83 | 195201.5 | 233423.92
2015 | 6 | 2015-06-01 | Q2 | 978963.83 | 195201.5 | 233423.92
2015 | 7 | 2015-07-01 | Q3 | 978963.83 | 195201.5 | 233423.92
2015 | 8 | 2015-08-01 | Q3 | 978963.83 | 195201.5 | 233423.92
2015 | 9 | 2015-09-01 | Q3 | 978963.83 | 195201.5 | 233423.92
2015 | 10 | 2015-10-01 | Q4 | 978963.83 | 195201.5 | 233423.92
2015 | 11 | 2015-11-01 | Q4 | 978963.83 | 195201.5 | 233423.92
2015 | 12 | 2015-12-01 | Q4 | 978963.83 | 195201.5 | 233423.92
2016 | 1 | 2016-01-01 | Q1 | 631560.92 | 231694.5 | 298862.67
2016 | 2 | 2016-02-01 | Q1 | 631560.92 | 231694.5 | 298862.67
2016 | 3 | 2016-03-01 | Q1 | 631560.92 | 231694.5 | 298862.67
2016 | 4 | 2016-04-01 | Q2 | 631560.92 | 231694.5 | 298862.67
2016 | 5 | 2016-05-01 | Q2 | 631560.92 | 231694.5 | 298862.67
2016 | 6 | 2016-06-01 | Q2 | 631560.92 | 231694.5 | 298862.67
2016 | 7 | 2016-07-01 | Q3 | 631560.92 | 231694.5 | 298862.67
2016 | 8 | 2016-08-01 | Q3 | 631560.92 | 231694.5 | 298862.67
2016 | 9 | 2016-09-01 | Q3 | 631560.92 | 231694.5 | 298862.67
2016 | 10 | 2016-10-01 | Q4 | 631560.92 | 231694.5 | 298862.67
2016 | 11 | 2016-11-01 | Q4 | 631560.92 | 231694.5 | 298862.67
2016 | 12 | 2016-12-01 | Q4 | 631560.92 | 231694.5 | 298862.67
2017 | 1 | 2017-01-01 | Q1 | 895769.98 | 119053.04 | 269547.21
2017 | 2 | 2017-02-01 | Q1 | 895769.98 | 119053.04 | 269547.21
2017 | 3 | 2017-03-01 | Q1 | 895769.98 | 119053.04 | 269547.21
2017 | 4 | 2017-04-01 | Q2 | 895769.98 | 119053.04 | 269547.21
2017 | 5 | 2017-05-01 | Q2 | 895769.98 | 119053.04 | 269547.21
2017 | 6 | 2017-06-01 | Q2 | 895769.98 | 119053.04 | 269547.21
2017 | 7 | 2017-07-01 | Q3 | 895769.98 | 119053.04 | 269547.21
2017 | 8 | 2017-08-01 | Q3 | 895769.98 | 119053.04 | 269547.21
2017 | 9 | 2017-09-01 | Q3 | 895769.98 | 119053.04 | 269547.21
2017 | 10 | 2017-10-01 | Q4 | 895769.98 | 119053.04 | 269547.21
2017 | 11 | 2017-11-01 | Q4 | 895769.98 | 119053.04 | 269547.21
2017 | 12 | 2017-12-01 | Q4 | 895769.98 | 119053.04 | 269547.21
2018 | 1 | 2018-01-01 | Q1 | 721979.33 | 358948.67 | 494907.92
2018 | 2 | 2018-02-01 | Q1 | 721979.33 | 358948.67 | 494907.92
2018 | 3 | 2018-03-01 | Q1 | 721979.33 | 358948.67 | 494907.92
2018 | 4 | 2018-04-01 | Q2 | 721979.33 | 358948.67 | 494907.92
2018 | 5 | 2018-05-01 | Q2 | 721979.33 | 358948.67 | 494907.92
2018 | 6 | 2018-06-01 | Q2 | 721979.33 | 358948.67 | 494907.92
2018 | 7 | 2018-07-01 | Q3 | 721979.33 | 358948.67 | 494907.92
2018 | 8 | 2018-08-01 | Q3 | 721979.33 | 358948.67 | 494907.92
2018 | 9 | 2018-09-01 | Q3 | 721979.33 | 358948.67 | 494907.92
2018 | 10 | 2018-10-01 | Q4 | 721979.33 | 358948.67 | 494907.92
2018 | 11 | 2018-11-01 | Q4 | 721979.33 | 358948.67 | 494907.92
2018 | 12 | 2018-12-01 | Q4 | 721979.33 | 358948.67 | 494907.92
2019 | 1 | 2019-01-01 | Q1 | 642257.09 | 296172.73 | 192913.02
2019 | 2 | 2019-02-01 | Q1 | 365925.26 | 99682.36 | 212381.86
2019 | 3 | 2019-03-01 | Q1 | 1998679.96 | 231966.21 | 532203.5
2019 | 4 | 2019-04-01 | Q2 | 1139456.18 | 704322.41 | 187335.2
2019 | 5 | 2019-05-01 | Q2 | 869717.52 | 226011.29 | 75173.31
2019 | 6 | 2019-06-01 | Q2 | 542611.35 | 236878.33 | 429054.97
2019 | 7 | 2019-07-01 | Q3 | 674678.6 | 291267.11 | 223412.25
2019 | 8 | 2019-08-01 | Q3 | 1034473.87 | 469527.25 | 536945.28
2019 | 9 | 2019-09-01 | Q3 | 539723.41 | 291624.18 | 850517.98
2019 | 10 | 2019-10-01 | Q4 | 1138487.27 | 240443.05 | 85233.29
2019 | 11 | 2019-11-01 | Q4 | 784355.53 | 59678.87 | 789705.23
2019 | 12 | 2019-12-01 | Q4 | 1175973.37 | 47466.94 | 146962.84
2020 | 1 | 2020-01-01 | Q1 | 1032653.66 | 51128.66 | 283234.65
2020 | 2 | 2020-02-01 | Q1 | 838128.86 | 170488.01 | 220750.93
2020 | 3 | 2020-03-01 | Q1 | 589731.92 | 119792.88 | 97830.31
2020 | 4 | 2020-04-01 | Q2 | 1087824.66 | 48791.76 | 556194.02
2020 | 5 | 2020-05-01 | Q2 | 506227.11 | 37351.38 | 89507.49
2020 | 6 | 2020-06-01 | Q2 | 57360.19 | 72796.74 | 1530.78
2020 | 7 | 2020-07-01 | Q3 | 632597.86 | 82590.51 | 18316.26
2020 | 8 | 2020-08-01 | Q3 | 1154035.81 | 28839.54 | 355963.74
2020 | 9 | 2020-09-01 | Q3 | 23158.53 | 0 | 0
2020 | 10 | 2020-10-01 | Q4
2020 | 11 | 2020-11-01 | Q4
2020 | 12 | 2020-12-01 | Q4
Formulas:
Representative Date = DATE(SafetySummary[[#This Row],[year]],SafetySummary[[#This Row],[month]],1)
Note on C103: Joel Brochu: Checked with Trevan - numbers are accurate, may have to do with delayed invoices. Value represents what was incurred that month through the invoice process.
Note on E106: Joel Brochu: Numbers as of Oct 19, 2020. Unsure why Maximo is reporting so low. May need to re-visit.
Note on F106: Joel Brochu: Numbers as of Oct 19, 2020. Unsure why Maximo is reporting so low. May need to re-visit.
Note on G106: Joel Brochu: Numbers as of Oct 19, 2020. Unsure why Maximo is reporting so low. May need to re-visit.